## Milestone Log
Foundation Regulatory Frameworks - Joint Industry Plan - Milestone Log
ID | Title | Project/Topic | Type | Milestone Date | Date Status | Owner | Level | Description | Dependencies | Status/Comments
JM-001 | Minister Approves Tranche 1-3 Rule Changes | Regulatory | Significant Market Milestone | Nov-Dec-20 | Confirmed | ETIU | 0 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Tranche 1 (Nov-20): Generator Performance Standards Framework (incl. Ch. 3a, Appendix 12, and transitional rules) ‘Administrative Package’ Frequency Operating Standards and Contingency Events Frameworks Tranche 2 (Dec-20): Foundation Market Parameters (incl. STEM) Frequency Co-optimised ESS Operating States and Tech Envelope Scheduling and Dispatch Outage Management and Commissioning Tests Operational Planning (PASA) WEM Monitoring and Compliance Market Settlement Tranche 3 (Dec-20): Reserve Capacity Mechanism (RCM) Prioritisation and Network Access Quantities Framework Participation of storage and hybrid facilities in the RCM RCM changes consequential to SCED Application and Queuing Policy for Constrained Network Access |  | On Track - all three Tranches published for consultation in October 20
JM-002 | Market Trial Commences | Program/Implementation | Significant Market Milestone | 2022-04-01 | To Be Confirmed | AEMO | 0 | Commencement of 'formal' Market Trial period where Market Participants and other parties will conduct defined end-to-end scenario based trials e.g. as opposed to purely system/user integration testing). |  | Scope of Market Trial and Dates to be developed via WRIG
JM-003 | SCED Go Live | Program/Implementation | Significant Market Milestone | 2022-10-01 | Confirmed | AEMO | 0 | Date on which first interval of Security Constrained Economic Dispatch (SCED) will take place in line with commencement of relevant WEM Rule Modifications and Go Live date referenced in WEM Rule 1.20. |  | Specific scope of Go Live milestone to be refined and defined via WRIG
JM-004 | Limit Advice Requirements Procedure Consultation Start | Constraints | WEM Procedure Milestone | 2020-10-13 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-005 | Constraint Formulation Procedure Consultation Start | Constraints | WEM Procedure Milestone | 2020-10-13 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-006 | Constraint Information Resource Procedure Consultation Start | Constraints | WEM Procedure Milestone | 2020-11-05 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-007 | Real Time Market – Dispatch Instructions & Conversions Procedure Consultation Start | WEMDE/Dispatch | WEM Procedure Milestone | 2020-10-29 | Complete | AEMO | 2 | AEMO will commence first stage 'informal' consultation process on WEM Procedure topic
JM-008 | Constraint Information Resource Procedure Live | Constraints | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-009 | Limit Advice Requirements Procedure Live | Constraints | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-010 | Constraint Equation Development Procedure Live | Constraints | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-011 | Real Time Market – Dispatch Instructions & Conversions Live | WEMDE/Dispatch | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-012 | GPS Testing Requirements Procedures Consultation Start | GPS | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 2 | AEMO will commence first stage 'informal' consultation process on WEM Procedure topic
JM-013 | GPS Monitoring Plan & Template Procedures Consultation Start | GPS | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-014 | GPS Process & Transition Considerations Procedures Consultation Start | GPS | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-015 | GPS Testing Requirements Procedures Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-016 | GPS Monitoring Plan & Template Procedures Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-017 | GPS Process & Transition Considerations Procedures Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-018 | Credible Contingency Events Procedure Consultation Start | System Planning (e.g. Outages, PASA) | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-019 | Credible Contingency Events Procedure Consultation Live | System Planning (e.g. Outages, PASA) | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-020 | WEMDE Interface Details Available | WEMDE/Dispatch | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-021 | Bids & Offers Interface Details Available | WEMDE/Dispatch | Technical Information Release | 2021-05-01 | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-022 | Settlements (Reform) Interface Details Available | Settlements | Technical Information Release | 2021-07-01 | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-023 | Outage Management Interface Details Available | System Planning (e.g. Outages, PASA) | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-024 | Commissioning Test Interface Details Available | System Planning (e.g. Outages, PASA) | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-025 | PASA Interface Details Available | System Planning (e.g. Outages, PASA) | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-026 | STEM Interface Details Available | STEM | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-027 | Registration Interface Details Available | Registrations | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-028 | GPS Market Trial | GPS | Technical Information Release | 2021-05-05 | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-029 | AEMO GPS Repository Live | GPS | Technical Go-Live | 2021-05-30 | To Be Confirmed | AEMO | 1 | GPS Repository completes formal testing and moves to Production environment.
JM-030 | Minister Approves Tranche 4-5 Rule Changes | Regulatory | Significant Market Milestone | 2021-04-01 | To Be Confirmed | ETIU | 0 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Tranche 4: Transitional Arrangements (e.g. ESS accreditation) Tranche 5: Non-Cooptimised ESS Framework Market Information Framework Market Power Mitigation Reliability Standards Framework Participation and Registration framework
JM-031 | WP Connection Process - connection application form updated for constrained access | Connections | Business Process | 2021-06-30 | To Be Confirmed | Western Power | 1 | Updated customer connection application form (including information for generator performance standards), Fact sheets, Hard copy and Online
JM-032 | WP Connection Process - Applications & Queuing Policy (AQP) | Regulatory | Business Process |  | To Be Confirmed | Western Power |  | Revised Applications and Queuing Policy, ETAC and Contributions Policy for constrained access (ETIU to consult industry and gazettal)
JM-033 | Generator Interim Access (GIA) service ceases and dispatched using SCED | WEMDE/Dispatch | Technical Go-Live | 2022-10-01 | To Be Confirmed | AEMO |  | GIA operation ceases and transition each facility to SCED control - assumed at Market Start 1 Oct 2022 |  | Likley to be merged with the SCED Go Live milestone as one component of that activity.
JM-034 | Generator Interim Access (GIA) - Terminate GIA related NCS | Connections | Business Process | Post 1-Oct 22 | To Be Confirmed | Western Power | 1 | Termination of GIA related Network Control Service after new market start in conjunction with any required contract amendments for constrained access
JM-035 | Market Participant Facility Readiness for SCED - SCADA upgrades/requirements provided to Western Power | WEMDE/Dispatch | Technical Implementation |  | To Be Confirmed | Western Power |  | Market Participants identify requirements for SCADA upgrades / changes to meet AEMO SCED requirements and provide to Western Power. (Subject to finalisation of requirements by AEMO in Q4 2020) | JM020
JM-036 | Market Participant Facility Readiness for SCED - SCADA upgrades/requirements implemented | WEMDE/Dispatch | Technical Implementation |  | To Be Confirmed | Western Power |  | Completion of SCADA upgrades / changes to meet AEMO SCED requirements (Note - required timeframe for market trials to be confirmed by AEMO/ WRIG) | JM020 & others
JM-037 | WEM Procedure - Limit Advice Development - Incorporate RCM limit advice | Constraints | WEM Procedure Milestone |  | To Be Confirmed | Western Power |  | Procedure updated to include RCM limit advice requirements
JM-038 | WEM Procedure - Limit Advice Development - Procedure Live | Constraints | WEM Procedure Milestone | 2022-10-01 | To Be Confirmed | Western Power | 1 | Finalise procedure post consultation
JM-039 | WEM Procedure - GPS Transition - Commence industry consultation | GPS | WEM Procedure Milestone | 2020-12-11 | Complete | Western Power | 1 | Draft procedure complete and commence 4 weeks industry consultation
JM-040 | WEM Procedure - GPS Transition - Procedure Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | Western Power | 1 | Finalise procedure post industry consultation
JM-041 | WEM Procedure - Loss Factors - Commence industry consultation |  | WEM Procedure Milestone |  | To Be Confirmed | Western Power |  | Draft procedure complete and commence 4 weeks industry consultation
JM-042 | WEM Procedure - Loss Factors - Finalise procedure post consultation |  | WEM Procedure Milestone |  | To Be Confirmed | Western Power |  | Draft procedure consultation closed
JM-043 | WEM Procedure - Loss Factors - Publish final procedure |  | WEM Procedure Milestone |  | To Be Confirmed | Western Power |  | Finalise procedure post industry consultation
JM-044 | WEM Procedure - Computer Model - Develop procedure and commence consultation | GPS | WEM Procedure Milestone | 2020-12-11 | To Be Confirmed | Western Power | 1 | Draft procedure complete and commence 4 weeks industry consultation
JM-045 | WEM Procedure - Computer Model - Procedure Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | Western Power | 1 | Finalise procedure post industry consultation
JM-046 | GPS Transition - Information capture template finalised | GPS | Business Process | 2020-12-01 | Complete | Western Power | 1 | GPS information capture template prepared by Western Power with input from AEMO and ETIU
JM-047 | GPS Transition - GPS information capture template provided to Market Participants | GPS | Business Process | 2020-12-01 | Complete | Western Power | 1 | Provide GPS information capture template to Market Participants
JM-048 | GPS Transition - GPS information capture template received from Market Participants | GPS | Business Process | 2021-03-31 | Confirmed | Western Power | 1 | Receive draft GPS information capture template back from Market Participants. Action undertaken by Market Participants. Consult with Western Power as required.
JM-049 | GPS Transition - GPS confirmed/finalised and input into Generator Register | GPS | Business Process | 2022-02-28 | To Be Confirmed | Western Power |  | GPS transition finalised with Market Participants and documented in Generator Register
JM-050 | GPS Transition - Generator Register - system to provide information to AEMO | GPS | Technical Implementation |  | To Be Confirmed | Western Power |  | Generator Register - system testing to transfer from Western Power to AEMO |  | JM-028
JM-051 | WP Limit Advice Development - initial set of thermal limits (non RCM) provided to AEMO | Constraints | Business Process | 2020-04-30 | Complete | Western Power | 1 | Thermal limit advice to AEMO initial set (non RCM limit advice)
JM-052 | WP Limit Advice Development - N-1 and N-1-1 Priority 1 limit advice to AEMO | Constraints | Business Process | 2022-01-01 | Confirmed | Western Power | 1 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 1
JM-053 | WP Limit Advice Development - N-1 and N-1-1 Priority 2 limit advice to AEMO | Constraints | Business Process | 2022-10-01 | Confirmed | Western Power | 1 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 2
JM-054 | WP Limit Advice Development - N-1 and N-1-1 Priority 3 limit advice to AEMO | Constraints | Business Process | 2023-06-01 | Confirmed | Western Power | 1 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 3
JM-055 | RCM 2021 Cycle - AEMO provides WP EOI and Facility Closure Info | Reserve Capacity Mechanism (RCM) | Business Process |  | To Be Confirmed | AEMO |  | AEMO provides WP EOI and Facility Closure Info
JM-056 | RCM 2021 Cycle - WP provides AEMO RCM limit advice | Reserve Capacity Mechanism (RCM) | Business Process |  | To Be Confirmed | Western Power |  | WP provides AEMO RCM Limit Advice
JM-057 | Weekly Settlement - Milestones | Settlements | Business Process | 2022-10-01 | To Be Confirmed | Western Power |  | Develop milestones for weekly settlement - Business Process | JM-022
JM-058 | Weekly Settlement - Milestones | Settlements | Technical Implementation | 2022-10-01 | To Be Confirmed | Western Power |  | Develop milestones for weekly settlement - Technical Implementation | JM-022
JM-059 | Outage Intention Plan - Outage Intention Plan Specification Available | System Planning (e.g. Outages, PASA) | Technical Information Release |  | To Be Confirmed | AEMO |  | Develop system to transfer Outage Intention Plan to AEMO - Test
JM-060 | Outage Intention Plan - Initial submission to AEMO | System Planning (e.g. Outages, PASA) | Business Process |  | To Be Confirmed | Western Power |  | Initial submission of Outage Intention Plan to AEMO
JM-061 | Outage Management - Scope of changes to WP and AEMO interface | System Planning (e.g. Outages, PASA) | Technical Information Release |  | To Be Confirmed | AEMO |  | Scope out changes to WP to AEMO software interface | JM-023
JM-062 | Outage Management - WP system changes complete | System Planning (e.g. Outages, PASA) | Technical Implementation |  | To Be Confirmed | Western Power |  | Development changes to eNAR | JM-023
JM-063 | Outage Management - WP system changes test | System Planning (e.g. Outages, PASA) | Technical Implementation |  | To Be Confirmed | Western Power |  | WP eNAR and AEMO systems test | JM-023
JM-064 | Outage Management - WP system changes production | System Planning (e.g. Outages, PASA) | Technical Implementation |  | To Be Confirmed | Western Power |  | WP eNAR and AEMO systems production | JM-023
JM-065 | WP Limit Advice Development - initial set of thermal limits (non RCM) provided to AEMO | Constraints | Business Process | 2020-04-30 | Complete | Western Power | 2 | Thermal limit advice to AEMO initial set (non RCM limit advice)
JM-066 | WP Connection Process - constrained access process applies to new access offers | Connections | Business Process | 2020-09-18 | Complete | Western Power | 1 | The Electricity Networks Access Code Amendments (No. 2) 2020 were gazetted 18 September - no further firm (unconstrained) services for generator connections
JM-067 | WEM Procedure - Limit Advice Development - Commence industry consultation | Constraints | WEM Procedure Milestone | 2020-10-03 | Complete | Western Power | 1 | Draft procedure complete and commence 4 weeks industry consultation
JM-068 | WP Limit Advice Development - N-0 system normal limit advice to AEMO | Constraints | Business Process | 2020-08-31 | Complete | Western Power | 2 | System Normal (N-0) non-thermal limit advice to AEMO
JM-069 | Comms infrastructure works complete | Site Works (Synergy) | Technical Implementation | 2021-05-01 | Confirmed | Synergy | 1
JM-070 | Control room complete | Site Works (Synergy) | Technical Implementation | 2021-09-01 | Confirmed | Synergy | 1
JM-071 | Pinjar Control Network works complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 1
JM-072 | Site SCADA works complete | Site Works (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 1
JM-073 | Control systems works complete | Site Works (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 1
JM-074 | Western Power SCADA works complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 1
JM-075 | Application development complete – core trading system | Technology (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 1
JM-076 | Development complete – reconciliation and settlement | Technology (Synergy) | Technical Implementation | 2022-08-01 | Confirmed | Synergy | 1
JM-077 | Migration planning and execution | Technology (Synergy) | Technical Implementation | 2022-05-01 | Confirmed | Synergy | 1
JM-078 | Completion of operator recruitment | Operational Capabilities (Synergy) | Technical Implementation | 2021-07-01 | Confirmed | Synergy | 1
JM-079 | Completion of trader recruitment Ph1 | Operational Capabilities (Synergy) | Technical Implementation | 2021-09-01 | Confirmed | Synergy | 1
JM-080 | Commencement of GT transition planning | Operational Capabilities (Synergy) | Technical Implementation | 2021-12-01 | Confirmed | Synergy | 1
JM-081 | Completion of trader recruitment Ph2 | Operational Capabilities (Synergy) | Technical Implementation | 2022-03-01 | Confirmed | Synergy | 1
JM-082 | Settlements Enhancements Interface Details Available | Settlements | Technical Information Release | 2021-02-01 | Confirmed | AEMO | 1
JM-083 | Settlement Enhancements Market Trial | Settlements | Technical Implementation | 2021-06-01 | Confirmed | AEMO | 1
JM-084 | Settlement Enhancements Go Live | Settlements | Technical Go-Live | 2021-07-01 | Confirmed | AEMO | 1
JM-085
JM-086
JM-087
JM-088
JM-089
JM-090
JM-091
JM-092
JM-093
JM-094
JM-095
JM-096
JM-097
JM-098
JM-099
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Level 0 - Significant 'Program Milestone' relevant to majority/all stakeholders and Market Particpants Level 1 - Significant 'Implementation Milestone' relevant to majority of stakeholders Level 2 - Important 'Implementation Milestone' relevant to one or small number of stakeholders or Market Particpants OR a preliminary milestone (e.g. early consultation in advance of formal consultation on a WEM Procedure)

## (Major) Change Log
JIP Release Date | Change Description
2020-12-17 | Initial set of Western Power and Synery Milestones added

## Issue Log
ID | Issue | Raised by | Date | Status/Updates

## Lookups
Project/Topic | Type | Date Status | Owner
Connections | Business Process | To Be Confirmed | AEMO
Constraints | Significant Market Milestone | Confirmed | ERA
Generator Interim Acces (GIA) | Staging Deployment | Complete | ETIU
GPS | Technical Go-Live |  | IPPs
Program/Implementation | Technical Implementation |  | Retailers
Registrations | Technical Information Release |  | Synergy
Regulatory | Training |  | Western Power
Reserve Capacity Mechanism (RCM) | WEM Procedure Milestone
Settlements
STEM
System Planning (e.g. Outages, PASA)
WEMDE/Dispatch
Site Works (Synergy)
Technology (Synergy)
Operational Capabilities (Synergy)
Contract Remeidation (Synergy)