## Slide 1
Version: 0.7 (DRAFT) Updated: 24/06/2021
JM001 - Minister Approves Tranche 1-3 Rule Changes
JM002 - Market Trial Commences
JM003 - SCED Go Live
SCED Workstream
Settlements Workstream
System Planning Workstream
Legacy Market Workstream
Registrations Workstream
JM029 - AEMO GPS Repository Live
JM020 - WEMDE Interface Details Available
JM021 – RTMS Interface Details Available
JM023 - Outage Management Interface Details Available
JM024 - Commissioning Test Interface Details Available
JM091 - RCM (Year 1) Interface Details Available
JM026 – STEM Phase 2 Interface Details Available (Dates TBC)
JM027 - Registration Interface Details Available (Dates TBC)
JM022 – Settlements (Reform) Interface Details Available
JM004 - Limit Advice Requirements Procedure Consultation Start
JM011 – Real Time Market – Dispatch Instructions & Conversions Live
JM006 - Constraint Information Resource Procedure Consultation Start
JM008 – Constraint Information Resource Procedure Live
JM012, JM013, JM014
GPS Testing Requirements, Monitoring Plan & Template, Process & Transition Considerations Procedures Consultation Start
JM015, JM016, JM017 - GPS Testing Requirements, Monitoring Plan & Template, Process & Transition Considerations Procedures Live
JM009 – Limit Advice Requirements Procedure Live
JM010 – Constraint Equation Development Procedure Live
JM005 - Constraint Equation Development Procedure Consultation Start
JM018 - Credible Contingency Events Procedure Consultation Start
JM019 - Credible Contingency Events Procedure Consultation Live
JM0030 - Minister Approves Tranche 4a
Rule Changes
Site Works
Technology
Contract Remediation
Operational Capabilities
JM069 – Comms infrastructure works complete
JM070 – Control room complete
JM071 & 72 – Pinjar Control Network works complete & WP SCADA works complete
JM073 and 74 – Site SCADA and Control Systems works complete
JM075 – Application dev complete – core trading system
JM077 – Migration planning & execution
JM076 – Dev complete – reconciliation & settlement
JM078 – Completion of operator recruitment
JM079 – Complete trader recruiting (Ph1)
JM081 – Complete trader recruitment (Ph2)
JM080 – Commencement of GT transition planning
JM066 – Constrained access process applies to new access offers
JM067 – Limit Advice Development - Consultation Start
Connections
Constraints
GPS
JM031 – connection application form updated for constrained access
JM034 – Generator Interim Access (GIA) - Terminate GIA related NCS
JM038, JM053 – Limit Advice Development - Procedure Live & N-1 and N-1-1 Priority 2 limit advice to AEMO
JM039, JM044, JM047 – GPS Transition & Computer Model - Commence industry consultation & GPS information capture template provided to Market Participants
JM040, JM045 – GPS Transition & Computer Model Procedures Live
JM048 – GPS information capture template received from Market Participants
JM052 – N-1 and N-1-1 Priority 1 limit advice to AEMO
JM028 - GPS Market Trial
JM082 – Settlements Enhancements Interface Details Available
JM084 – Settlement Enhancements Market Trial
JM083 – Settlement Enhancements Go Live
JM085 – Tranche 1 Procedures Complete (RCM)
JM086 – Phase 1 Market Trials Commence (RCM)
JM087 – Phase 1 Go Live (RCM)
JM0088 - Minister Approves Tranche 4B
Rule Changes
JM0089 - Minister Approves Tranche 5
Rule Changes
JM090 – Settlement Enhancements Release 2 Go Live
JM037 – Limit Advice Development - Incorporate RCM limit advice
JM092 – RCM (Year 3) Interface Details Available (Dates TBC)
JM093 – RTMS Market Test Commence

## Slide 2: Joint Industry Plan (JIP) Milestones
As further planning progresses to detail the Implementation Program Plan, key milestones with industry-facing impacts will be added to the Joint Industry Plan.
The following categories of milestones are included in the JIP:
Category | Symbol | Description
Significant Market Milestone |  | A significant event in the WEM Reform Program, not necessarily related to system implementation.
Procedure Milestone |  | Events relating to consultation or development of Market Procedures.
Technical Implementation Release |  | Staging or Production release for a system that may be used by Market Participant users or integrate with Market Participant systems.
Staging Deployment |  | Staging deployment for Market Participants to test interfaces, business rules or usability of systems prior to formal go-live.
Technical Information Release |  | Information released that may be used by Market Participants to assist implementation activities.
Training |  | Training for Market Participants with regard to systems or market design.
Business Process |  | Activities or deliverables related to internal or market processes
Technical Implementation Milestone (non-release) |  | Activities or deliverables related to system implementation (e.g. design or testing artefacts)
Further milestone categories may be added as necessary to improve the usability of the JIP as planning progresses.