## Sheet1
Insert name of State Government department, agency or instrumentality
Insert date of report
Proposed Ground Disturbing Activities to be undertaken in the Yamatji Nation Agreement Area for the following 6 months. List should include all Low and Major ground disturbing activities. Minor Impact Activities that involve no or negligible ground disturbance are not included unless with the boundaries of a known Aboriginal heritage site. (Variance to reporting requirements of YGSHA Clause 7.1(c) has been made with the agreement of YSRC)
Date of Activity | Nature of Activity (please include additional comment if within a known Aboriginal Site boundary or an approval may be sought under AHA 1972 | Location of Activity - description and central GPS coordinate/s | YSRC comment of any concerns in compliance with YGSHA Clause 7.1(d)
2021-05-24 | Undertake remedial works, site clean up and fence repairs at ID 5559 (Willigulli) (PA 37) | Site is located in the Shire of Northampton. Works are across the site with coordinates being: 252107mE 6856265mN Zone 50 | Example only
2021-06-01 | Regular check of ALT Reserve 2596 Mullewa and remove any rubbish contained at the Reserve | ALT Reserve Coordinates being 354259.2mE 6842253mN Zone 50 | Example only
2021-06-01 | Site Audit ID 5191 (Racecourse Paddiock 1) (PA 26) to assess possible site damage following cyclone. Check no ancestral remains have been exposed. | Site is located in the Shire of Northampton with coordinates being: 263669mE 6859383mN Zone 50 | Example only
2021-06-10 | Site visit to ALT property in land Mulewa (Wandanooks/Karavloo). Check condition of roads, fences and undertake minor remedial works required. | ALT Reserve Coordinates being 363712.2mE 659417.4mN Zone 50 | Example only
2021-06-23 | Place signage advising of Aboriginal sites in arae aroun Little Bay Road. Sites in the area include ID 17164 (Horrocks Beach), ID 18433 (Horrocks Midden) which is a lodged place. | ID 17164 (Horrocks Beach) coordinates being: 246772mE 6860129mN Zone 50 ID 18433 (Horrocks Midden) coordinates being: 246543mE 6860371mN Zone 50 | Example only