## WEM Procedure List
Date Published: | 2021-09-30
AEMO has prepared this preliminary document to provide information about AEMO's WEM Procedures and proposed WEM Procedure timelines, based on the information available to AEMO as at the date of the document. This document or the information in it may not be accurate or complete and may be subsequently updated or amended. AEMO has made every effort to ensure the quality of the information in this document but cannot guarantee its accuracy or completeness. For a forward plan of when WRIG WEM Procedure topic discussions will take place, please refer to the WEM Procedure Schedule slide within the latest WRIG meeting slides.
Procedure Name | Procedure HoP | Topic | New/ Re-write /Update | Size of change (L, M, S) | Date Topic taken to WRIG | Est. Completion of Topic Discussions | Est. Consultation Date | Est. WEM Procedure Publication | Date Published on AEMO's Website (Provisional or Commenced)
WEM Procedure: Limit Advice Requirements | 2.27A.10 | Thermal Limit Advice Requirements | New | M | 2020-10-01 | Complete | 12/10/2020 - Closed | 2022-10-01
Non-Thermal Limit Advice Requirements
Non-Thermal Limit Advice Review
RCM Limit Advice
WEM Procedure: Constraint Formulation | 2.27A.10; | Standard Methodology for Constraint Equations | New | L | 2020-10-01 | Complete | 12/10/2020 - Closed | 2022-10-01
Development
Operating Margins
Network Constraint Formulation
The Constraint Library
Special Constraints
Constraint Naming
Quality Control
WEM Procedure: Congestion Information Resource | 2.27B.8 | Congestion information Resource | New | S | 2020-10-29 | Complete | 19/11/2020 - Closed | 2022-10-01
Information to be Provided by Network Generators
WEM Procedure: Generator Monitoring Plans | 1.41.6; 3A.6.2 3A.9.1. | Template Generator Monitoring Plan | New | L | 2020-11-26 | Complete | 11/12/2020 - Closed | Complete | 1/02/2021 - Commenced
Compliance Testing and Monitoring Requirements
Submissions, Assessment and Approval Process
Existing Transmission Connected Generating Systems
Non-Compliance with Generator Monitoring Plan
WEM Procedure: Credible Contingency Events | 3.8A.4 | Contingency Event Framework | New | S | First Release: 17/12/2020 - Complete Revised Version: 27/05/2021 - Complete | Complete | First Release: 18/01/2021 - Closed Revised Version: 25/6/2021 - Closed | Complete | First Release: 1/02/2021 Second Release: 29/07/2021 - Commenced
WEM Procedure: Frequency Co-Optimised Essential System Services Accreditation | 2.34A.13; | Transitional Accreditation for the Provision of ESS | New | L | 1/10/2020 02/09/2021 | Complete | 09/09/2021 - Closed | 2021-10-01
Accreditation Methodology for ESS Providers
RoCoF Ride Through Capability
Settlement Exemption Process (contingency, Rocof)
WEM Procedure: SESSM Procurement | 3.11.4; 3.15A.46 | SESSM Procurement Methodology | New | M |  | 2022-07-28 | 2022-08-05 | 2022-10-31
SESSM Procurement Trigger
WEM Procedure: ESS Quantity Determination Methodology | 3.11.7 | ESS Quantity Determination Methodology | New | M |  | 2022-06-30 | 2022-07-08 | 2022-10-01
WEM Procedure: Communications and Control Systems | 2.36A.5; 2.35.4; | Communications and Control - IT Systems | Update | M | 2021-04-29 | Complete | 15/09/2021 - Closed | 1/10/2021 01/10/2022 - second version (Prov Pub)
|  | Communications and Control - Backup processes | New
Communications and Control - Recording requirements
Communications Standard
|  | SCADA point requirements (generators, networks) |  |  | 2021-03-25
WEM Procedure: IMS Interface for Network Operators | 2.36.7 | Transfer of Information | Update | M |  | 2023-03-30 | 2023-04-20 | 2023-07-14
|  | Technical and Communication Criteria | New
|  | Rule Participant registration exemption | New
WEM Procedure: Monitoring and Reporting Compliance | 2.13.19; 7.10.5; 7.10.21. | Facility Tolerance for Dispatch Compliance | Update | M |  | 2022-06-30 | 2022-07-08 | 2022-10-01
Monitoring and Compliance
WEM Procedure: Notices and Communications | 1.6.2; 3.5.1A; 7.11.8 | Guidelines for Dispatch based Advisories | New | M |  | 2022-06-30 | 2022-07-08 | 2022-10-01
Guidelines for Market based Market Advisories
Guidelines for any other communication
Declaring Emergency Operating States
WEM Procedure: Real-Time Market Timetable | 7.1.2(a) | Real-Time Market Timetable | New | S |  | 2022-06-30 | 2022-07-08 | 2022-10-01
WEM Procedure: Price determination | 7.11C.1; 7.11C.11 | Energy Price Determination | New | M |  | 2022-06-30 | 2022-07-08 | 2022-10-01
ESS Price Determincation
WEM Procedure: Dispatch Algorithm | 7.2.5 | Formulation | New | L |  | 2022-06-30 | 2022-07-08 | 2022-10-01
ESS Factors
Inflexibility Profiles
Infeasibility outcomes
Unavailability outcomes
WEM Procedure: Participant Submissions | 7.4.20; 7.4.22; 7.4.38; 7.4.53; 7.4.62 | Submission Type | New | L | 2021-09-30 | Complete | 2021-10-30 | 2022-01-31
Submission Process
Submission Format
Validation
Standing Conversion
Acceptance/Acknowledgement
WEM Procedure: Facility Dispatch Process | 7.2.8; 7.3.4; 7.4.53; 7.5.4; 7.6.3; 7.6.18; 7.6.27; 7.6.33; 7.7.14; 7.8.9; 7.13.5; 7.13.3; 7.13.8. | Dispatch Communication Process (issue, acknowledge) | Update | L |  | 2022-06-30 | 2022-07-08 | 2022-10-01
Dispatch Conversion
Dispatch Override
DSP Dispatch
Constraint Relaxation
Invoking Constraints
Forecast Operational Demand
WEM Procedure: Dispatch Settlement and Monitoring Data | 7.13.3; 7.13.5; 7.13.8 | Settlement and Monitoring Data | New | M |  | 2022-06-30 | 2022-07-08 | 2022-10-01
Decrease in Consumption for DSP Calculation
Estimation of max quantity of sent out energy for intermittent components of Semi-Scheduled Facilities
WEM Procedure: Outages | 3.18.4; 3.19.11; 3.21.10; 3.21.17. | Outage Intention Plan (OIP) | New | L |  | 2022-04-28 | 2022-05-06 | 2022-08-01
Outage Submission (including by component, type)
|  | Outage Coordination/Prioritisation | Update
|  | Outage Evaluation/Approval | New
Outage Revisions
Outage Quantity Determination
Intermittent Load - Generation outage process
Outage Compensation
WEM Procedure: Reliability Standard Implementation Procedure | 3.3.2 | Processes for managing Reliability | New | M |  | 2022-07-28 | 2022-08-08 | 2022-11-01
WEM Procedure: ST PASA | 3.16.10 | PASA Reporting | Update | M | 2021-06-24 | 2023-01-26 | 2023-02-15 | 2023-05-15
WEM Procedure: MT PASA | 3.16.10 | PASA Reporting | Update | M | 2021-06-24 | 2022-01-27 | 2022-02-01 | 2022-04-30
WEM Procedure: Low Reserve Conditions | 3.17.11 | PASA Low Reserve Planning | New | M |  | 2022-07-28 | 2022-08-08 | 2022-11-01
WEM Procedure: Power System Security | 3.2.7; 3.2.2 | Determination of the Technical Envelope | New | L |  | 2022-07-28 | 2022-08-08 | 2022-11-01
Delivery and treatment of Equipment Limits
Power System Stability (including System Strength)
Inertia Requirements
WEM Procedure: Commissioning Tests | 3.21A.27 | Submission Process | Update | M |  | 2022-05-26 | 2022-06-07 | 2022-08-30
Timeline
Submission format
Validation
Approval
Rescheduling
WEM Procedure: Certification of Reserve Capacity | 4.9.10; 4.10A.11; 4.28C.15; 4.30.12 | Degradation of ESR | Update | L | 05/08/2021 02/09/2021 | Complete | 2021-09-22 | 2021-11-01
Certification of Hybrid Facilities
Unassessable technology combinations
Certification of Facility/Technology classes
Independent Expert Reports
Outages Rule Change RC_2014_03
RLM Rule Change RC_2019_03
Early Certification
Certification of upgrades
WEM Procedure: RCM Constraints | 2.27A.10 | NAQ required Constraints | New | M |  | 2022-01-27 | 2022-01-27 | 2022-03-01
WEM Procedure: RCM Limit Advice (Transitional) | 2.27A.10 | RCM Limit Advice | New | M |  | 2022-01-27 | 2022-01-27 | 2022-03-01
WEM Procedure: Assignment of NAQs | 4.15.17 | NAQ Model | New | L |  | 2022-05-26 | 2022-06-09 | 2022-09-01
Facility Dispatch Scenarios Determination
Determining NAQ
WEM Procedure: ESR obligation intervals | 4.11.3A(c) | Defining ESR obligation intervals | New | M | 2021-03-25 | Complete | 03/05/2021 - Closed | Complete | 1/07/2021 - Commenced
Moving of ESR obligation intervals
WEM Procedure: Declaration of Bilateral Trades and the Capacity Credit assignment | 4.14.11; 4.17.9 | Clarification of nominating for price | Update | M |  | 2021-11-25 | 2021-12-03 | 2022-03-01
Existing procedure content
WEM Procedure: Supplementary Reserve Capacity | 4.24.18 | Acquiring Eligible Services | Update | S |  | 2023-01-26 | 2023-01-31 | 2023-05-01
Entering into Supplementary Capacity Contracts
Determining maximum contract value per hour of availability
Supplementary Capacity payments for parties who aren't a Market Participant
Determining a provider of an Eligible Service has access to the network
WEM Procedure: Reserve Capacity Security Procedure | 4.13.8; 4.13A.23 | Determining Reserve Capacity Security | Update | S |  | 2022-01-27 | 2022-02-01 | 2022-03-01
Acceptable Credit Criteria assessments
Reserve Capacity Secuirty arrangements
WEM Procedure: Reserve Capacity Performance Monitoring | 4.27.12 | Perfomance Monitoring | Update | S |  | 2023-01-26 | 2023-01-31 | 2023-05-01
|  | Performance Reports | Update
WEM Procedure: Consumption Deviation Applications | 4.26.2CE; 4.28.9E. | Relevent Demand | Update | S |  | 2023-01-26 | 2023-01-31 | 2023-05-01
NTDL
WEM Procedure: Undertaking the Long Term PASA and conducting the review of the Planning Criterion | 4.5.14 | Undertaking the Long Term PASA | Update | M |  | 2022-01-27 | 2022-01-06 | 2022-04-01
|  | Review of the Planning Criterion | Update | M
WEM Procedure: Reserve Capacity Testing | 4.25.14 | Testing Requirements (inc re-testing) | Update | L |  | 2023-01-26 | 2023-01-31 | 2023-05-01
DSP Testing
Hybrid Facility Testing
Non-Hybrid Facility Testing
ESR Component Testing
WEM Procedure: Facility Sub-Metering | 2.29.15 | Facility Sub-Metering standards | New | L | 2021-03-25 | Complete | 03/06/2021 - Closed | Complete | 1/07/2021 - Commenced
Facility Sub-Metering usage in RCM
WEM Procedure: Temperature adjustment for RCOQ | 4.12.8 | Adjustments to the Reserve Capacity Obligation Quantity | New | M |  | 2023-01-26 | 2023-01-31 | 2023-05-01
WEM Procedure: Rule Participant Registration and Deregistration Process | TBC | TBC | Update | L |  | 2022-09-29 | 2022-10-06 | 2023-01-01
WEM Procedure: Facility registration, de-registration and transfer Procedure | TBC | TBC | Update | L |  | 2022-09-29 | 2022-10-06 | 2023-01-01
WEM Procedure: Network Modelling Data | 2.28.20 | Network Modelling Data Provision | Update | S |  | 2022-06-30 | 2022-07-08 | 2022-10-01
WEM Procedure: Meter Data Submission Procedure | 8.6.2 | Meter Data Submission format | Update | M |  | 2023-01-26 | 2023-01-31 | 2023-05-01
WEM Procedure: Settlements | 9.2.1; 9.2.2; 4.28A.3 | Settlement Process | Update | L |  | 2023-01-26 | 2023-01-31 | 2023-05-01
Uplift Payment methodology
Estimation of Facility capacity for ESS
Intermittent Load Refunds - Generation outage refunds
Financial Penalty Distribution Process
WEM Procedure: Capacity Credit Allocations | 4.30.12 | Daily Allocation process | Update | M |  | 2023-01-26 | 2023-01-31 | 2023-05-01
WEM Procedure: Individual Reserve Capacity Requirements (IRCR) | 4.28.12 | IRCR Methodology | Update | S |  | 2023-01-26 | 2023-01-31 | 2023-05-01
Consideration of ESR contribution
WEM Procedure: Prudential Requirements | 2.43.1 | Credit Limits | Update | L |  | 2023-01-26 | 2023-01-31 | 2023-05-01
|  | Credit Support | Update
|  | Acceptable Credit Criteria | Update
WEM Procedure: Data and IT Interface Requirements | 2.36.5 | Cyber | New | S | 2020-12-17 | Complete | 16/07/2021 - Closed | Complete | 29/07/2021 - Commenced
Portal and IDAM
WEM Procedure: Information Confidentiality | 10.2.7 | Setting and publishing confidentiality statuses | Update | S |  | TBD | TBD | TBD
WEM Procedure: Indicative Facility Class and RCM Facility Class Assessment | 4.8A.7 | Indicative Facility Class Registration | New | L | 2021-05-27 | Complete | 09/07/2021 - Closed | Complete | 29/07/2021 - Commenced
WEM Procedure: Transitional Registration | 1.47.8 | Assignment of a Facility Class | New | S |  | 2022-09-29 | 2022-10-06 | 2023-01-01
Mapping of existing Facilitites to new Facility Classes
WEM Procedure: Monitoring and Reporting Protocol | 2.15.4 | Monitoring and reporting compliance | Update | M |  | 2023-06-29 | 2023-07-10 | 2023-10-01