## Milestone Log
Foundation Regulatory Frameworks - Joint Industry Plan - Milestone Log
ID | Title | Project/Topic | Type | Milestone Date | Date Status | Owner | Level | Description | Dependencies | Status/Comments | Included in interim graphic (1/10/2021)
JM-001 | Minister Approves Tranche 1-3 Rule Changes | Regulatory | Significant Market Milestone | Nov-Dec-20 | Confirmed | EPWA | 0 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Tranche 1 (Nov-20): Generator Performance Standards Framework (incl. Ch. 3a, Appendix 12, and transitional rules) ‘Administrative Package’ Frequency Operating Standards and Contingency Events Frameworks Tranche 2 (Dec-20): Foundation Market Parameters (incl. STEM) Frequency Co-optimised ESS Operating States and Tech Envelope Scheduling and Dispatch Outage Management and Commissioning Tests Operational Planning (PASA) WEM Monitoring and Compliance Market Settlement Tranche 3 (Dec-20): Reserve Capacity Mechanism (RCM) Prioritisation and Network Access Quantities Framework Participation of storage and hybrid facilities in the RCM RCM changes consequential to SCED Application and Queuing Policy for Constrained Network Access |  | On Track - all three Tranches published for consultation in October 20 | TRUE
JM-002 | Market Trial Commences | Program/Implementation | Significant Market Milestone | 2023-01-01 | To Be Confirmed | AEMO | 0 | Commencement of 'formal' Market Trial period where Market Participants and other parties will conduct defined end-to-end scenario based trials e.g. as opposed to purely system/user integration testing). |  | Scope of Market Trial and Dates to be developed via WRIG | TRUE
JM-003 | SCED Go Live | Program/Implementation | Significant Market Milestone | 2023-10-01 | Confirmed | AEMO | 0 | Date on which first interval of Security Constrained Economic Dispatch (SCED) will take place in line with commencement of relevant WEM Rule Modifications and Go Live date referenced in WEM Rule 1.20. |  | Specific scope of Go Live milestone to be refined and defined via WRIG | TRUE
JM-004 | Limit Advice Requirements Procedure Consultation Start | Constraint Management | WEM Procedure Milestone | 2020-10-13 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-005 | Constraint Formulation Procedure Consultation Start | Constraint Management | WEM Procedure Milestone | 2020-10-13 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation |  |  | TRUE
JM-006 | Constraint Information Resource Procedure Consultation Start | Constraint Management | WEM Procedure Milestone | 2020-11-05 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation |  |  | TRUE
JM-007 | Facility Dispatch Process Procedure Consultation Start | WEMDI UI and E-terra integration | WEM Procedure Milestone | 2020-10-29 | Complete | AEMO | 2 | AEMO will commence first stage 'informal' consultation process on WEM Procedure topic |  |  | TRUE
JM-008 | Constraint Information Resource Procedure Live | Constraint Management | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect |  |  | TRUE
JM-009 | Limit Advice Requirements Procedure Live | Constraint Management | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-010 | Constraint Equation Development Procedure Live | Constraint Management | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-011 | Facility Dispatch Process Procedure Live | WEMDI UI and E-terra integration | WEM Procedure Milestone | 2022-10-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-012 | GPS Testing Requirements Procedures Consultation Start | GPS | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 2 | AEMO will commence first stage 'informal' consultation process on WEM Procedure topic
JM-013 | GPS Monitoring Plan & Template Procedures Consultation Start | GPS | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-014 | GPS Process & Transition Considerations Procedures Consultation Start | GPS | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-015 | GPS Testing Requirements Procedures Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-016 | GPS Monitoring Plan & Template Procedures Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-017 | GPS Process & Transition Considerations Procedures Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-018 | Credible Contingency Events Procedure Consultation Start | System Operation Planning | WEM Procedure Milestone | 2020-12-01 | Complete | AEMO | 1 | AEMO will publish draft WEM Procedure and commence four weeks formal consultation
JM-019 | Credible Contingency Events Procedure Consultation Live | System Operation Planning | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | WEM Procedure takes legal effect
JM-020 | WEMDE technical specifications available | WEM Dispatch Engine | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide details regarding how participants are to be supplied the WEMDE solution files.
JM-021 | Technical documentation published (Release 1) | Real Time Market Submissions (RTMS) | Technical Information Release | 2021-10-20 | Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) |  | AEMO plans to release a draft version 0.4 to the market in September 2021 to support training prior to MARKET TEST.
JM-022 | Technical documentation published | Settlements Reform | Technical Information Release | 2023-01-03 | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-023 | Technical documentation published | Outage Management | Technical Information Release | 2022-06-01 | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) |  |  | TRUE
JM-024 | Technical documentation published | Commissioning Test | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) |  |  | TRUE
JM-025 | Technical documentation published | MT PASA | Technical Information Release | 2022-08-08 | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) |  |  | TRUE
JM-026 | Technical documentation published | STEM | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) |  |  | TRUE
JM-027 | Technical documentation published | Registrations | Technical Information Release | TBC | To Be Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) |  |  | TRUE
JM-028 | Participant testing | GPS | Technical Information Release | 2021-06-28 | Confirmed | AEMO | 1 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) |  | Market Trial is still ongoing as at 27/08/2021; Check again at 30/09/21 | TRUE
JM-029 | AEMO GPS Repository Live | GPS | Technical Go-Live | 2021-07-28 | Complete | AEMO | 1 | GPS Repository completes formal testing and moves to Production environment.
JM-030 | Minister Approves Tranche 4a Rule Changes | Regulatory | Significant Market Milestone | 2021-04-30 | Confirmed | EPWA | 0 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Tranche 4: Transitional Arrangements (e.g. ESS accreditation) Tranche 5: Non-Cooptimised ESS Framework Market Information Framework Market Power Mitigation Reliability Standards Framework Participation and Registration framework |  |  | TRUE
JM-031 | Connection Application Form Updated for Constrained Access | Connections | Business Process | 2021-07-31 | Complete | Western Power | 1 | Updated customer connection application form (including information for generator performance standards) Dependant on the approval of Access Code Tranche 2 amendments. | JM-032 |  | TRUE
JM-032 | Revised Applications and Queuing Policy (AQP) and Contribution Policy Published | Regulatory | Business Process | 2021-07-31 | To Be Confirmed | Western Power |  | Revised Applications and Queuing Policy, ETAC and Contributions Policy for constrained access (ETIU to consult industry and gazettal) Dependant on the approval of Access Code Tranche 2 amendments. |  |  | TRUE
JM-033 | Generator Interim Access (GIA) service ceases and dispatched using SCED | Program/Implementation | Technical Go-Live | 2023-10-01 | To Be Confirmed | AEMO |  | GIA operation ceases and transition each facility to SCED control - assumed at Market Start 1 Oct 2022 |  | Likley to be merged with the SCED Go Live milestone as one component of that activity.
JM-034 | Terminate GIA Related NCS | Connections | Business Process | Post 1-Oct 22 | Confirmed | Western Power | 1 | Termination of GIA related Network Control Service after new market start in conjunction with any required contract amendments for constrained access
JM-035 | Market Participant SCADA Requirements Provided to Western Power | Site Works (Non-Synergy) | Technical Implementation |  | To Be Confirmed | Western Power |  | Market Participants identify requirements for SCADA upgrades / changes to meet AEMO SCED requirements and provide to Western Power. |  |  | TRUE
JM-036 | Western Power SCADA Works Complete (Non-Synergy) | Site Works (Non-Synergy) | Technical Implementation |  | To Be Confirmed | Western Power |  | Completion of SCADA upgrades / changes to meet AEMO SCED requirements (Note - required timeframe for market trials to be confirmed by AEMO/ WRIG) | JM-035 |  | TRUE
JM-037 | WEM Procedure - Limit Advice Development - Consultation Start | Constraint Management | WEM Procedure Milestone | Q1-2022 | To Be Confirmed | Western Power | 1 | Procedure updated to include RCM limit advice requirements |  |  | TRUE
JM-038 | WEM Procedure - Limit Advice Development - Procedure Live | Constraint Management | WEM Procedure Milestone | Q1 2022 | To Be Confirmed | Western Power | 1 | Finalise procedure post consultation | JM-037 |  | TRUE
JM-039 | WEM Procedure - Generator Performance Standards for Existing Transmission Connected Generating Systems - Consultation Start | GPS | WEM Procedure Milestone | 2020-12-11 | Complete | Western Power | 1 | Draft procedure complete and commence 4 weeks industry consultation |  |  | TRUE
JM-040 | WEM Procedure - Generator Performance Standards for Existing Transmission Connected Generating Systems - Procedure Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | Western Power | 1 | Finalise procedure post industry consultation | JM-039 |  | TRUE
JM-041 | WEM Procedure - Loss Factors - Consultation Start | WEM Dispatch Engine | WEM Procedure Milestone | Q2-2022 | To Be Confirmed | Western Power |  | Draft procedure complete and commence 4 weeks industry consultation
JM-042 | WEM Procedure - Loss Factors - Procedure Live | WEM Dispatch Engine | WEM Procedure Milestone | Q2-2022 | To Be Confirmed | Western Power |  | Draft procedure consultation closed | JM-041
JM-043 | Loss Factors Provided for New Market | WEM Dispatch Engine | Business Process | 2022-06-01 | Confirmed | Western Power |  | Finalise procedure post industry consultation | JM-042
JM-044 | WEM Procedure - Generation System Model Submission and Maintenance - Consultation Start | GPS | WEM Procedure Milestone | 2020-12-11 | Complete | Western Power | 1 | Draft procedure complete and commence 4 weeks industry consultation |  |  | TRUE
JM-045 | WEM Procedure - Generation System Model Submission and Maintenance - Procedure Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | Western Power | 1 | Finalise procedure post industry consultation | JM-045 |  | TRUE
JM-047 | GPS Submission Template provided to Market Participants | GPS | Business Process | 2020-12-01 | Complete | Western Power | 1 | Provide GPS information capture template to Market Participants |  |  | TRUE
JM-048 | Draft GPS Submissions Received from Market Participants | GPS | Business Process | 2021-03-31 | Complete | Western Power | 1 | Receive draft GPS information capture template back from Market Participants. Action undertaken by Market Participants. Consult with Western Power as required. | JM-047 |  | TRUE
JM-049 | GPS Updates provided to AEMO GPS Repository | GPS | Business Process | 2022-02-28 | Confirmed | Western Power |  | GPS transition finalised with Market Participants and documented in Generator Register | JM-029 |  | TRUE
JM-051 | Limit Advice Development - Initial Set of Thermal Limits provided to AEMO | Constraint Management | Business Process | 2020-04-30 | Complete | Western Power | 1 | Thermal limit advice to AEMO initial set (non RCM limit advice) |  |  | TRUE
JM-052 | Limit Advice Development - N-1 and N-1-1 Priority 1 Limit Advice to AEMO | Constraint Management | Business Process | 2022-01-01 | Confirmed | Western Power | 1 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 1 | JM-068 |  | TRUE
JM-053 | Limit Advice Development - N-1 and N-1-1 Priority 2 Limit Advice to AEMO | Constraint Management | Business Process | 2022-10-01 | Confirmed | Western Power | 1 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 2 | JM-052 |  | TRUE
JM-054 | Limit Advice Development - N-1 and N-1-1 Priority 3 Limit Advice to AEMO | Constraint Management | Business Process | 2023-06-01 | Confirmed | Western Power | 1 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 3 | JM-053 |  | TRUE
JM-055 | RCM 2021 Cycle - AEMO provides EOI and Facility Closure Info | Reserve Capacity Mechanism (RCM) | Business Process | 2021-09-30 | Confirmed | AEMO | 1 | AEMO provides WP EOI and Facility Closure Info |  |  | TRUE
JM-056 | RCM 2021 Cycle – RCM Limit Advice provided to AEMO | Reserve Capacity Mechanism (RCM) | Business Process | 2022-03-01 | To Be Confirmed | Western Power |  | WP provides AEMO RCM Limit Advice based on AEMO's provision of RCM Requirements |  |  | TRUE
JM-057 | Weekly Settlement - WP and AEMO Interface - Ready for Test | Settlements Reform | Technical Implementation |  | To Be Confirmed | Western Power |  | WP and AEMO B2B Settlement interface ready for test | JM-022 |  | TRUE
JM-058 | Weekly Settlement - WP and AEMO Interface - Ready for Trials | Settlements Reform | Technical Implementation | 2022-04-01 | To Be Confirmed | Western Power |  | WP and AEMO B2B Settlement interface ready for trials | JM-057 |  | TRUE
JM-059 | Outage Intention Plan - Outage Intention Plan Specification Available | Outage Management | Technical Information Release | TBC | To Be Confirmed | AEMO |  | Develop system to transfer Outage Intention Plan to AEMO - Test | JM-058 |  | TRUE
JM-062 | Outage Management WP and AEMO Interface - Ready for Test | Outage Management | Technical Implementation |  | To Be Confirmed | Western Power |  | WP and AEMO B2B outage management interface ready for test | JM-023
JM-063 | Outage Management WP and AEMO Interface - Ready for Trials | Outage Management | Technical Implementation | 2022-04-01 | To Be Confirmed | Western Power |  | WP and AEMO B2B outage management interface ready for trials | JM-062
JM-064 | Outage Management WP and AEMO Interface - Ready for Market Start | Outage Management | Technical Implementation | 2022-10-01 | To Be Confirmed | Western Power |  | WP and AEMO B2B outage management interface ready for market start | JM-063
JM-066 | Constrained Access Process Applies to New Access Offers | Connections | Business Process | 2020-09-18 | Complete | Western Power | 1 | The Electricity Networks Access Code Amendments (No. 2) 2020 were gazetted 18 September - no further firm (unconstrained) services for generator connections |  |  | TRUE
JM-068 | Limit Advice Development - N-0 System Normal Limit Advice to AEMO | Constraint Management | Business Process | 2020-08-31 | Complete | Western Power | 2 | System Normal (N-0) non-thermal limit advice to AEMO | JM-051
JM-070 | Control room complete | Site Works (Synergy) | Technical Implementation | 2021-09-01 | Confirmed | Synergy | 1 |  |  |  | TRUE
JM-071 | Pinjar Control Network works complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 1
JM-072 | Site SCADA works complete | Site Works (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 1 |  |  |  | TRUE
JM-073 | Control systems works complete | Site Works (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 1
JM-074 | Western Power SCADA works complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 1
JM-075 | Application development complete – core trading system | Technology (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 1
JM-076 | Development complete – reconciliation and settlement | Technology (Synergy) | Technical Implementation | 2022-08-01 | Confirmed | Synergy | 1 |  |  |  | TRUE
JM-077 | Migration planning and execution | Technology (Synergy) | Technical Implementation | 2022-05-01 | Confirmed | Synergy | 1 |  |  |  | TRUE
JM-078 | Completion of operator recruitment Ph 1 | Operational Capabilities (Synergy) | Training | 2021-07-01 | Complete | Synergy | 1 |  |  |  | TRUE
JM-079 | Completion of trader recruitment Ph1 | Operational Capabilities (Synergy) | Training | 2021-09-01 | Complete | Synergy | 1 |  |  |  | TRUE
JM-080 | Commencement of GT transition planning | Operational Capabilities (Synergy) | Business Process | 2021-12-01 | Confirmed | Synergy | 1 |  |  |  | TRUE
JM-081 | Completion of trader recruitment Ph2 | Operational Capabilities (Synergy) | Training | 2022-03-01 | Confirmed | Synergy | 1 |  |  |  | TRUE
JM-082 | Technical documentation published (Release 1) | Settlements Enhancements | Technical Information Release | 2021-02-01 | Confirmed | AEMO | 1 |  |  |  | TRUE
JM-083 | Participant testing (Release 1) | Settlements Enhancements | Technical Implementation | 2021-07-01 | Confirmed | AEMO | 1 |  |  |  | TRUE
JM-084 | Release 1 (go-live) | Settlements Enhancements | Technical Go-Live | 2021-08-02 | Confirmed | AEMO | 1 |  |  |  | TRUE
JM-085 | Tranche 1 Procedures Complete (RCM) | Reserve Capacity Mechanism (RCM) | WEM Procedure Milestone | 2021-08-01 | Complete | AEMO | 1 |  |  | Date slip from July to August 2021, but now complete. | TRUE
JM-086 | Participant testing (Phase 1, Release 1) | Reserve Capacity Mechanism (RCM) | Technical Implementation | 2021-10-15 | Confirmed | AEMO | 1 |  |  |  | TRUE
JM-087 | Release go-live (Phase 1, Release 1) | Reserve Capacity Mechanism (RCM) | Technical Go-Live | 2021-12-01 | Confirmed | AEMO | 1 |  |  |  | TRUE
JM-088 | Minister Approves Tranche 4b Rule Changes | Regulatory | Significant Market Milestone | Jul/Aug-21 | Confirmed | EPWA | 0 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Non-Cooptimised ESS Framework Market Information Framework Market Power Mitigation Reliability Standards Framework Participation and Registration framework |  |  | TRUE
JM-089 | Minister Approves Tranche 5 Rule Changes | Regulatory | Significant Market Milestone | 2021-12-01 | Confirmed | EPWA | 0 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Non-Cooptimised ESS Framework Market Information Framework Market Power Mitigation Reliability Standards Framework Participation and Registration framework |  |  | TRUE
JM-090 | Release 2 (go-live) | Settlements Enhancements | Technical Go-Live | 2021-09-29 | Confirmed | AEMO | 1 |  |  |  | TRUE
JM-091 | Technical documentation published (Phase 1, Release 1) | Reserve Capacity Mechanism (RCM) | Technical Information Release | 2021-10-28 | To Be Confirmed | AEMO | 1 | RCM Phase 1 of 2021 RC Cycle, release 3 (R1.2 API Spec version) will complete this first phase of RCM work |  |  | TRUE
JM-092 | Technical documentation published (Phase 3) | Reserve Capacity Mechanism (RCM) | Technical Information Release | TBC | To Be Confirmed | AEMO | 1
JM-093 | RTMS Market Test Commence | Real Time Market Submissions (RTMS) | Staging Deployment | TBC | To Be Confirmed | AEMO | 1
JM-094 | Pinjar comms link complete | Site Works (Synergy) | Technical Implementation | 2021-06-30 | Complete | Synergy | 2 |  |  | Added by Synergy, updated in JIP for 29/07/21 meeting; Replace JM-069 | TRUE
JM-095 | Kemerton comms link complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 2 |  |  | Added by Synergy, updated in JIP for 29/07/21 meeting; Replace JM-069 | TRUE
JM-096 | Completion of operator recruitment Ph 2 | Operational Capabilities (Synergy) | Training | 2021-10-01 | Confirmed | Synergy | 1 |  |  | Added by Synergy, updated in JIP for 29/07/21 meeting | TRUE
JM-097 | Minister Approves Tranche 6 Rule Changes | Regulatory | Significant Market Milestone | 2022-12-01 | TBC | EPWA | 0 |  |  | Note that timing remains highly uncertain at present. Date is included here to ensure the milestone appears in graphical depictions
JM-098 | Latest procedure published | WEMDI UI and E-terra integration | WEM Procedure Milestone | 2022-10-01 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-099 | Initiation | Constraint Management | Project establishment | 2020-07-01 | Complete | AEMO | 2
JM-100 | Planning | Constraint Management | Project establishment | 2020-08-03 | Complete | AEMO | 2 |  |  |  | TRUE
JM-101 | CIR publication (Interim solution) | Constraint Management | Technical Information Release | 2021-12-01 | TBC | AEMO | 1 |  |  |  | TRUE
JM-102 | Latest procedure published | Constraint Management | WEM Procedure Milestone | 2022-10-01 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project. |  |  | TRUE
JM-103 | Initiation | WEM Dispatch Engine | Project establishment | 2020-11-02 | Complete | AEMO | 2 |  |  |  | TRUE
JM-104 | Release 1 | WEM Dispatch Engine | Technical Implementation | 2022-03-14 | Confirmed | AEMO | 1 |  |  |  | TRUE
JM-105 | Latest procedure published | WEM Dispatch Engine | WEM Procedure Milestone | 2023-07-14 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project. |  |  | TRUE
JM-106 | Initiation | Real Time Market Submissions (RTMS) | Project establishment | 2020-08-31 | Complete | AEMO | 2
JM-107 | Planning complete | Real Time Market Submissions (RTMS) | Project establishment | 2021-03-29 | Complete | AEMO | 2
JM-108 | Training | Real Time Market Submissions (RTMS) | Participant training and testing | 2021-11-02 | Confirmed | AEMO | 2
JM-109 | Latest procedure published | Real Time Market Submissions (RTMS) | WEM Procedure Milestone | 2022-01-31 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-110 | Initiation | Outage Management | Project establishment | 2021-05-19 | Complete | AEMO | 2
JM-111 | Planning complete | Outage Management | Project establishment | 2021-08-13 | Confirmed | AEMO | 2
JM-112 | Test plan | Outage Management | Participant training and testing | 2022-04-25 | Confirmed | AEMO | 2
JM-113 | Release 1 | Outage Management | Technical Implementation | 2022-05-31 | TBC | AEMO | 1
JM-114 | Participant testing | Outage Management | Participant training and testing | 2022-07-13 | TBC | AEMO | 2
JM-115 | Latest procedure published | Outage Management | WEM Procedure Milestone | 2022-08-01 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-116 | Initiation | Commissioning Test | Project establishment | 2022-07-04 | Confirmed | AEMO | 2
JM-117 | Planning complete | Commissioning Test | Project establishment | 2022-07-29 | TBC | AEMO | 2
JM-118 | Latest procedure published | Commissioning Test | WEM Procedure Milestone | 2022-08-30 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-119 | Initiation | MT PASA | Project establishment | 2021-10-21 | Confirmed | AEMO | 2
JM-120 | Planning complete | MT PASA | Project establishment | 2022-02-16 | TBC | AEMO | 2
JM-121 | Test plan | MT PASA | Participant training and testing | 2022-07-14 | TBC | AEMO | 2
JM-122 | Release 1 | MT PASA | Technical Implementation | 2022-08-11 | TBC | AEMO | 1
JM-123 | Participant testing | MT PASA | Participant training and testing | 2022-09-08 | TBC | AEMO | 2
JM-124 | Latest procedure published | MT PASA | WEM Procedure Milestone | 2022-10-31 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-125 | Initiation | Forecast Integration | Project establishment | 2021-11-24 | Confirmed | AEMO | 2
JM-126 | Planning complete | Forecast Integration | Project establishment | 2022-04-06 | TBC | AEMO | 2
JM-127 | Initiation | System Operation Planning | Project establishment | 2022-07-01 | TBC | AEMO | 2
JM-128 | Planning complete | System Operation Planning | Project establishment | 2022-10-21 | TBC | AEMO | 2
JM-129 | Latest procedure published | System Operation Planning | WEM Procedure Milestone | 2022-11-01 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-130 | Initiation | ST PASA | Project establishment | 2022-07-01 | TBC | AEMO | 2
JM-131 | Planning complete | ST PASA | Project establishment | 2022-09-22 | TBC | AEMO | 2
JM-132 | Latest procedure published | ST PASA | WEM Procedure Milestone | 2023-05-15 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-133 | Initiation | Settlements Reform | Project establishment | 2021-09-15 | Confirmed | AEMO | 2
JM-134 | Planning complete | Settlements Reform | Project establishment | 2022-01-25 | TBC | AEMO | 2
JM-135 | Latest procedure published | Settlements Reform | WEM Procedure Milestone | 2023-05-01 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-136 | Release go-live (P1,R2) | RCM Reform | Technical Go-Live | 2022-02-09 | Confirmed | AEMO | 1
JM-137 | Participant testing (P1,R3) | RCM Reform | Participant training and testing | 2022-03-23 | Confirmed | AEMO | 2
JM-138 | Release go-live (P1,R3) | RCM Reform | Technical Go-Live | 2022-04-06 | Confirmed | AEMO | 1
JM-139 | Release go-live (P2) | RCM Reform | Technical Go-Live | 2022-10-03 | TBC | AEMO | 2
JM-140 | Initiation (P3) | RCM Reform | Project establishment | 2022-09-15 | TBC | AEMO | 2
JM-141 | Latest procedure published | RCM Reform | WEM Procedure Milestone | 2023-05-01 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-142 | Initiation | STEM | Project establishment | 2022-09-20 | TBC | AEMO | 2
JM-143 | Planning complete | STEM | Project establishment | 2022-10-14 | TBC | AEMO | 2
JM-144 | Participant testing | STEM | Participant training and testing | 2023-03-01 | TBC | AEMO | 2
JM-145 | Latest procedure published | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-146 | Initiation | Registrations | Project establishment | 2021-10-20 | Confirmed | AEMO | 2
JM-147 | Planning complete | Registrations | Project establishment | 2022-01-31 | TBC | AEMO | 2
JM-148 | Release 1 | Registrations | Technical Implementation | 2023-03-01 | TBC | AEMO | 1
JM-149 | Latest procedure published | Registrations | WEM Procedure Milestone | 2023-01-01 | Confirmed | AEMO | 1 | This milestone lists the latest publication date for all procedures identified by AEMO as being core to this project.
JM-150
JM-151
JM-152
JM-153
JM-154
JM-155
JM-156
JM-157
JM-158
JM-159
JM-160
JM-161
JM-162
JM-163
JM-164
JM-165
JM-166
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Level 0 - Significant 'Program Milestone' relevant to majority/all stakeholders and Market Particpants Level 1 - Significant 'Implementation Milestone' relevant to majority of stakeholders Level 2 - Important 'Implementation Milestone' relevant to one or small number of stakeholders or Market Particpants OR a preliminary milestone (e.g. early consultation in advance of formal consultation on a WEM Procedure)
Note on F25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mike replaced 1/05/21 based on WRIG-IT dates from 26/08 presentation
Note on G25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Contingent of Erika and team keeping to the 31 August commitment from WRIG-IT 26/08
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dino to check if current
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dino to check if current
Note on G35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amended 31/08/21 [Confirmed to complete] - see email from Mark McKinnon to Mike Reid same day
Note on J35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amended 31/08/21 [removed some minor details] - see email from Mark McKinnon to Mike Reid same day
Note on C57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed initials WP as believe MP was intended.
Note on F57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Edited based on discussion with Nicki 27.08.21
Note on F82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 26/08/21, Mike changed date from July to August
Note on F88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from Feb 2022
Note on F90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mike replaced 1/09/2021 with 10/11/2021 based on WRIG-IT presentation of 26/08/2021

## (Major) Change Log
JIP Release Date | Change Description
2020-12-17 | Initial set of Western Power and Synery Milestones added
2021-07-22 | Synergy milestones added (JM-094,JM-095, JM-096); Western Power milestones deleted (JM-046, JM-050, JM-060, JM-061, JM-065, JM-067) and various edits to WP titles, timings and dependencies; JM-028, 029, 083, 084 - minor date changes; JM-085 Status change confirmed to complete
2021-09-02 | Synergy milestone JM-069 deleted since this was replaced with JM-094 and JM-095
2021-09-02 | AEMO changes JM-085: Changed from 1/07 to 1/08/2021; JM-021: Changed from 1/05 to 17/09/2021; JM-055: Added a date (30/09/2021), where previously there was no date. Removed “WP” [believe was intended to be MPs]; JM-093: Replaced 1/09/2021 with 10/11/2021 based on WRIG-IT presentation of 26/08; JM-091: Modified name to clarify. Changed date from August 2021 to 28/02/2022; JM-023: Changed from 1/09/2021 to 1/02/2022; JM-024: Changed from 1/11/2021 to 1/04/2022; Also replaced "Interface Details Available" with "technical specifications available" for all AEMO milestones using the phrase
2021-09-30 | Names of existing AEMO Milestones streamlined for charting (JM-002; JM-003; JM-020; JM-021; JM-022; JM-023; JM-024; JM-025; JM-026; JM-027; JM-028; JM-029; JM-033; JM-055; JM-059; JM-082; JM-083; JM-084; JM-086; JM-087; JM-090; JM-091; JM-092; JM-093; ); New Milestone added for WEM Rules Tranche 6; New AEMO Milestones added from JM-097 to JM-149 to provide additional detail across the WEM Reform Program; Existing WEMP Milestones retained, but new WEMP milestones introduced showing when the last procedure necessary for a given project is published.

## Issue Log
ID | Issue | Raised by | Date | Status/Updates

## Lookups
Project/Topic | Type | Date Status | Owner
Connections | Business Process | To Be Confirmed | AEMO
Constraints | Significant Market Milestone | Confirmed | ERA
Generator Interim Acces (GIA) | Staging Deployment | Complete | ETIU
GPS | Technical Go-Live |  | IPPs
Program/Implementation | Technical Implementation |  | Retailers
Registrations | Technical Information Release |  | Synergy
Regulatory | Training |  | Western Power
Reserve Capacity Mechanism (RCM) | WEM Procedure Milestone
Settlements
STEM
System Planning (e.g. Outages, PASA)
WEMDE/Dispatch
Site Works (Synergy)
Technology (Synergy)
Operational Capabilities (Synergy)
Contract Remeidation (Synergy)