## Milestone Log
Foundation Regulatory Frameworks - Joint Industry Plan - Milestone Log
Source: https://aemocloud.sharepoint.com/:x:/s/WEMReformProgramTeam/EfSy0qbTEZtGiREHKf4t4tEBwAgvtu1Tdah-4p6er9l9sA?e=hE54ag
ID | Title | Project/Topic | Type | Milestone Date | Date Status | Owner | Outline Level | Description | Dependencies | Status/Comments
JM-001 | Minister Approves Tranche 1-3 Rule Changes | Regulatory | Significant Market Milestone | 2020-12-01 | Confirmed | EPWA | 2 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Tranche 1 (Nov-20): Generator Performance Standards Frame |  | On Track - all three Tranches published for consultation in October 20
JM-030 | Minister Approves Tranche 4a Rule Changes | Regulatory | Significant Market Milestone | 2021-04-30 | Confirmed | EPWA | 2 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Tranche 4: Transitional Arrangements (e.g. ESS accreditat
JM-088 | Minister Approves Tranche 4b Rule Changes | Regulatory | Significant Market Milestone | 2021-09-30 | Confirmed | EPWA | 2 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Non-Cooptimised ESS Framework Market Information Framewor
JM-089 | Minister Approves Tranche 5 Rule Changes | Regulatory | Significant Market Milestone | 2021-12-01 | Confirmed | EPWA | 2 | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Non-Cooptimised ESS Framework Market Information Framewor
JM-097 | Minister Approves Tranche 6 Rule Changes | Regulatory | Significant Market Milestone | 2022-12-01 | TBC | EPWA | 2 |  |  | Note that timing remains highly uncertain at present. Date is included here to ensure the milestone appears in graphical depictions
JM-099 | Initiation (Constraint Management) | Constraint Management | Project establishment | 2020-07-01 | Complete | AEMO | 3
JM-100 | Planning (Constraint Management) | Constraint Management | Project establishment | 2020-11-13 | Complete | AEMO | 3
JM-101 | CIR publication (Interim solution) (Constraint Management) | Constraint Management | Technical Information Release | 2021-12-31 | TBC | AEMO | 3
JM-102 | Latest procedure published (Constraint Management) | Constraint Management | WEM Procedure Milestone | 2022-07-26 | Confirmed | AEMO | 3
JM-106 | Initiation (RTMS) | RTMS | Project establishment | 2020-08-31 | Complete | AEMO | 3
JM-107 | Planning complete (RTMS) | RTMS | Project establishment | 2021-03-29 | Complete | AEMO | 3
JM-108 | Training (RTMS) | RTMS | Participant training and testing | 2021-11-02 | Confirmed | AEMO | 3
JM-021 | Technical documentation published (Release 1) (RTMS) | RTMS | Technical Information Release | 2022-01-31 | Confirmed | AEMO | 3 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) |  | AEMO plans to release a draft version 0.4 to the market in September 2021 to support training prior to MARKET TEST.
JM-109 | Latest procedure published (RTMS) | RTMS | WEM Procedure Milestone | 2021-12-10 | Confirmed | AEMO | 3
JM-103 | Initiation (WEM Dispatch Engine) | WEM Dispatch Engine | Project establishment | 2020-11-02 | Complete | AEMO | 3
JM-104 | Release 1 (WEM Dispatch Engine) | WEM Dispatch Engine | Technical Implementation | 2022-02-25 | Confirmed | AEMO | 3
JM-105 | Latest procedure published (WEM Dispatch Engine) | WEM Dispatch Engine | WEM Procedure Milestone | 2022-07-26 | Confirmed | AEMO | 3
JM-098 | Latest procedure published (WEMDE UI) | WEMDE UI | WEM Procedure Milestone | 2022-07-25 | Confirmed | AEMO | 3
JM-082 | Technical documentation published (Release 1) (Settlements Enhancements) | Settlements Enhancements | Technical Information Release | 2021-07-01 | Complete | AEMO | 3
JM-083 | Participant testing (Release 1) (Settlements Enhancements) | Settlements Enhancements | Technical Implementation | 2021-07-01 | Complete | AEMO | 3
JM-084 | Release 1 (go-live) (Settlements Enhancements) | Settlements Enhancements | Technical Go-Live | 2021-08-02 | Complete | AEMO | 3
JM-090 | Release 2 (go-live) (Settlements Enhancements) | Settlements Enhancements | Technical Go-Live | 2021-09-29 | Confirmed | AEMO | 3
JM-135 | Latest procedure published (Settlements Reform) | Settlements Reform | WEM Procedure Milestone | 2023-02-23 | Confirmed | AEMO | 3
JM-110 | Initiation (Outage Management) | Outage Management | Project establishment | 2021-05-19 | Complete | AEMO | 3
JM-111 | Planning complete (Outage Management) | Outage Management | Project establishment | 2021-09-29 | Confirmed | AEMO | 3
JM-059 | Outage Intention Plan Spec (Outage Management) | Outage Management | Technical Information Release | 2022-09-26 | TBC | AEMO | 3
JM-113 | Release 1 (Outage Management) | Outage Management | Technical Implementation | 2022-08-29 | TBC | AEMO | 3
JM-112 | Test plan (Outage Management) | Outage Management | Participant training and testing | 2022-04-25 | Confirmed | AEMO | 3
JM-023 | Business Documentation (Work Instructions, User Guides) (Outage Management) | Outage Management | Technical Information Release | 2022-09-12 | TBC | AEMO | 3 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-115 | Latest procedure published (Outage Management) | Outage Management | WEM Procedure Milestone | 2022-05-24 | Confirmed | AEMO | 3
JM-116 | Initiation (Commissioning Test) | Commissioning Test | Project establishment | 2022-07-04 | Confirmed | AEMO | 3
JM-117 | Planning complete (Commissioning Test) | Commissioning Test | Project establishment | 2022-07-29 | TBC | AEMO | 3
JM-118 | Latest procedure published (Commissioning Test) | Commissioning Test | WEM Procedure Milestone | 2022-06-23 | Confirmed | AEMO | 3
JM-119 | Initiation (MT PASA) | MT PASA | Project establishment | 2021-10-21 | Confirmed | AEMO | 3
JM-120 | Planning complete (MT PASA) | MT PASA | Project establishment | 2022-02-16 | TBC | AEMO | 3
JM-123 | Participant testing (MT PASA) | MT PASA | Participant training and testing | 2022-09-08 | TBC | AEMO | 3
JM-122 | Release 1 (MT PASA) | MT PASA | Technical Implementation | 2022-08-11 | TBC | AEMO | 3
JM-121 | Test plan (MT PASA) | MT PASA | Participant training and testing | 2022-07-13 | TBC | AEMO | 3
JM-124 | Latest procedure published (MT PASA) | MT PASA | WEM Procedure Milestone | 2022-08-23 | Confirmed | AEMO | 3
JM-125 | Initiation (Forecasting Integration) | Forecasting Integration | Project establishment | 2021-11-24 | Confirmed | AEMO | 3
JM-126 | Planning complete (Forecasting Integration) | Forecasting Integration | Project establishment | 2022-04-01 | TBC | AEMO | 3
JM-127 | Initiation (System Operation Planning) | System Operation Planning | Project establishment | 2022-07-01 | TBC | AEMO | 3
JM-128 | Planning complete (System Operation Planning) | System Operation Planning | Project establishment | 2022-10-21 | TBC | AEMO | 3
JM-129 | Latest procedure published (System Operation Planning) | System Operation Planning | WEM Procedure Milestone | 2023-05-09 | Confirmed | AEMO | 3
JM-130 | Initiation (ST PASA) | ST PASA | Project establishment | 2022-07-01 | TBC | AEMO | 3
JM-131 | Planning complete (ST PASA) | ST PASA | Project establishment | 2022-09-22 | TBC | AEMO | 3
JM-132 | Latest procedure published (ST PASA) | ST PASA | WEM Procedure Milestone | 2023-03-08 | Confirmed | AEMO | 3
JM-055 | EOI and Facility Closure Info provided (RCM) | RCM | Technical Information Release | 2021-09-30 | Complete | AEMO | 3
JM-091 | Technical documentation published (Phase 1, Release 1) (RCM) | RCM | Technical Information Release | 2021-11-09 | Complete | AEMO | 3
JM-086 | Participant testing (P1,R1) (RCM) | RCM | Technical Implementation | 2021-11-10 | Confirmed | AEMO | 3
JM-087 | Release go-live (P1,R1) (RCM) | RCM | Technical Go-Live | 2021-11-24 | Confirmed | AEMO | 3
JM-136 | Release go-live (P1,R2, internal) (RCM) | RCM | Technical Go-Live | 2022-02-09 | Confirmed | AEMO | 3
JM-137 | Participant testing (P1,R3) (RCM) | RCM | Participant training and testing | 2022-03-21 | Confirmed | AEMO | 3
JM-138 | Release go-live (P1,R3) (RCM) | RCM | Technical Go-Live | 2022-04-04 | Confirmed | AEMO | 3
JM-139 | Release go-live (P2) (RCM) | RCM | Technical Go-Live | 2022-10-03 | TBC | AEMO | 3
JM-140 | Initiation (Phase 3) (RCM) | RCM | Project establishment | 2022-09-15 | TBC | AEMO | 3
JM-141 | Latest procedure published (RCM) | RCM | WEM Procedure Milestone | 2023-02-23 | Confirmed | AEMO | 3
JM-142 | Initiation (STEM) | STEM | Project establishment | 2022-09-20 | TBC | AEMO | 3
JM-143 | Planning complete (STEM) | STEM | Project establishment | 2022-10-14 | TBC | AEMO | 3
JM-144 | Participant testing (STEM) | STEM | Participant training and testing | 2023-03-01 | TBC | AEMO | 3
JM-026 | Technical documentation published (STEM) | STEM | Technical Information Release | 2023-01-03 | TBC | AEMO | 3 | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs)
JM-028 | GPS Participant testing (GPS) | GPS | Technical Information Release | 2021-07-05 | Complete | AEMO | 3
JM-029 | AEMO GPS Repository Live (GPS) | GPS | Technical Go-Live | 2021-08-04 | Complete | AEMO | 3
JM-145 | Latest procedure published (GPS) | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | AEMO | 3
JM-146 | Initiation (Registration) | Registration | Project establishment | 2021-10-20 | Confirmed | AEMO | 3
JM-147 | Planning complete (Registration) | Registration | Project establishment | 2022-02-16 | TBC | AEMO | 3
JM-148 | Release 1 (Registration) | Registration | Technical Implementation | 2023-03-01 | TBC | AEMO | 3
JM-149 | Latest procedure published (Registration) | Registration | WEM Procedure Milestone | 2022-10-17 | Confirmed | AEMO | 3
JM-002 | Market Trial Commences (Market Trial) | Market Trial | Significant Market Milestone | 2023-03-03 | TBC | AEMO | 1 | Commencement of 'formal' Market Trial period where Market Participants and other parties will conduct defined end-to-end scenario based trials e.g. as opposed to purely system/user integration testing). |  | Scope of Market Trial and Dates to be developed via WRIG
JM-003 | New Market Go-Live (Go-Live) | Go-Live | Significant Market Milestone | 2023-10-01 | Confirmed | AEMO | 2 | Date on which first interval of Security Constrained Economic Dispatch (SCED) will take place in line with commencement of relevant WEM Rule Modifications and Go Live date referenced in WEM Rule 1.20. |  | Specific scope of Go Live milestone to be refined and defined via WRIG
JM-033 | Generator Interim Access (GIA) service ceases and dispatched using SCED (Go-Live) | Go-Live | Technical Go-Live | 2023-10-01 | Confirmed | AEMO | 3
JM-031 | Connection Application Form Updated for Constrained Access | Connections | Business Process | 2021-08-02 | Complete | Western Power | 2 | Updated customer connection application form (including information for generator performance standards) Dependant on the approval of Access Code Tranche 2 amendments. | JM-032
JM-032 | Revised Applications and Queuing Policy (AQP) and Contribution Policy Published | Regulatory | Business Process | 2021-08-02 | TBC | Western Power | 2 | Revised Applications and Queuing Policy, ETAC and Contributions Policy for constrained access (ETIU to consult industry and gazettal) Dependant on the approval of Access Code Tranche 2 amendments.
JM-034 | Terminate GIA Related NCS | Connections | Business Process | 2023-10-31 | Confirmed | Western Power | 2 | Termination of GIA related Network Control Service after new market start in conjunction with any required contract amendments for constrained access
JM-043 | Loss Factors Provided for New Market | WEM Dispatch Engine | Business Process | 2022-06-01 | Confirmed | Western Power | 2 | Finalise procedure post industry consultation | JM-042
JM-047 | GPS Submission Template provided to Market Participants | GPS | Business Process | 2020-12-01 | Complete | Western Power | 2 | Provide GPS information capture template to Market Participants
JM-048 | Draft GPS Submissions Received from Market Participants | GPS | Business Process | 2021-03-31 | Complete | Western Power | 2 | Receive draft GPS information capture template back from Market Participants. Action undertaken by Market Participants. Consult with Western Power as required. | JM-047
JM-049 | GPS Updates provided to AEMO GPS Repository | GPS | Business Process | 2022-02-28 | Confirmed | Western Power | 2 | GPS transition finalised with Market Participants and documented in Generator Register | JM-029
JM-051 | Limit Advice Development - Initial Set of Thermal Limits provided to AEMO | Constraint Management | Business Process | 2020-07-01 | Complete | Western Power | 2 | Thermal limit advice to AEMO initial set (non RCM limit advice)
JM-052 | Limit Advice Development - N-1 and N-1-1 Priority 1 Limit Advice to AEMO | Constraint Management | Business Process | 2022-01-04 | Confirmed | Western Power | 2 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 1 | JM-068
JM-053 | Limit Advice Development - N-1 and N-1-1 Priority 2 Limit Advice to AEMO | Constraint Management | Business Process | 2022-10-03 | Confirmed | Western Power | 2 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 2 | JM-052
JM-054 | Limit Advice Development - N-1 and N-1-1 Priority 3 Limit Advice to AEMO | Constraint Management | Business Process | 2023-06-01 | Confirmed | Western Power | 2 | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 3 | JM-053
JM-056 | RCM 2021 Cycle – RCM Limit Advice provided to AEMO | Reserve Capacity Mechanism (RCM) | Business Process | 2022-03-01 | TBC | Western Power | 2 | WP provides AEMO RCM Limit Advice based on AEMO's provision of RCM Requirements
JM-066 | Constrained Access Process Applies to New Access Offers | Connections | Business Process | 2020-09-18 | Complete | Western Power | 2 | The Electricity Networks Access Code Amendments (No. 2) 2020 were gazetted 18 September - no further firm (unconstrained) services for generator connections
JM-068 | Limit Advice Development - N-0 System Normal Limit Advice to AEMO | Constraint Management | Business Process | 2020-08-31 | Complete | Western Power | 2 | System Normal (N-0) non-thermal limit advice to AEMO | JM-051
JM-035 | Market Participant SCADA Requirements Provided to Western Power | Site Works (Non-Synergy) | Technical Implementation | 2022-06-01 | TBC | Western Power | 2 | Market Participants identify requirements for SCADA upgrades / changes to meet AEMO SCED requirements and provide to Western Power.
JM-036 | Western Power SCADA Works Complete (Non-Synergy) | Site Works (Non-Synergy) | Technical Implementation | 2022-12-01 | TBC | Western Power | 2 | Completion of SCADA upgrades / changes to meet AEMO SCED requirements (Note - required timeframe for market trials to be confirmed by AEMO/ WRIG) | JM-035
JM-057 | Weekly Settlement - WP and AEMO Interface - Ready for Test | Settlements Reform | Technical Implementation | 2023-01-03 | TBC | Western Power | 2 | WP and AEMO B2B Settlement interface ready for test | JM-022
JM-058 | Weekly Settlement - WP and AEMO Interface - Ready for Trials | Settlements Reform | Technical Implementation | 2022-04-01 | TBC | Western Power | 2 | WP and AEMO B2B Settlement interface ready for trials | JM-057
JM-062 | Outage Management WP and AEMO Interface - Ready for Test | Outage Management | Technical Implementation | 2022-08-01 | TBC | Western Power | 2 | WP and AEMO B2B outage management interface ready for test | JM-023
JM-063 | Outage Management WP and AEMO Interface - Ready for Trials | Outage Management | Technical Implementation | 2023-01-03 | TBC | Western Power | 2 | WP and AEMO B2B outage management interface ready for trials | JM-062
JM-064 | Outage Management WP and AEMO Interface - Ready for Market Start | Outage Management | Technical Implementation | 2023-04-03 | TBC | Western Power | 2 | WP and AEMO B2B outage management interface ready for market start | JM-063
JM-037 | WEM Procedure - Limit Advice Development - Consultation Start | Constraint Management | WEM Procedure Milestone | 2022-02-01 | TBC | Western Power | 2 | Procedure updated to include RCM limit advice requirements
JM-038 | WEM Procedure - Limit Advice Development - Procedure Live | Constraint Management | WEM Procedure Milestone | 2022-03-31 | TBC | Western Power | 2 | Finalise procedure post consultation | JM-037
JM-039 | WEM Procedure - Generator Performance Standards for Existing Transmission Connected Generating Systems - Consultation Start | GPS | WEM Procedure Milestone | 2020-12-11 | Complete | Western Power | 2 | Draft procedure complete and commence 4 weeks industry consultation
JM-040 | WEM Procedure - Generator Performance Standards for Existing Transmission Connected Generating Systems - Procedure Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | Western Power | 2 | Finalise procedure post industry consultation | JM-039
JM-041 | WEM Procedure - Loss Factors - Consultation Start | WEM Dispatch Engine | WEM Procedure Milestone | 2022-03-01 | TBC | Western Power | 2 | Draft procedure complete and commence 4 weeks industry consultation
JM-042 | WEM Procedure - Loss Factors - Procedure Live | WEM Dispatch Engine | WEM Procedure Milestone | 2022-05-02 | TBC | Western Power | 2 | Draft procedure consultation closed | JM-041
JM-044 | WEM Procedure - Generation System Model Submission and Maintenance - Consultation Start | GPS | WEM Procedure Milestone | 2020-12-11 | Complete | Western Power | 2 | Draft procedure complete and commence 4 weeks industry consultation
JM-045 | WEM Procedure - Generation System Model Submission and Maintenance - Procedure Live | GPS | WEM Procedure Milestone | 2021-02-01 | Complete | Western Power | 2 | Finalise procedure post industry consultation | JM-045
JM-080 | Commencement of GT transition planning | Operational Capabilities (Synergy) | Business Process | 2021-12-01 | Confirmed | Synergy | 2
JM-070 | Control room complete | Site Works (Synergy) | Technical Implementation | 2021-09-01 | Confirmed | Synergy | 2
JM-071 | Pinjar Control Network works complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 2
JM-072 | Site SCADA works complete | Site Works (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 2
JM-073 | Control systems works complete | Site Works (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 2
JM-074 | Western Power SCADA works complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 2
JM-075 | Application development complete – core trading system | Technology (Synergy) | Technical Implementation | 2021-11-01 | Confirmed | Synergy | 2
JM-076 | Development complete – reconciliation and settlement | Technology (Synergy) | Technical Implementation | 2022-08-01 | Confirmed | Synergy | 2
JM-077 | Migration planning and execution | Technology (Synergy) | Technical Implementation | 2022-05-02 | Confirmed | Synergy | 2
JM-094 | Pinjar comms link complete | Site Works (Synergy) | Technical Implementation | 2021-06-30 | Complete | Synergy | 2 |  |  | Added by Synergy, updated in JIP for 29/07/21 meeting; Replace JM-069
JM-095 | Kemerton comms link complete | Site Works (Synergy) | Technical Implementation | 2021-10-01 | Confirmed | Synergy | 2 |  |  | Added by Synergy, updated in JIP for 29/07/21 meeting; Replace JM-069
JM-078 | Completion of operator recruitment Ph 1 | Operational Capabilities (Synergy) | Training | 2021-07-01 | Complete | Synergy | 2
JM-079 | Completion of trader recruitment Ph1 | Operational Capabilities (Synergy) | Training | 2021-09-01 | Complete | Synergy | 2
JM-081 | Completion of trader recruitment Ph2 | Operational Capabilities (Synergy) | Training | 2022-03-01 | Confirmed | Synergy | 2
JM-096 | Completion of operator recruitment Ph 2 | Operational Capabilities (Synergy) | Training | 2021-10-01 | Confirmed | Synergy | 2 |  |  | Added by Synergy, updated in JIP for 29/07/21 meeting

## (Major) Change Log
JIP Release Date | Change Description
2020-12-17 | Initial set of Western Power and Synery Milestones added
2021-07-22 | Synergy milestones added (JM-094,JM-095, JM-096); Western Power milestones deleted (JM-046, JM-050, JM-060, JM-061, JM-065, JM-067) and various edits to WP titles, timings and dependencies; JM-028, 029, 083, 084 - minor date changes; JM-085 Status change confirmed to complete
2021-09-02 | Synergy milestone JM-069 deleted since this was replaced with JM-094 and JM-095
2021-09-02 | AEMO changes JM-085: Changed from 1/07 to 1/08/2021; JM-021: Changed from 1/05 to 17/09/2021; JM-055: Added a date (30/09/2021), where previously there was no date. Removed “WP” [believe was intended to be MPs]; JM-093: Replaced 1/09/2021 with 10/11/2021 based on WRIG-IT presentation of 26/08; JM-091: Modified name to clarify. Changed date from August 2021 to 28/02/2022; JM-023: Changed from 1/09/2021 to 1/02/2022; JM-024: Changed from 1/11/2021 to 1/04/2022; Also replaced "Interface Details Available" with "technical specifications available" for all AEMO milestones using the phrase
2021-09-30 | Names of existing AEMO Milestones streamlined for charting (JM-002; JM-003; JM-020; JM-021; JM-022; JM-023; JM-024; JM-025; JM-026; JM-027; JM-028; JM-029; JM-033; JM-055; JM-059; JM-082; JM-083; JM-084; JM-086; JM-087; JM-090; JM-091; JM-092; JM-093; ); New Milestone added for WEM Rules Tranche 6; New AEMO Milestones added from JM-097 to JM-149 to provide additional detail across the WEM Reform Program; Existing WEMP Milestones retained, but new WEMP milestones introduced showing when the last procedure necessary for a given project is published.
2021-11-25 | Removed the individual WEMP Milestones JM-004, JM-005, JM-006, JM-007, JM-008, JM-009, JM-010, JM-011, JM-012, JM-013, JM-014, JM-015, JM-016, JM-017, JM-018, JM-019, since these are now separately tracked and publicised via AEMO's WEM procedures timeline published on the WRIG website, instead each project carries a publication milestone for the last of the procedures the project must deliver - See milestones: JM-102, JM-109, JM-105, JM-098, JM-135, JM-115, JM-118, JM-124, JM-129, JM-132, JM-141, JM-145, JM-149; Removed JM-092 for RCM Phase 3 Technical documentation, since timing is too uncertain to record

## Issue Log
ID | Issue | Raised by | Date | Status/Updates

## Lookups
Project/Topic | Type | Date Status | Owner
Connections | Business Process | To Be Confirmed | AEMO
Constraints | Significant Market Milestone | Confirmed | ERA
Generator Interim Acces (GIA) | Staging Deployment | Complete | ETIU
GPS | Technical Go-Live |  | IPPs
Program/Implementation | Technical Implementation |  | Retailers
Registrations | Technical Information Release |  | Synergy
Regulatory | Training |  | Western Power
Reserve Capacity Mechanism (RCM) | WEM Procedure Milestone
Settlements
STEM
System Planning (e.g. Outages, PASA)
WEMDE/Dispatch
Site Works (Synergy)
Technology (Synergy)
Operational Capabilities (Synergy)
Contract Remeidation (Synergy)