## Task_Table1
ID | Unique_ID | Name | Owner | Start_Date | Finish_Date | Milestone_Type | Timing_Status | Project_Topic | Workstream | Description | JIP_Milestone_Ref_No_(Old) | Dependencies
1 | 3779 | Regulatory Framework |  | 1 December 2020 8:00 AM | 1 December 2022 5:00 PM
2 | 3780 | Minister Approves Tranche 1-3 Rule Changes | EPWA | 1 December 2020 8:00 AM | 1 December 2020 8:00 AM | Significant Market Milestone | Confirmed |  |  | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Tranche 1 (Nov-20): Generator Performance Standards Fram | JM-001
3 | 3794 | Minister Approves Tranche 4a Rule Changes | EPWA | 30 April 2021 8:00 AM | 30 April 2021 8:00 AM | Significant Market Milestone | Confirmed |  |  | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Tranche 4: Transitional Arrangements (e.g. ESS accredita | JM-030
4 | 3793 | Minister Approves Tranche 4b Rule Changes | EPWA | 30 September 2021 8:00 AM | 30 September 2021 8:00 AM | Significant Market Milestone | Confirmed |  |  | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Non-Cooptimised ESS Framework Market Information Framewo | JM-088
5 | 3792 | Minister Approves Tranche 5 Rule Changes | EPWA | 1 December 2021 8:00 AM | 1 December 2021 8:00 AM | Significant Market Milestone | Confirmed |  |  | Target dates for approval of WEM Rules modifications to enact WEM Reform market design as set out in Taskforce Information Papers. Milestone encompasses approval by Minister of Energy and Gazettal. Non-Cooptimised ESS Framework Market Information Framewo | JM-089
6 | 3781 | Minister Approves Tranche 6 Rule Changes | EPWA | 1 December 2022 8:00 AM | 1 December 2022 8:00 AM | Significant Market Milestone | TBC |  |  |  | JM-097
7 | 312 | SCED Workstream |  | 1 July 2020 8:00 AM | 29 September 2023 5:00 PM |  |  |  | SCED
8 | 126 | P2078 Constraint Management Reform | AEMO | 1 July 2020 8:00 AM | 31 December 2021 5:00 PM |  |  | Constraint Management | SCED
9 | 340 | Initiation (Constraint Management) | AEMO | 1 July 2020 8:00 AM | 1 July 2020 8:00 AM | Project establishment | Complete | Constraint Management | SCED |  | JM-099
10 | 2527 | Planning complete (Constraint Management) | AEMO | 13 November 2020 8:00 AM | 13 November 2020 8:00 AM | Project establishment | Complete | Constraint Management | SCED |  | JM-100
11 | 736 | CIR publication (Interim solution) (Constraint Management) | AEMO | 25 February 2022 8:00 AM | 25 February 2022 8:00 AM | Technical Information Release | TBC | Constraint Management | SCED |  | JM-101
12 | 4920 | Limit Advice Development - Initial Set of Thermal Limits provided to AEMO | Western Power | 1 July 2020 8:00 AM | 1 July 2020 8:00 AM | Business Process | Complete | Constraint Management | SCED | Thermal limit advice to AEMO initial set (non RCM limit advice) | JM-051
13 | 4921 | Limit Advice Development - N-0 System Normal Limit Advice to AEMO | Western Power | 31 August 2020 8:00 AM | 31 August 2020 8:00 AM | Business Process | Complete | Constraint Management | SCED | System Normal (N-0) non-thermal limit advice to AEMO | JM-068 | JM-051
14 | 4922 | Limit Advice Development – AEMO priority circuits | Western Power | 31 October 2022 8:00 AM | 31 October 2022 8:00 AM | Business Process | Confirmed | Constraint Management | SCED | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 1 | JM-052 | JM-068
15 | 4924 | Limit Advice Development – Network outages beyond market start | Western Power | 31 July 2023 8:00 AM | 31 July 2023 8:00 AM | Business Process | Confirmed | Constraint Management | SCED | N-1 and N-1-1 non-thermal limit advice to AEMO - Priority 3 | JM-054 | JM-053
16 | 4925 | WEM Procedure - Limit Advice Development - Consultation Start | Western Power | 1 February 2022 8:00 AM | 1 February 2022 8:00 AM | WEM Procedure Milestone | Complete | Constraint Management | SCED | Procedure updated to include RCM limit advice requirements | JM-037
17 | 4926 | WEM Procedure – Limit Advice Development – publish | Western Power | 30 April 2022 8:00 AM | 30 April 2022 8:00 AM | WEM Procedure Milestone | Confirmed | Constraint Management | SCED | Finalise procedure post consultation | JM-038 | JM-037
18 | 4939 | Connection Application Form Updated for Constrained Access | Western Power | 2 August 2021 8:00 AM | 2 August 2021 8:00 AM | Business Process | Complete | Constraint Management | SCED | Updated customer connection application form (including information for generator performance standards) Dependant on the approval of Access Code Tranche 2 amendments. | JM-031 | JM-032
19 | 4898 | WEM Procedures (Constraint Management) | AEMO | 1 July 2020 8:00 AM | 30 September 2022 5:00 PM | WEM Procedure Milestone | TBC | Constraint Management | SCED
20 | 4776 | WEM Procedure - Congestion Information Resource (Notional WRIG date) (Constraint Management) | AEMO | 28 July 2022 8:00 AM | 28 July 2022 8:00 AM | WEM Procedure Milestone | TBC | Constraint Management | SCED |  | JM-159
21 | 4777 | WEM Procedure - Congestion Information Resource (External Consultation) (Constraint Management) | AEMO | 15 August 2022 8:00 AM | 2 September 2022 5:00 PM | WEM Procedure Milestone | TBC | Constraint Management | SCED |  | JM-160
22 | 4778 | WEM Procedure - Congestion Information Resource (Publish Provisional Procedure) (Constraint Management) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | Constraint Management | SCED |  | JM-161
23 | 4779 | WEM Procedure - Constraint Formulation (Notional WRIG date) (Constraint Management) | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | WEM Procedure Milestone | TBC | Constraint Management | SCED |  | JM-156
24 | 4780 | WEM Procedure - Constraint Formulation (External Consultation) (Constraint Management) | AEMO | 12 August 2022 8:00 AM | 1 September 2022 5:00 PM | WEM Procedure Milestone | TBC | Constraint Management | SCED |  | JM-157
25 | 4781 | WEM Procedure - Constraint Formulation (Publish Provisional Procedure) (Constraint Management) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | Constraint Management | SCED |  | JM-158
26 | 4782 | WEM Procedure - Limit Advice Requirements (Notional WRIG date) (Constraint Management) | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | WEM Procedure Milestone | TBC | Constraint Management | SCED |  | JM-153
27 | 4783 | WEM Procedure - Limit Advice Requirements (External Consultation) (Constraint Management) | AEMO | 12 August 2022 8:00 AM | 1 September 2022 5:00 PM | WEM Procedure Milestone | TBC | Constraint Management | SCED |  | JM-154
28 | 4784 | WEM Procedure - Limit Advice Requirements (Publish Provisional Procedure) (Constraint Management) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | Constraint Management | SCED |  | JM-155
29 | 651 | P2171 RTMS | AEMO | 1 July 2020 8:00 AM | 31 March 2023 5:00 PM |  |  | RTMS | SCED
30 | 319 | Initiation (RTMS) | AEMO | 31 August 2020 8:00 AM | 29 March 2021 5:00 PM | Project establishment | Complete | RTMS | SCED |  | JM-106
31 | 654 | Planning complete (RTMS) | AEMO | 29 March 2021 8:00 AM | 29 March 2021 8:00 AM | Project establishment | Complete | RTMS | SCED |  | JM-107
32 | 758 | RTMS Showcases | AEMO | 2 November 2021 8:00 AM | 3 November 2021 5:00 PM | Participant training and testing | Complete | RTMS | SCED |  | JM-108
33 | 2525 | Technical documentation published (Release 1) (RTMS) | AEMO | 31 January 2022 8:00 AM | 31 January 2022 8:00 AM | Technical Information Release | Confirmed | RTMS | SCED | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) | JM-021
34 | 4946 | Market Participant Test Phase Commences | AEMO | 15 February 2022 8:00 AM | 15 February 2022 8:00 AM | Technical Implementation | TBC | RTMS | SCED | RTMS to be released into MPT environment for participants to test their ability to make submissions and query the submissions on file
35 | 4947 | Intensive Support Window for RTMS system in MPT closes | AEMO | 15 April 2022 8:00 AM | 15 April 2022 8:00 AM | Participant training and testing | TBC | RTMS | SCED | When this milestone is reached, Market Participants will still be able to access the Test Environment, but support provided by AEMO will be reduced to best endeavours.
36 | 4900 | WEM Procedures (RTMS) | AEMO | 25 November 2021 8:00 AM | 1 March 2022 5:00 PM | WEM Procedure Milestone | TBC | RTMS | SCED
37 | 4785 | WEM Procedure - Real-Time Market Submissions (Notional WRIG date) (RTMS) | AEMO | 25 November 2021 8:00 AM | 25 November 2021 8:00 AM | WEM Procedure Milestone | Complete | RTMS | SCED |  | JM-244
38 | 4786 | WEM Procedure - Real-Time Market Submissions (External Consultation) (RTMS) | AEMO | 11 January 2022 8:00 AM | 10 February 2022 5:00 PM | WEM Procedure Milestone | TBC | RTMS | SCED |  | JM-245
39 | 4787 | WEM Procedure - Real-Time Market Submissions (Publish Provisional Procedure) (RTMS) | AEMO | 1 March 2022 8:00 AM | 2 March 2022 5:00 PM | WEM Procedure Milestone | TBC | RTMS | SCED |  | JM-246
40 | 659 | P2079 WEMDE (Dispatch Engine) | AEMO | 1 July 2020 8:00 AM | 19 September 2023 5:00 PM |  |  | WEM Dispatch Engine | SCED
41 | 661 | Initiation (WEM Dispatch Engine) | AEMO | 2 November 2020 8:00 AM | 24 September 2021 5:00 PM | Project establishment | Complete | WEM Dispatch Engine | SCED |  | JM-103
42 | 4948 | Preliminary guidance on Dispatch Outcome files | AEMO | 16 December 2021 8:00 AM | 16 December 2021 8:00 AM | Technical Information Release | Complete | WEM Dispatch Engine | SCED
43 | 4949 | WEMDE Draft Specifications for Dispatch Outcome File - Release 1 | AEMO | 31 March 2022 8:00 AM | 31 March 2022 8:00 AM | Technical Information Release | Confirmed | WEM Dispatch Engine | SCED |  | JM-104
44 | 4967 | WRIG-IT session on Draft Specification for Dispatch Outcome File | AEMO | 31 March 2022 8:00 AM | 31 March 2022 8:00 AM | Information and engagement | Confirmed | WEM Dispatch Engine | SCED
45 | 4966 | SCADA Specifications for Dispatch Instructions - Release 1 | AEMO | 16 September 2022 8:00 AM | 16 September 2022 8:00 AM | Technical Information Release | Confirmed | WEM Dispatch Engine | SCED
46 | 4968 | WRIG-IT session on Dispatch instructions | AEMO | 30 September 2022 8:00 AM | 30 September 2022 8:00 AM | Information and engagement | TBC | WEM Dispatch Engine | SCED
47 | 4969 | WEMDE Showcase for external stakeholders | AEMO | 31 July 2022 8:00 AM | 31 July 2022 8:00 AM | Participant training and testing | TBC | WEM Dispatch Engine | SCED
48 | 4940 | Loss Factors Provided for New Market | Western Power | 1 June 2023 8:00 AM | 1 June 2023 8:00 AM | Business Process | Confirmed | WEM Dispatch Engine | SCED | Finalise procedure post industry consultation | JM-043 | JM-042
49 | 4910 | WEM Procedures (WEM Dispatch Engine) | AEMO | 30 June 2022 8:00 AM | 30 September 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED
50 | 4788 | WEM Procedure - Dispatch Algorithm (Notional WRIG date) (WEM Dispatch Engine) | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-177
51 | 4789 | WEM Procedure - Dispatch Algorithm (External Consultation) (WEM Dispatch Engine) | AEMO | 12 August 2022 8:00 AM | 1 September 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-178
52 | 4790 | WEM Procedure - Dispatch Algorithm (Publish Provisional Procedure) (WEM Dispatch Engine) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-179
53 | 4791 | WEM Procedure - ESS Quantity Determination Methodology (Notional WRIG date) (WEM Dispatch Engine) | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-162
54 | 4792 | WEM Procedure - ESS Quantity Determination Methodology (External Consultation) (WEM Dispatch Engine) | AEMO | 12 August 2022 8:00 AM | 1 September 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-163
55 | 4793 | WEM Procedure - ESS Quantity Determination Methodology (Publish Provisional Procedure) (WEM Dispatch Engine) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-164
56 | 4794 | WEM Procedure - Monitoring and Reporting Compliance (Notional WRIG date) (WEM Dispatch Engine) | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-165
57 | 4795 | WEM Procedure - Monitoring and Reporting Compliance (External Consultation) (WEM Dispatch Engine) | AEMO | 12 August 2022 8:00 AM | 1 September 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-166
58 | 4796 | WEM Procedure - Monitoring and Reporting Compliance (Publish Provisional Procedure) (WEM Dispatch Engine) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-167
59 | 4797 | WEM Procedure - Price Determination (Notional WRIG date) (WEM Dispatch Engine) | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-174
60 | 4798 | WEM Procedure - Price Determination (External Consultation) (WEM Dispatch Engine) | AEMO | 12 August 2022 8:00 AM | 1 September 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-175
61 | 4799 | WEM Procedure - Price Determination (Publish Provisional Procedure) (WEM Dispatch Engine) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-176
62 | 4800 | WEM Procedure - Real-Time Market Timetable (Notional WRIG date) (WEM Dispatch Engine) | AEMO | 28 July 2022 8:00 AM | 28 July 2022 8:00 AM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-171
63 | 4801 | WEM Procedure - Real-Time Market Timetable (External Consultation) (WEM Dispatch Engine) | AEMO | 15 August 2022 8:00 AM | 2 September 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-172
64 | 4802 | WEM Procedure - Real-Time Market Timetable (Publish Provisional Procedure) (WEM Dispatch Engine) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED |  | JM-173
65 | 4945 | WEM procedure determining loss factors (Notional WRIG) | Western Power | 28 July 2022 8:00 AM | 28 July 2022 8:00 AM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED
66 | 4937 | WEM procedure determining loss factors (Consultation start) | Western Power | 1 August 2022 8:00 AM | 1 August 2022 8:00 AM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED | Draft procedure complete and commence 4 weeks industry consultation | JM-041
67 | 4938 | WEM procedure determining loss factors (Publish) | Western Power | 1 October 2023 8:00 AM | 1 October 2023 8:00 AM | WEM Procedure Milestone | TBC | WEM Dispatch Engine | SCED | Publication date is yet to be confirmed. Date currently given reflects the in-force date. | JM-042 | JM-041
68 | 1232 | P2170 WEMDE UI | AEMO | 1 July 2020 8:00 AM | 20 February 2023 5:00 PM |  |  | WEMDE UI | SCED
69 | 4899 | WEM Procedures (WEMDE UI) | AEMO | 30 June 2022 8:00 AM | 30 September 2022 5:00 PM | WEM Procedure Milestone | TBC | WEMDE UI | SCED
70 | 4803 | WEM Procedure - Dispatch Settlement and Monitoring Data (Notional WRIG date) (WEMDE UI) | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | WEM Procedure Milestone | TBC | WEMDE UI | SCED |  | JM-183
71 | 4804 | WEM Procedure - Dispatch Settlement and Monitoring Data (External Consultation) (WEMDE UI) | AEMO | 12 August 2022 8:00 AM | 1 September 2022 5:00 PM | WEM Procedure Milestone | TBC | WEMDE UI | SCED |  | JM-184
72 | 4805 | WEM Procedure - Dispatch Settlement and Monitoring Data (Publish Provisional Procedure) (WEMDE UI) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | WEMDE UI | SCED |  | JM-185
73 | 4806 | WEM Procedure - Facility Dispatch Process (Notional WRIG date) (WEMDE UI) | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | WEM Procedure Milestone | TBC | WEMDE UI | SCED |  | JM-180
74 | 4807 | WEM Procedure - Facility Dispatch Process (External Consultation) (WEMDE UI) | AEMO | 12 August 2022 8:00 AM | 1 September 2022 5:00 PM | WEM Procedure Milestone | TBC | WEMDE UI | SCED |  | JM-181
75 | 4808 | WEM Procedure - Facility Dispatch Process (Publish Provisional Procedure) (WEMDE UI) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | WEMDE UI | SCED |  | JM-182
76 | 4809 | WEM Procedure - Notices and Communications (Notional WRIG date) (WEMDE UI) | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | WEM Procedure Milestone | TBC | WEMDE UI | SCED |  | JM-168
77 | 4810 | WEM Procedure - Notices and Communications (External Consultation) (WEMDE UI) | AEMO | 12 August 2022 8:00 AM | 1 September 2022 5:00 PM | WEM Procedure Milestone | TBC | WEMDE UI | SCED |  | JM-169
78 | 4811 | WEM Procedure - Notices and Communications (Publish Provisional Procedure) (WEMDE UI) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | WEMDE UI | SCED |  | JM-170
79 | 313 | Settlements Workstream |  | 1 July 2020 8:00 AM | 1 May 2023 5:00 PM |  | Confirmed |  | Settlements
80 | 648 | P1639 Settlements Enhancements | AEMO | 1 July 2020 8:00 AM | 29 September 2021 5:00 PM |  |  | Settlements Enhancements | Settlements
81 | 3897 | Technical documentation published (Release 1) (Settlements Enhancements) | AEMO | 1 July 2021 8:00 AM | 1 July 2021 8:00 AM | Technical Information Release | Complete | Settlements Enhancements | Settlements |  | JM-082
82 | 3898 | Participant testing (Release 1) (Settlements Enhancements) | AEMO | 1 July 2021 8:00 AM | 1 July 2021 8:00 AM | Technical Implementation | Complete | Settlements Enhancements | Settlements |  | JM-083
83 | 1053 | Release 1 (go-live) (Settlements Enhancements) | AEMO | 2 August 2021 8:00 AM | 2 August 2021 8:00 AM | Technical Go-Live | Complete | Settlements Enhancements | Settlements |  | JM-084
84 | 1969 | Release 2 (go-live) (Settlements Enhancements) | AEMO | 29 September 2021 8:00 AM | 29 September 2021 8:00 AM | Technical Go-Live | Complete | Settlements Enhancements | Settlements |  | JM-090
85 | 330 | P2106 Settlements Reform | AEMO | 26 August 2021 8:00 AM | 27 January 2023 5:00 PM |  |  | Settlements Reform | Settlements
86 | 1076 | Planning complete (Settlements Reform) | AEMO | 20 January 2022 8:00 AM | 20 January 2022 8:00 AM | Project establishment | TBC | Settlements Reform | Settlements |  | JM-134
87 | 1058 | Settlements API specification published | AEMO | 12 August 2022 8:00 AM | 12 August 2022 8:00 AM | Technical Information Release | TBC | Settlements Reform | Settlements |  | JM-022
88 | 4950 | Settlements Formulation Document Released (Draft) | AEMO | 15 April 2022 8:00 AM | 15 April 2022 8:00 AM | Technical Information Release | TBC | Settlements Reform | Settlements | AEMO intends to publish a draft version, giving Market Participants an early view of the formulation document, prior to having the document independently certified.
89 | 4951 | Settlements Formulation Document Released (Certified and Finalised) | AEMO |  |  | Technical Information Release | TBC | Settlements Reform | Settlements
90 | 4955 | Capacity Credits Allocation API Specification | AEMO | 17 June 2022 8:00 AM | 17 June 2022 8:00 AM | Technical Information Release | TBC | Settlements Reform | Settlements | These system changes will be undertaken as part of the Settlements Project although this in an RCM-related feature
91 | 4930 | Weekly Settlement - WP and AEMO Interface - Ready for Test | Western Power | 3 January 2023 8:00 AM | 3 January 2023 8:00 AM | Technical Implementation | TBC | Settlements Reform | Settlements | WP and AEMO B2B Settlement interface ready for test | JM-057 | JM-022
92 | 4931 | Weekly Settlement - WP and AEMO Interface - Ready for Trials | Western Power | 1 April 2023 8:00 AM | 1 April 2023 8:00 AM | Technical Implementation | TBC | Settlements Reform | Settlements | WP and AEMO B2B Settlement interface ready for trials | JM-058 | JM-057
93 | 4904 | WEM Procedures (Settlements Reform) | AEMO | 26 January 2023 8:00 AM | 1 May 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements
94 | 4812 | WEM Procedure - Capacity Credit Allocations (Notional WRIG date) (Settlements Reform) | AEMO | 23 February 2023 8:00 AM | 23 February 2023 8:00 AM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-253
95 | 4813 | WEM Procedure - Capacity Credit Allocations (External Consultation) (Settlements Reform) | AEMO | 15 March 2023 8:00 AM | 4 April 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-254
96 | 4814 | WEM Procedure - Capacity Credit Allocations (Publish Provisional Procedure) (Settlements Reform) | AEMO | 1 May 2023 8:00 AM | 2 May 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-255
97 | 4815 | WEM Procedure - Individual Reserve Capacity Requirements (IRCR) (Notional WRIG date) (Settlements Reform) | AEMO | 23 February 2023 8:00 AM | 23 February 2023 8:00 AM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-256
98 | 4816 | WEM Procedure - Individual Reserve Capacity Requirements (IRCR) (External Consultation) (Settlements Reform) | AEMO | 15 March 2023 8:00 AM | 4 April 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-257
99 | 4817 | WEM Procedure - Individual Reserve Capacity Requirements (IRCR) (Publish Provisional Procedure) (Settlements Reform) | AEMO | 1 May 2023 8:00 AM | 2 May 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-258
100 | 4818 | WEM Procedure - Meter Data Submission Procedure (Notional WRIG date) (Settlements Reform) | AEMO | 26 January 2023 8:00 AM | 26 January 2023 8:00 AM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-247
101 | 4819 | WEM Procedure - Meter Data Submission Procedure (External Consultation) (Settlements Reform) | AEMO | 14 March 2023 8:00 AM | 3 April 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-248
102 | 4820 | WEM Procedure - Meter Data Submission Procedure (Publish Provisional Procedure) (Settlements Reform) | AEMO | 1 May 2023 8:00 AM | 2 May 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-249
103 | 4821 | WEM Procedure - Prudential Requirements (Notional WRIG date) (Settlements Reform) | AEMO | 26 January 2023 8:00 AM | 26 January 2023 8:00 AM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-259
104 | 4822 | WEM Procedure - Prudential Requirements (External Consultation) (Settlements Reform) | AEMO | 14 March 2023 8:00 AM | 3 April 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-260
105 | 4823 | WEM Procedure - Prudential Requirements (Publish Provisional Procedure) (Settlements Reform) | AEMO | 1 May 2023 8:00 AM | 2 May 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-261
106 | 4824 | WEM Procedure - Settlements (Notional WRIG date) (Settlements Reform) | AEMO | 26 January 2023 8:00 AM | 26 January 2023 8:00 AM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-250
107 | 4825 | WEM Procedure - Settlements (External Consultation) (Settlements Reform) | AEMO | 14 March 2023 8:00 AM | 3 April 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-251
108 | 4826 | WEM Procedure - Settlements (Publish Provisional Procedure) (Settlements Reform) | AEMO | 1 May 2023 8:00 AM | 2 May 2023 5:00 PM | WEM Procedure Milestone | TBC | Settlements Reform | Settlements |  | JM-252
109 | 314 | System Planning Workstream P2105 |  | 19 May 2021 8:00 AM | 13 November 2023 5:00 PM |  |  | Outage Management | System Planning
110 | 1586 | P2105 Outage Management |  | 19 May 2021 8:00 AM | 1 December 2022 5:00 PM |  |  | Outage Management | System Planning
111 | 1604 | Release 1 (Outage Management) | AEMO | 17 June 2022 8:00 AM | 17 June 2022 8:00 AM | Technical Implementation | TBC | Outage Management | System Planning | Scope includes: OM User Interface for Market Participants, Submission of Outage Plans, Amend, Withdrawal, History, AEMO assessment and monitoring UI | JM-113
112 | 4957 | Market Test for Market Participants commence (Release 1) | AEMO | 17 June 2022 8:00 AM | 17 June 2022 8:00 AM | Technical Implementation | TBC | Outage Management | System Planning
113 | 2521 | Network Operator API specifications | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | Project establishment | TBC | Outage Management | System Planning |  | JM-111
114 | 4956 | Release 2 (Outage Management) | AEMO | 18 November 2022 8:00 AM | 18 November 2022 8:00 AM | Technical Implementation | TBC | Outage Management | System Planning | Scope includes: OM API for network operator, covering Planned / Opportunistic / Forced Outages
115 | 4958 | Market Test for Network Operator commence (Release 2) | AEMO | 18 November 2022 8:00 AM | 18 November 2022 8:00 AM | Technical Implementation | TBC | Outage Management | System Planning
116 | 4932 | Outage Management WP and AEMO Interface - Ready for Test | Western Power | 1 August 2022 8:00 AM | 1 August 2022 8:00 AM | Technical Implementation | TBC | Outage Management | System Planning | WP and AEMO B2B outage management interface ready for test | JM-062 | JM-023
117 | 4933 | Outage Management WP and AEMO Interface - Ready for Trials | Western Power | 3 January 2023 8:00 AM | 3 January 2023 8:00 AM | Technical Implementation | TBC | Outage Management | System Planning | WP and AEMO B2B outage management interface ready for trials | JM-063 | JM-062
118 | 4934 | Outage Management WP and AEMO Interface - Ready for Market Start | Western Power | 3 April 2023 8:00 AM | 3 April 2023 8:00 AM | Technical Implementation | TBC | Outage Management | System Planning | WP and AEMO B2B outage management interface ready for market start | JM-064 | JM-063
119 | 4909 | WEM Procedures (Outage Management) | AEMO | 28 April 2022 8:00 AM | 1 August 2022 5:00 PM | WEM Procedure Milestone | TBC | Outage Management | System Planning
120 | 4827 | WEM Procedure - Outages (Notional WRIG date) (Outage Management) | AEMO | 28 April 2022 8:00 AM | 28 April 2022 8:00 AM | WEM Procedure Milestone | TBC | Outage Management | System Planning |  | JM-150
121 | 4828 | WEM Procedure - Outages (External Consultation) (Outage Management) | AEMO | 14 June 2022 8:00 AM | 5 July 2022 5:00 PM | WEM Procedure Milestone | TBC | Outage Management | System Planning |  | JM-151
122 | 4829 | WEM Procedure - Outages (Publish Provisional Procedure) (Outage Management) | AEMO | 1 August 2022 8:00 AM | 2 August 2022 5:00 PM | WEM Procedure Milestone | TBC | Outage Management | System Planning |  | JM-152
123 | 1619 | P2215 Commissioning Test | AEMO | 4 July 2022 8:00 AM | 24 March 2023 5:00 PM |  |  | Commissioning Test | System Planning
124 | 1620 | Initiation (Commissioning Test) | AEMO | 4 July 2022 8:00 AM | 3 August 2022 5:00 PM | Project establishment | Confirmed | Commissioning Test | System Planning |  | JM-116
125 | 1624 | Planning complete (Commissioning Test) | AEMO | 29 July 2022 8:00 AM | 29 July 2022 8:00 AM | Project establishment | TBC | Commissioning Test | System Planning |  | JM-117
126 | 4908 | WEM Procedures (Commissioning Test) | AEMO | 26 May 2022 8:00 AM | 30 August 2022 5:00 PM | WEM Procedure Milestone | TBC | Commissioning Test | System Planning
127 | 4830 | WEM Procedure - Commissioning Tests (Notional WRIG date) (Commissioning Test) | AEMO | 26 May 2022 8:00 AM | 26 May 2022 8:00 AM | WEM Procedure Milestone | TBC | Commissioning Test | System Planning |  | JM-189
128 | 4831 | WEM Procedure - Commissioning Tests (External Consultation) (Commissioning Test) | AEMO | 13 July 2022 8:00 AM | 2 August 2022 5:00 PM | WEM Procedure Milestone | TBC | Commissioning Test | System Planning |  | JM-190
129 | 4832 | WEM Procedure - Commissioning Tests (Publish Provisional Procedure) (Commissioning Test) | AEMO | 30 August 2022 8:00 AM | 31 August 2022 5:00 PM | WEM Procedure Milestone | TBC | Commissioning Test | System Planning |  | JM-191
130 | 1656 | P2216 MT PASA | AEMO | 5 July 2021 8:00 AM | 22 December 2022 5:00 PM |  |  | MT PASA | System Planning
131 | 1657 | Initiation (MT PASA) | AEMO | 26 July 2021 8:00 AM | 21 February 2022 5:00 PM | Project establishment | Confirmed | MT PASA | System Planning |  | JM-119
132 | 1661 | Work Package 1 (planning and commercials) complete | AEMO | 31 March 2022 8:00 AM | 31 March 2022 8:00 AM | Project establishment | Confirmed | MT PASA | System Planning | In this stage, AEMO completes commercial and planning tasks | JM-120
133 | 4960 | Work Package 2 (proof of concept) complete | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | Technical Implementation | TBC | MT PASA | System Planning | In this stage, AEMO will build a proof of concept model of the SWIS, using proprietary modelling software
134 | 4961 | Work Package 3 (execution) complete | AEMO | 30 November 2022 8:00 AM | 30 November 2022 8:00 AM | Technical Implementation | TBC | MT PASA | System Planning | In this stage, AEMO will integrate the SWIS model with other modules to establish the full stochastic modelling solution
135 | 1673 | Release 1 (MT PASA) | AEMO | 13 September 2022 8:00 AM | 13 September 2022 8:00 AM | Technical Implementation | TBC | MT PASA | System Planning |  | JM-122
136 | 4907 | WEM Procedures (MT PASA) | AEMO | 27 January 2022 8:00 AM | 31 October 2022 5:00 PM | WEM Procedure Milestone | Confirmed | MT PASA | System Planning
137 | 4833 | WEM Procedure - MT PASA (Notional WRIG date) (MT PASA) | AEMO | 27 January 2022 8:00 AM | 27 January 2022 8:00 AM | WEM Procedure Milestone | TBC | MT PASA | System Planning |  | JM-195
138 | 4834 | WEM Procedure - MT PASA (External Consultation) (MT PASA) | AEMO | 9 March 2022 8:00 AM | 30 March 2022 5:00 PM | WEM Procedure Milestone | TBC | MT PASA | System Planning |  | JM-196
139 | 4835 | WEM Procedure - MT PASA (Publish Provisional Procedure) (MT PASA) | AEMO | 29 April 2022 8:00 AM | 2 May 2022 5:00 PM | WEM Procedure Milestone | TBC | MT PASA | System Planning |  | JM-197
140 | 4836 | WEM Procedure - SESSM Procurement (Notional WRIG date) (MT PASA) | AEMO | 30 June 2022 8:00 AM | 30 June 2022 8:00 AM | WEM Procedure Milestone | TBC | MT PASA | System Planning |  | JM-192
141 | 4837 | WEM Procedure - SESSM Procurement (External Consultation) (MT PASA) | AEMO | 12 September 2022 8:00 AM | 30 September 2022 5:00 PM | WEM Procedure Milestone | TBC | MT PASA | System Planning |  | JM-193
142 | 4838 | WEM Procedure - SESSM Procurement (Publish Provisional Procedure) (MT PASA) | AEMO | 31 October 2022 8:00 AM | 1 November 2022 5:00 PM | WEM Procedure Milestone | TBC | MT PASA | System Planning |  | JM-194
143 | 1688 | P2217 Forecast Integration (FI) | AEMO | 5 July 2021 8:00 AM | 9 January 2023 5:00 PM |  |  | Forecasting Integration | System Planning
144 | 1689 | Initiation (Forecasting Integration) | AEMO | 4 October 2021 8:00 AM | 31 December 2021 5:00 PM | Project establishment | Confirmed | Forecasting Integration | System Planning |  | JM-125
145 | 1693 | Planning complete (Forecasting Integration) | AEMO | 31 December 2021 8:00 AM | 31 December 2021 8:00 AM | Project establishment | TBC | Forecasting Integration | System Planning |  | JM-126
146 | 1824 | P2218 SO Planning Tools | AEMO | 1 July 2022 8:00 AM | 12 June 2023 5:00 PM |  |  | System Operation Planning Tools | System Planning
147 | 1825 | Initiation (System Operation Planning Tools) | AEMO | 1 July 2022 8:00 AM | 21 October 2022 5:00 PM | Project establishment | TBC | System Operation Planning Tools | System Planning |  | JM-127
148 | 1829 | Planning complete (System Operation Planning Tools) | AEMO | 21 October 2022 8:00 AM | 21 October 2022 8:00 AM | Project establishment | TBC | System Operation Planning Tools | System Planning |  | JM-128
149 | 4905 | WEM Procedures (System Operation Planning Tools) | AEMO | 28 July 2022 8:00 AM | 14 July 2023 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning
150 | 4839 | WEM Procedure - IMS Interface for Network Operators (Notional WRIG date) (System Operation Planning Tools) | AEMO | 27 April 2023 8:00 AM | 27 April 2023 8:00 AM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-262
151 | 4840 | WEM Procedure - IMS Interface for Network Operators (External Consultation) (System Operation Planning Tools) | AEMO | 29 May 2023 8:00 AM | 16 June 2023 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-263
152 | 4841 | WEM Procedure - IMS Interface for Network Operators (Publish Provisional Procedure) (System Operation Planning Tools) | AEMO | 14 July 2023 8:00 AM | 17 July 2023 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-264
153 | 4842 | WEM Procedure - Low Reserve Conditions (Notional WRIG date) (System Operation Planning Tools) | AEMO | 28 July 2022 8:00 AM | 28 July 2022 8:00 AM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-268
154 | 4843 | WEM Procedure - Low Reserve Conditions (External Consultation) (System Operation Planning Tools) | AEMO | 13 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-269
155 | 4844 | WEM Procedure - Low Reserve Conditions (Publish Provisional Procedure) (System Operation Planning Tools) | AEMO | 1 November 2022 8:00 AM | 2 November 2022 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-270
156 | 4845 | WEM Procedure - Network Modelling Data (Notional WRIG date) (System Operation Planning Tools) | AEMO | 28 July 2022 8:00 AM | 28 July 2022 8:00 AM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-186
157 | 4846 | WEM Procedure - Network Modelling Data (External Consultation) (System Operation Planning Tools) | AEMO | 15 August 2022 8:00 AM | 2 September 2022 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-187
158 | 4847 | WEM Procedure - Network Modelling Data (Publish Provisional Procedure) (System Operation Planning Tools) | AEMO | 30 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-188
159 | 4848 | WEM Procedure - Power System Security (Notional WRIG date) (System Operation Planning Tools) | AEMO | 28 July 2022 8:00 AM | 28 July 2022 8:00 AM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-271
160 | 4849 | WEM Procedure - Power System Security (External Consultation) (System Operation Planning Tools) | AEMO | 13 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-272
161 | 4850 | WEM Procedure - Power System Security (Publish Provisional Procedure) (System Operation Planning Tools) | AEMO | 1 November 2022 8:00 AM | 2 November 2022 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-273
162 | 4851 | WEM Procedure - Reliability Standard Implementation (Notional WRIG date) (System Operation Planning Tools) | AEMO | 28 July 2022 8:00 AM | 28 July 2022 8:00 AM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-265
163 | 4852 | WEM Procedure - Reliability Standard Implementation (External Consultation) (System Operation Planning Tools) | AEMO | 13 September 2022 8:00 AM | 3 October 2022 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-266
164 | 4853 | WEM Procedure - Reliability Standard Implementation (Publish Provisional Procedure) (System Operation Planning Tools) | AEMO | 1 November 2022 8:00 AM | 2 November 2022 5:00 PM | WEM Procedure Milestone | TBC | System Operation Planning Tools | System Planning |  | JM-267
165 | 1856 | P2219 ST PASA | AEMO | 1 July 2022 8:00 AM | 13 November 2023 5:00 PM |  |  | ST PASA | System Planning
166 | 1857 | Initiation (ST PASA) | AEMO | 1 July 2022 8:00 AM | 22 September 2022 5:00 PM | Project establishment | TBC | ST PASA | System Planning |  | JM-130
167 | 1861 | Planning complete (ST PASA) | AEMO | 22 September 2022 8:00 AM | 22 September 2022 8:00 AM | Project establishment | TBC | ST PASA | System Planning |  | JM-131
168 | 4906 | WEM Procedures (ST PASA) | AEMO | 23 February 2023 8:00 AM | 15 May 2023 5:00 PM | WEM Procedure Milestone | TBC | ST PASA | System Planning
169 | 4854 | WEM Procedure - ST PASA (Notional WRIG date) (ST PASA) | AEMO | 23 February 2023 8:00 AM | 23 February 2023 8:00 AM | WEM Procedure Milestone | TBC | ST PASA | System Planning |  | JM-274
170 | 4855 | WEM Procedure - ST PASA (External Consultation) (ST PASA) | AEMO | 28 March 2023 8:00 AM | 17 April 2023 5:00 PM | WEM Procedure Milestone | TBC | ST PASA | System Planning |  | JM-275
171 | 4856 | WEM Procedure - ST PASA (Publish Provisional Procedure) (ST PASA) | AEMO | 15 May 2023 8:00 AM | 16 May 2023 5:00 PM | WEM Procedure Milestone | TBC | ST PASA | System Planning |  | JM-276
172 | 316 | Legacy Market Workstream |  | 16 March 2021 8:00 AM | 4 September 2023 5:00 PM |  |  |  | Legacy Market Workstream
173 | 4928 | Reserve Capacity |  | 16 March 2021 8:00 AM | 4 September 2023 5:00 PM |  |  |  | Legacy Market Workstream
174 | 351 | Phase 1 - Indicative Facility Class, CRC Application & RLM | AEMO | 14 April 2021 8:00 AM | 4 September 2023 5:00 PM |  | Confirmed | RCM | Legacy Market Workstream
175 | 3893 | EOI and Facility Closure Info provided (RCM) | AEMO | 30 September 2021 8:00 AM | 30 September 2021 8:00 AM | Technical Information Release | Complete | RCM | Legacy Market Workstream |  | JM-055
176 | 3804 | Technical documentation published (Phase 1, Release 1) (RCM) | AEMO | 9 November 2021 8:00 AM | 9 November 2021 8:00 AM | Technical Information Release | Complete | RCM | Legacy Market Workstream |  | JM-091
177 | 1137 | Participant testing (P1,R1) (RCM) | AEMO | 10 November 2021 8:00 AM | 23 November 2021 5:00 PM | Technical Implementation | Confirmed | RCM | Legacy Market Workstream |  | JM-086
178 | 1174 | Release go-live (P1,R1) (RCM) | AEMO | 24 November 2021 8:00 AM | 24 November 2021 8:00 AM | Technical Go-Live | Confirmed | RCM | Legacy Market Workstream |  | JM-087
179 | 1176 | Release go-live (P1,R2, internal) (RCM) | AEMO | 9 February 2022 8:00 AM | 9 February 2022 8:00 AM | Technical Go-Live | Complete | RCM | Legacy Market Workstream |  | JM-136
180 | 4954 | Market Trial information published (P1,R3) (RCM) | AEMO | 3 March 2022 8:00 AM | 3 March 2022 8:00 AM | Technical Information Release | Complete | RCM | Legacy Market Workstream | Likely to take the form of an email to market participants and updates to the Reformer
181 | 4952 | Technical docs published (P1,R3) (RCM) - minor changes to: Release Notes, User Guide and Submission Spec Document (re Trade Declarations) | AEMO | 9 March 2021 8:00 AM | 9 March 2021 8:00 AM | Technical Information Release | Complete | RCM | Legacy Market Workstream
182 | 1214 | Participant testing (P1,R3) (RCM) | AEMO | 16 March 2022 8:00 AM | 29 March 2022 5:00 PM | Participant training and testing | Confirmed | RCM | Legacy Market Workstream |  | JM-137
183 | 4963 | WRIG Information session outlining consultation process for NAQ WEM Procedure | AEMO | 24 March 2022 8:00 AM | 24 March 2022 8:00 AM | Information and engagement | Complete | RCM | Legacy Market Workstream
184 | 1213 | Release go-live (P1,R3) (RCM) | AEMO | 30 March 2022 8:00 AM | 30 March 2022 8:00 AM | Technical Go-Live | Confirmed | RCM | Legacy Market Workstream |  | JM-138
185 | 724 | RCM Reform Phase 2 - NAQ | AEMO | 1 July 2021 8:00 AM | 10 March 2023 5:00 PM |  | Confirmed | RCM | Legacy Market Workstream
186 | 4970 | WRIG session explaining NAQ Consult Plan | AEMO | 24 March 2022 8:00 AM | 24 March 2022 8:00 AM | Information and engagement | Complete | RCM | Legacy Market Workstream
187 | 4962 | WRIG-IT Information session explaining key NAQ changes, project approach and engagement | AEMO | 31 March 2022 8:00 AM | 31 March 2022 8:00 AM | Project establishment | Confirmed | RCM | Legacy Market Workstream
188 | 4975 | WRIG IT session explaining RCM Release 2.1 Test Plan | AEMO | 1 September 2022 8:00 AM | 1 September 2022 8:00 AM | Participant training and testing | TBC | RCM | Legacy Market Workstream
189 | 4976 | Publish RCM Release 2.1 Technical documentation | AEMO | 21 September 2022 8:00 AM | 21 September 2022 8:00 AM | Technical Information Release | Confirmed | RCM | Legacy Market Workstream | Release Notes, User Guide, Submission Specification
190 | 4977 | RCM Portal Release 2.1 Market Trial | AEMO | 28 September 2022 8:00 AM | 28 September 2022 8:00 AM | Participant training and testing | Confirmed | RCM | Legacy Market Workstream
191 | 4978 | RCM Portal Release 2.1 Go-Live | AEMO | 12 October 2022 8:00 AM | 12 October 2022 8:00 AM | Technical Go-Live | Confirmed | RCM | Legacy Market Workstream |  | Replaces JM-139
192 | 4979 | Release information explaining RCM Release 2.2 Test Plan | AEMO | 16 January 2023 8:00 AM | 16 January 2023 8:00 AM | Participant training and testing | TBC | RCM | Legacy Market Workstream
193 | 4980 | Publish RCM Release 2.2 Technical documentation | AEMO | 18 January 2023 8:00 AM | 18 January 2023 8:00 AM | Technical Information Release | Confirmed | RCM | Legacy Market Workstream | Release Notes, User Guide, Submission Specification
194 | 4981 | RCM Portal Release 2.2 Market Trial | AEMO | 25 January 2023 8:00 AM | 25 January 2023 8:00 AM | Participant training and testing | Confirmed | RCM | Legacy Market Workstream
195 | 4982 | RCM Portal Release 2.2 Go-Live | AEMO | 8 February 2023 8:00 AM | 8 February 2023 8:00 AM | Technical Go-Live | Confirmed | RCM | Legacy Market Workstream |  | Replaces JM-139
196 | 4983 | WRIG IT session explaining RCM Release 2.3 Test Plan | AEMO | 3 March 2023 8:00 AM | 3 March 2023 8:00 AM | Participant training and testing | TBC | RCM | Legacy Market Workstream
197 | 4984 | Publish RCM Release 2.3 Technical documentation | AEMO | 15 March 2023 8:00 AM | 15 March 2023 8:00 AM | Technical Information Release | Confirmed | RCM | Legacy Market Workstream | Release Notes, User Guide, Submission Specification
198 | 4985 | RCM Portal Release 2.3 Market Trial | AEMO | 22 March 2023 8:00 AM | 22 March 2023 8:00 AM | Participant training and testing | Confirmed | RCM | Legacy Market Workstream
199 | 4986 | RCM Portal Release 2.3 and NAQ Solution Go-Live | AEMO | 5 April 2023 8:00 AM | 5 April 2023 8:00 AM | Technical Go-Live | Confirmed | RCM | Legacy Market Workstream |  | Replaces JM-139
200 | 4974 | RCM Portal Final Release and NAQ Solution Go-Live | AEMO | 5 April 2023 8:00 AM | 5 April 2023 8:00 AM | Technical Go-Live | Confirmed | RCM | Legacy Market Workstream |  | Replaces JM-139
201 | 725 | RCM Reform Phase 3 | AEMO | 15 September 2022 8:00 AM | 15 September 2022 8:00 AM |  | Confirmed | RCM | Legacy Market Workstream
202 | 2524 | Initiation (Phase 3) (RCM) | AEMO | 15 September 2022 8:00 AM | 15 September 2022 8:00 AM | Project establishment | TBC | RCM | Legacy Market Workstream |  | JM-140
203 | 4903 | WEM Procedures and related artefacts (RCM) | AEMO | 25 November 2021 8:00 AM | 1 May 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream
204 | 4857 | WEM Procedure - Assignment of NAQs (Notional WRIG date) (RCM) | AEMO | 26 May 2022 8:00 AM | 26 May 2022 8:00 AM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-205
205 | 4858 | WEM Procedure - Assignment of NAQs (External Consultation) (RCM) | AEMO | 15 July 2022 8:00 AM | 4 August 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-206
206 | 4859 | WEM Procedure - Assignment of NAQs (Publish Provisional Procedure) (RCM) | AEMO | 1 September 2022 8:00 AM | 2 September 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-207
207 | 4860 | WEM Procedure - Consumption Deviation Applications (Notional WRIG date) (RCM) | AEMO | 23 February 2023 8:00 AM | 23 February 2023 8:00 AM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-220
208 | 4861 | WEM Procedure - Consumption Deviation Applications (External Consultation) (RCM) | AEMO | 15 March 2023 8:00 AM | 4 April 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-221
209 | 4862 | WEM Procedure - Consumption Deviation Applications (Publish Provisional Procedure) (RCM) | AEMO | 1 May 2023 8:00 AM | 2 May 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-222
210 | 4863 | WEM Procedure - Declaration of Bilateral Trades and the Capacity Credit assignment (2021 Cycle) (Notional WRIG date) (RCM) | AEMO | 25 November 2021 8:00 AM | 25 November 2021 8:00 AM | WEM Procedure Milestone | Complete | RCM | Legacy Market Workstream |  | JM-208
211 | 4864 | WEM Procedure - Declaration of Bilateral Trades and the Capacity Credit assignment (2021 Cycle) (External Consultation) (RCM) | AEMO | 11 January 2022 8:00 AM | 10 February 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-209
212 | 4865 | WEM Procedure - Declaration of Bilateral Trades and the Capacity Credit assignment (2021 Cycle) (Publish Provisional Procedure) (RCM) | AEMO | 1 March 2022 8:00 AM | 2 March 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-210
213 | 4866 | WEM Procedure - Declaration of Bilateral Trades and the Capacity Credit assignment (2022 Cycle) (Notional WRIG date) (RCM) | AEMO | 26 May 2022 8:00 AM | 26 May 2022 8:00 AM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-211
214 | 4867 | WEM Procedure - Declaration of Bilateral Trades and the Capacity Credit assignment (2022 Cycle) (External Consultation) (RCM) | AEMO | 15 July 2022 8:00 AM | 4 August 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-212
215 | 4868 | WEM Procedure - Declaration of Bilateral Trades and the Capacity Credit assignment (2022 Cycle) (Publish Provisional Procedure) (RCM) | AEMO | 1 September 2022 8:00 AM | 2 September 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-213
216 | 4869 | WEM Procedure - RCM Constraints (External Consultation) (RCM) | AEMO | 11 January 2022 8:00 AM | 10 February 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-200
217 | 4870 | WEM Procedure - RCM Constraints (Notional WRIG date) (RCM) | AEMO | 27 January 2022 8:00 AM | 27 January 2022 8:00 AM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-199
218 | 4871 | WEM Procedure - RCM Constraints (Publish Provisional Procedure) (RCM) | AEMO | 1 March 2022 8:00 AM | 2 March 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-201
219 | 4872 | WEM Procedure - RCM Limit Advice (Transitional) (External Consultation) (RCM) | AEMO | 11 January 2022 8:00 AM | 10 February 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-203
220 | 4873 | WEM Procedure - RCM Limit Advice (Transitional) (Notional WRIG date) (RCM) | AEMO | 27 January 2022 8:00 AM | 27 January 2022 8:00 AM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-202
221 | 4874 | WEM Procedure - RCM Limit Advice (Transitional) (Publish Provisional Procedure) (RCM) | AEMO | 1 March 2022 8:00 AM | 2 March 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-204
222 | 4875 | WEM Procedure - Reserve Capacity Performance Monitoring (Notional WRIG date) (RCM) | AEMO | 23 February 2023 8:00 AM | 23 February 2023 8:00 AM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-217
223 | 4876 | WEM Procedure - Reserve Capacity Performance Monitoring (External Consultation) (RCM) | AEMO | 15 March 2023 8:00 AM | 4 April 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-218
224 | 4877 | WEM Procedure - Reserve Capacity Performance Monitoring (Publish Provisional Procedure) (RCM) | AEMO | 1 May 2023 8:00 AM | 2 May 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-219
225 | 4878 | WEM Procedure - Reserve Capacity Security Procedure (External Consultation) (RCM) | AEMO | 15 March 2023 8:00 AM | 4 April 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-227
226 | 4879 | WEM Procedure - Reserve Capacity Security Procedure (Notional WRIG date) (RCM) | AEMO | 30 March 2023 8:00 AM | 30 March 2023 8:00 AM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-226
227 | 4880 | WEM Procedure - Reserve Capacity Security Procedure (Publish Provisional Procedure) (RCM) | AEMO | 1 May 2023 8:00 AM | 2 May 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-228
228 | 4881 | WEM Procedure - Reserve Capacity Testing (Notional WRIG date) (RCM) | AEMO | 26 January 2023 8:00 AM | 26 January 2023 8:00 AM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-223
229 | 4882 | WEM Procedure - Reserve Capacity Testing (External Consultation) (RCM) | AEMO | 14 March 2023 8:00 AM | 3 April 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-224
230 | 4883 | WEM Procedure - Reserve Capacity Testing (Publish Provisional Procedure) (RCM) | AEMO | 1 May 2023 8:00 AM | 2 May 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-225
231 | 4884 | WEM Procedure - Supplementary Reserve Capacity (Date TBC) (Notional WRIG date) (RCM) | AEMO | 23 February 2023 8:00 AM | 23 February 2023 8:00 AM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-214
232 | 4885 | WEM Procedure - Supplementary Reserve Capacity (Date TBC) (External Consultation) (RCM) | AEMO | 15 March 2023 8:00 AM | 4 April 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-215
233 | 4886 | WEM Procedure - Supplementary Reserve Capacity (Date TBC) (Publish Provisional Procedure) (RCM) | AEMO | 1 May 2023 8:00 AM | 2 May 2023 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-216
234 | 4887 | WEM Procedure - Undertaking the Long Term PASA and conducting the review of the Planning Criterion (External Consultation) (RCM) | AEMO | 11 February 2022 8:00 AM | 4 March 2022 5:00 PM | WEM Procedure Milestone | TBC | RCM | Legacy Market Workstream |  | JM-198
235 | 4929 | RCM 2021 Cycle – RCM Limit Advice provided to AEMO | Western Power | 18 July 2022 8:00 AM | 18 July 2022 8:00 AM | WEM Procedure Milestone | TBC | RCM / Constraints | Legacy Market Workstream | WP provides AEMO RCM Limit Advice based on AEMO's provision of RCM Requirements | JM-056
236 | 14 | P2109 STEM Reform Phase | AEMO | 20 September 2022 8:00 AM | 1 March 2023 5:00 PM |  | Confirmed | STEM | Legacy Market Workstream
237 | 2347 | Initiation (STEM) | AEMO | 20 September 2022 8:00 AM | 15 November 2022 5:00 PM | Project establishment | TBC | STEM | Legacy Market Workstream |  | JM-142
238 | 2343 | Planning complete (STEM) | AEMO | 14 October 2022 8:00 AM | 14 October 2022 8:00 AM | Project establishment | TBC | STEM | Legacy Market Workstream |  | JM-143
239 | 2337 | Participant testing (STEM) | AEMO | 1 March 2023 8:00 AM | 1 March 2023 8:00 AM | Participant training and testing | TBC | STEM | Legacy Market Workstream |  | JM-144
240 | 2314 | Technical documentation published (STEM) | AEMO | 3 January 2023 8:00 AM | 3 January 2023 8:00 AM | Technical Information Release | TBC | STEM | Legacy Market Workstream | AEMO will provide technical and implementation details related to the specific AEMO-Participant system interface(e.g. specifications, APIs) | JM-026
241 | 315 | Registration Workstream |  | 1 July 2020 8:00 AM | 31 March 2023 5:00 PM |  |  |  | Registration
242 | 136 | P2082 GPS Reform | AEMO | 1 July 2020 8:00 AM | 30 September 2021 5:00 PM |  |  | GPS | Registration
243 | 3899 | GPS Participant testing (GPS) | AEMO | 5 July 2021 8:00 AM | 28 July 2021 5:00 PM | Technical Information Release | Complete | GPS | Registration |  | JM-028
244 | 3900 | AEMO GPS Repository Live (GPS) | AEMO | 4 August 2021 8:00 AM | 4 August 2021 8:00 AM | Technical Go-Live | Complete | GPS | Registration |  | JM-029
245 | 4913 | GPS Submission Template provided to Market Participants | Western Power | 1 December 2020 8:00 AM | 1 December 2020 8:00 AM | Business Process | Complete | GPS | Registration | Provide GPS information capture template to Market Participants | JM-047
246 | 4914 | Draft GPS Submissions Received from Market Participants | Western Power | 31 March 2021 8:00 AM | 31 March 2021 8:00 AM | Business Process | Complete | GPS | Registration | Receive draft GPS information capture template back from Market Participants. Action undertaken by Market Participants. Consult with Western Power as required. | JM-048 | JM-047
247 | 4915 | GPS Updates provided to AEMO GPS Repository | Western Power | 31 December 2022 8:00 AM | 31 December 2022 8:00 AM | Business Process | Confirmed | GPS | Registration | GPS transition finalised with Market Participants and documented in Generator Register. Timing is subject to Market Participant Extensions. | JM-049 | JM-029
248 | 4916 | WEM Procedure - Generator Performance Standards for Existing Transmission Connected Generating Systems - Consultation Start | Western Power | 11 December 2020 8:00 AM | 11 December 2020 8:00 AM | WEM Procedure Milestone | Complete | GPS | Registration | Draft procedure complete and commence 4 weeks industry consultation | JM-039
249 | 4917 | WEM Procedure - Generator Performance Standards for Existing Transmission Connected Generating Systems - Procedure Live | Western Power | 1 February 2021 8:00 AM | 1 February 2021 8:00 AM | WEM Procedure Milestone | Complete | GPS | Registration | Finalise procedure post industry consultation | JM-040 | JM-039
250 | 4918 | WEM Procedure - Generation System Model Submission and Maintenance - Consultation Start | Western Power | 11 December 2020 8:00 AM | 11 December 2020 8:00 AM | WEM Procedure Milestone | Complete | GPS | Registration | Draft procedure complete and commence 4 weeks industry consultation | JM-044
251 | 4943 | GPS guidelines (Notional WRIG) | Western Power | 26 May 2022 8:00 AM | 26 May 2022 8:00 AM | WEM Procedure Milestone | Complete | GPS | Registration | Guideline for assessment of technical standards and relevent generator modifications
252 | 4944 | GPS guidelines (Published) | Western Power | 1 July 2022 8:00 AM | 1 July 2022 8:00 AM | WEM Procedure Milestone | Complete | GPS | Registration | Guideline for assessment of technical standards and relevent generator modifications
253 | 4919 | WEM Procedure - Generation System Model Submission and Maintenance - Procedure Live | Western Power | 1 February 2021 8:00 AM | 1 February 2021 8:00 AM | WEM Procedure Milestone | Complete | GPS | Registration | Finalise procedure post industry consultation | JM-045 | JM-045
254 | 4902 | WEM Procedures (GPS) | AEMO | 1 February 2021 8:00 AM | 1 February 2021 8:00 AM | WEM Procedure Milestone | Confirmed | GPS | Registration
255 | 3846 | Last Procedure Published (GPS) | AEMO | 1 February 2021 8:00 AM | 1 February 2021 8:00 AM | WEM Procedure Milestone | Complete | GPS | Registration |  | JM-145
256 | 2 | P2107 Registration Reform | AEMO | 20 October 2021 8:00 AM | 31 March 2023 5:00 PM |  |  | Registrations | Registration
257 | 1033 | Initiation (Registrations) | AEMO | 20 October 2021 8:00 AM | 16 February 2022 5:00 PM | Project establishment | Confirmed | Registrations | Registration |  | JM-146
258 | 1029 | User interface Draft user guide released | AEMO |  |  | Technical Information Release | TBC | Registrations | Registration |  | JM-147
259 | 1040 | Registrations API Specification (if required) | AEMO |  |  | Technical Information Release | TBC | Registrations | Registration | AEMO has not yet determined whether an API will be required for the submission and querying of registration standing data. | JM-148
260 | 4901 | WEM Procedures (Registrations) | AEMO | 29 September 2022 8:00 AM | 21 December 2022 5:00 PM | WEM Procedure Milestone | TBC | Registrations | Registration
261 | 4888 | WEM Procedure - Facility registration, de-registration and transfer Procedure (Notional WRIG date) (Registrations) | AEMO | 29 September 2022 8:00 AM | 29 September 2022 8:00 AM | WEM Procedure Milestone | TBC | Registrations | Registration |  | JM-238
262 | 4889 | WEM Procedure - Facility registration, de-registration and transfer Procedure (External Consultation) (Registrations) | AEMO | 3 November 2022 8:00 AM | 23 November 2022 5:00 PM | WEM Procedure Milestone | TBC | Registrations | Registration |  | JM-239
263 | 4890 | WEM Procedure - Facility registration, de-registration and transfer Procedure (Publish Provisional Procedure) (Registrations) | AEMO | 21 December 2022 8:00 AM | 22 December 2022 5:00 PM | WEM Procedure Milestone | TBC | Registrations | Registration |  | JM-240
264 | 4891 | WEM Procedure - Rule Participant Registration and Deregistration Process (Notional WRIG date) (Registrations) | AEMO | 29 September 2022 8:00 AM | 29 September 2022 8:00 AM | WEM Procedure Milestone | TBC | Registrations | Registration |  | JM-235
265 | 4892 | WEM Procedure - Rule Participant Registration and Deregistration Process (External Consultation) (Registrations) | AEMO | 3 November 2022 8:00 AM | 23 November 2022 5:00 PM | WEM Procedure Milestone | TBC | Registrations | Registration |  | JM-236
266 | 4893 | WEM Procedure - Rule Participant Registration and Deregistration Process (Publish Provisional Procedure) (Registrations) | AEMO | 21 December 2022 8:00 AM | 22 December 2022 5:00 PM | WEM Procedure Milestone | TBC | Registrations | Registration |  | JM-237
267 | 4894 | WEM Procedure - Transitional Registration (Notional WRIG date) (Registrations) | AEMO | 29 September 2022 8:00 AM | 29 September 2022 8:00 AM | WEM Procedure Milestone | TBC | Registrations | Registration |  | JM-241
268 | 4895 | WEM Procedure - Transitional Registration (External Consultation) (Registrations) | AEMO | 4 November 2022 8:00 AM | 24 November 2022 5:00 PM | WEM Procedure Milestone | TBC | Registrations | Registration |  | JM-242
269 | 4896 | WEM Procedure - Transitional Registration (Publish Provisional Procedure) (Registrations) | AEMO | 21 December 2022 8:00 AM | 22 December 2022 5:00 PM | WEM Procedure Milestone | TBC | Registrations | Registration |  | JM-243
270 | 3778 | Control Room Transition |  | 30 June 2021 8:00 AM | 1 August 2022 5:00 PM |  |  |  | SCED
271 | 3849 | Commencement of GT transition planning | Synergy | 1 December 2021 8:00 AM | 1 December 2021 8:00 AM | Business Process | Confirmed | Control Room Transition | SCED |  | JM-080
272 | 3850 | Control room complete | Synergy | 1 September 2021 8:00 AM | 1 September 2021 8:00 AM | Technical Implementation | Confirmed | Control Room Transition | SCED |  | JM-070
273 | 3851 | Pinjar Control Network works complete | Synergy | 1 October 2021 8:00 AM | 1 October 2021 8:00 AM | Technical Implementation | Confirmed | Control Room Transition | SCED |  | JM-071
274 | 3853 | Control systems works complete | Synergy | 1 November 2021 8:00 AM | 1 November 2021 8:00 AM | Technical Implementation | Confirmed | Control Room Transition | SCED |  | JM-073
275 | 3857 | Migration planning and execution | Synergy | 2 May 2022 8:00 AM | 2 May 2022 8:00 AM | Technical Implementation | Confirmed | Control Room Transition | SCED |  | JM-077
276 | 3858 | Pinjar comms link complete | Synergy | 30 June 2021 8:00 AM | 30 June 2021 8:00 AM | Technical Implementation | Complete | Control Room Transition | SCED |  | JM-094
277 | 3859 | Kemerton comms link complete | Synergy | 30 December 2022 8:00 AM | 30 December 2022 8:00 AM | Technical Implementation | Confirmed | Control Room Transition | SCED |  | JM-095
278 | 3860 | Completion of operator recruitment Ph 1 | Synergy | 1 July 2021 8:00 AM | 1 July 2021 8:00 AM | Training | Complete | Control Room Transition | SCED |  | JM-078
279 | 3863 | Completion of operator recruitment Ph 2 | Synergy | 1 October 2021 8:00 AM | 1 October 2021 8:00 AM | Training | Confirmed | Control Room Transition | SCED |  | JM-096
280 | 4912 | Operational Control Protocols Scoping Complete | Synergy/AEMO/Western Power |  |  | Technical Implementation | TBC | Control Room Transition | SCED |  | JM-277
281 | 4942 | Synergy Control Room fully operational - 'go-live' | Synergy | 1 October 2023 8:00 AM | 1 October 2023 8:00 AM | Technical Go-Live | Confirmed | Control Room Transition | SCED |  | JM-278
282 | 4911 | Other new market readiness activities |  | 18 September 2020 8:00 AM | 31 October 2023 5:00 PM
283 | 3865 | Revised Applications and Queuing Policy (AQP) and Contribution Policy Published | Western Power | 2 August 2021 8:00 AM | 2 August 2021 8:00 AM | Business Process | Complete |  | SCED | Revised Applications and Queuing Policy, ETAC and Contributions Policy for constrained access (ETIU to consult industry and gazettal) Dependant on the approval of Access Code Tranche 2 amendments. | JM-032
284 | 3866 | Terminate GIA Related NCS | Western Power | 31 October 2023 8:00 AM | 31 October 2023 8:00 AM | Business Process | Confirmed |  | SCED | Termination of GIA related Network Control Service after new market start in conjunction with any required contract amendments for constrained access | JM-034
285 | 3876 | Constrained Access Process Applies to New Access Offers | Western Power | 18 September 2020 8:00 AM | 18 September 2020 8:00 AM | Business Process | Complete |  | SCED | The Electricity Networks Access Code Amendments (No. 2) 2020 were gazetted 18 September - no further firm (unconstrained) services for generator connections | JM-066
286 | 3852 | Site SCADA works complete | Synergy | 1 November 2021 8:00 AM | 1 November 2021 8:00 AM | Technical Implementation | Confirmed |  | SCED |  | JM-072
287 | 3854 | Western Power SCADA works complete | Synergy | 30 June 2023 8:00 AM | 30 June 2023 8:00 AM | Technical Implementation | Confirmed |  | SCED |  | JM-074
288 | 3855 | Application development complete – core trading system | Synergy | 30 December 2022 8:00 AM | 30 December 2022 8:00 AM | Technical Implementation | Confirmed |  | SCED |  | JM-075
289 | 3856 | Development complete – reconciliation and settlement | Synergy | 30 March 2023 8:00 AM | 30 March 2023 8:00 AM | Technical Implementation | Confirmed |  | SCED |  | JM-076
290 | 3861 | Completion of trader recruitment Ph1 | Synergy | 1 September 2021 8:00 AM | 1 September 2021 8:00 AM | Training | Complete |  | SCED |  | JM-079
291 | 3862 | Completion of trader recruitment Ph2 | Synergy | 30 March 2023 8:00 AM | 30 March 2023 8:00 AM | Training | Confirmed |  | SCED |  | JM-081
292 | 4941 | Generator Interim Access (GIA) service ceases and dispatched using SCED () | AEMO | 1 October 2023 8:00 AM | 1 October 2023 8:00 AM | Technical Go-Live | Confirmed |  | SCED |  | JM-033
293 | 290 | Market Trials & Support | AEMO | 1 December 2022 8:00 AM | 29 September 2023 5:00 PM |  |  |  | MKT TRIAL
294 | 3774 | Market Trial Commences (Market Trial) | AEMO | 3 March 2023 8:00 AM | 3 March 2023 8:00 AM | Significant Market Milestone | TBC | Market Trial | MKT TRIAL | Commencement of 'formal' Market Trial period where Market Participants and other parties will conduct defined end-to-end scenario based trials e.g. as opposed to purely system/user integration testing). | JM-002
295 | 291 | New Market Go-Live | AEMO | 1 October 2023 8:00 AM | 1 October 2023 8:00 AM | Significant Market Milestone | Confirmed |  |  | Date on which first interval of Security Constrained Economic Dispatch (SCED) will take place in line with commencement of relevant WEM Rule Modifications and Go Live date referenced in WEM Rule 1.20. | JM-003
296 | 4897 | WEM Procedures (Core Program) | AEMO | 29 June 2023 8:00 AM | 29 September 2023 5:00 PM | WEM Procedure Milestone | Confirmed | Core Program | Core Program
297 | 4773 | WEM Procedure - Monitoring and Reporting Protocol (Notional WRIG date) (Core Program) | AEMO | 29 June 2023 8:00 AM | 29 June 2023 8:00 AM | WEM Procedure Milestone | TBC | Core Program | Core Program |  | JM-229
298 | 4774 | WEM Procedure - Monitoring and Reporting Protocol (External Consultation) (Core Program) | AEMO | 14 August 2023 8:00 AM | 1 September 2023 5:00 PM | WEM Procedure Milestone | TBC | Core Program | Core Program |  | JM-230
299 | 4775 | WEM Procedure - Monitoring and Reporting Protocol (Publish Provisional Procedure) (Core Program) | AEMO | 29 September 2023 8:00 AM | 2 October 2023 5:00 PM | WEM Procedure Milestone | TBC | Core Program | Core Program |  | JM-231