## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Manually Scheduled | EXPLORATION TENURE APPROVALS | 418 days | 27/02/13 8:00 AM | 03/10/14 5:00 PM |  | 1 | NB: This process is used only if there is no existing tenure.
2 | Yes | Auto Scheduled | Acreage Release (PGERA67) | 182 days | 27/02/13 8:00 AM | 07/11/13 5:00 PM |  | 2 | http://www.dmp.wa.gov.au/documents/PD-PTLA-POL-102D.pdf
3 | Yes | Auto Scheduled | Pre-gazette development | 60 days | 27/02/13 8:00 AM | 21/05/13 5:00 PM |  | 3
4 | Yes | Auto Scheduled | Determine area, prepare maps of lease showing conservation estates, reserves, NT | 4 wks | 27/02/13 8:00 AM | 26/03/13 5:00 PM |  | 4
5 | Yes | Auto Scheduled | Consultation with stakeholders | 4 wks | 27/03/13 8:00 AM | 23/04/13 5:00 PM | 4 | 4
6 | Yes | Auto Scheduled | Preparation of Gazette notice | 4 wks | 24/04/13 8:00 AM | 21/05/13 5:00 PM | 5 | 4
7 | Yes | Auto Scheduled | Publish Gazette Notice (s30) | 1 day | 22/05/13 8:00 AM | 22/05/13 5:00 PM | 3 | 3
8 | Yes | Auto Scheduled | Prepare bid | 6 mons | 23/05/13 8:00 AM | 06/11/13 5:00 PM | 7 | 3
9 | Yes | Auto Scheduled | Lodge bid with DMP (s31) | 1 day | 07/11/13 8:00 AM | 07/11/13 5:00 PM | 8 | 3
10 | Yes | Auto Scheduled | Award of Exploration Permit (s38) | 223 days | 08/11/13 8:00 AM | 16/09/14 5:00 PM | 9 | 2 | http://www.dmp.wa.gov.au/1691.aspx
11 | Yes | Auto Scheduled | assessment of bids/applications | 3 mons | 08/11/13 8:00 AM | 30/01/14 5:00 PM | 9 | 3 | http://www.dmp.wa.gov.au/documents/EXPLORATION_PERMIT_APPLICATION_PROCESS_FLOWCHART_(WEB).pdf
12 | Yes | Auto Scheduled | bid assessment report | 4 wks | 31/01/14 8:00 AM | 27/02/14 5:00 PM | 11 | 3
13 | Yes | Auto Scheduled | response to preferred applicant letter | 14 days | 28/02/14 8:00 AM | 19/03/14 5:00 PM | 12 | 3
14 | Yes | Auto Scheduled | Native Title Agreements | 143 days | 28/02/14 8:00 AM | 16/09/14 5:00 PM |  | 3
15 | Yes | Auto Scheduled | Advertised (s29 NTA) | 120 days | 20/03/14 8:00 AM | 03/09/14 5:00 PM | 13 | 4
16 | Yes | Auto Scheduled | Administration | 60 days | 20/03/14 8:00 AM | 11/06/14 5:00 PM | 15SS,17SS | 4
17 | Yes | Auto Scheduled | "Right to Negotiate" | 125 days | 28/02/14 8:00 AM | 21/08/14 5:00 PM | 13SS | 4 | this is an estimate only - times will vary depending on nature of agreements
18 | Yes | Auto Scheduled | State Deed (s31) | 18 days | 22/08/14 8:00 AM | 16/09/14 5:00 PM | 17 | 4 | this is an estimate only - times vary depending on signatories
19 | Yes | Auto Scheduled | Permit grant | 31 days | 22/08/14 8:00 AM | 03/10/14 5:00 PM |  | 2
20 | Yes | Auto Scheduled | offer of grant | 30 days | 22/08/14 8:00 AM | 02/10/14 5:00 PM | 13,17 | 3
21 | Yes | Auto Scheduled | award permit | 1 day | 03/10/14 8:00 AM | 03/10/14 5:00 PM | 20 | 3
22 | Yes | Auto Scheduled | EXPLORATION | 1030 days | 03/10/14 5:00 PM | 14/09/18 5:00 PM | 21 | 1 | *NB: projects may be referred at exploration through State or Federal environmental approval process
23 | Yes | Auto Scheduled | Activity Approval (Drilling) | 90 days | 03/10/14 5:00 PM | 06/02/15 5:00 PM |  | 2 | Required for each activity, batch approvals may be sought
24 | Yes | Auto Scheduled | Submit application | 0 days | 03/10/14 5:00 PM | 03/10/14 5:00 PM | 21 | 3
25 | Yes | Auto Scheduled | Assess Technical Report | 30 days | 06/10/14 8:00 AM | 14/11/14 5:00 PM | 24SS | 3
26 | Yes | Auto Scheduled | Assess Well Operation Management Plan (WOMP) and Drill Program | 30 days | 06/10/14 8:00 AM | 14/11/14 5:00 PM | 24SS | 3
27 | Yes | Auto Scheduled | Assess Safety Management System | 20 days | 06/10/14 8:00 AM | 31/10/14 5:00 PM | 24SS | 3
28 | Yes | Auto Scheduled | Heritage Clearance | 30 days | 06/10/14 8:00 AM | 14/11/14 5:00 PM | 21SS | 3
29 | Yes | Auto Scheduled | Access and Compensation Agreements | 90 days | 06/10/14 8:00 AM | 06/02/15 5:00 PM | 21SS | 3 | this is an estimate only - times will vary depending on nature of agreements
30 | Yes | Auto Scheduled | Environment Plans | 30 days | 06/10/14 8:00 AM | 14/11/14 5:00 PM | 24SS | 3 | may be referred under EPBC Act for Federal government assessment
31 | Yes | Auto Scheduled | Data submission | 1 day | 17/11/14 8:00 AM | 17/11/14 5:00 PM | 30 | 3 | proponent must submit resource data to DMP throughout activity
32 | Yes | Manually Scheduled | EXPLORATION ACTIVITY (seismic, drilling, interpreting data) | 12 mons | 17/11/14 8:00 AM | 16/10/15 5:00 PM | 30 | 2
33 | Yes | Auto Scheduled | Licence to construct a well (s26d RIWA) | 30 days | 06/10/14 8:00 AM | 14/11/14 5:00 PM | 21 | 2 | only required if company needs to drill water well for water supply
34 | Yes | Auto Scheduled | Licence to Take water (s5c RIWA) | 60 days | 06/10/14 8:00 AM | 26/12/14 5:00 PM | 21 | 2 | only if new water well or table
35 | Yes | Auto Scheduled | Native Vegetation Clearing Approvals (schedule 6) (EP Act) | 60 days | 06/10/14 8:00 AM | 26/12/14 5:00 PM | 21 | 2
36 | Yes | Auto Scheduled | Activity Approval (Fraccing) | 30 days | 16/10/15 5:00 PM | 27/11/15 5:00 PM | 32 | 2 | Required for each activity, batch approvals may be sought
37 | Yes | Auto Scheduled | Submit application | 0 days | 16/10/15 5:00 PM | 16/10/15 5:00 PM | 32 | 3
38 | Yes | Auto Scheduled | Assess Technical Report | 30 days | 19/10/15 8:00 AM | 27/11/15 5:00 PM | 37SS | 3
39 | Yes | Auto Scheduled | Assess Well Operation Management Plan (WOMP) and Drill Program | 30 days | 19/10/15 8:00 AM | 27/11/15 5:00 PM | 37SS | 3
40 | Yes | Auto Scheduled | Assess Safety Management System | 20 days | 19/10/15 8:00 AM | 13/11/15 5:00 PM | 37SS | 3
41 | Yes | Auto Scheduled | Environment Plans | 30 days | 19/10/15 8:00 AM | 27/11/15 5:00 PM | 37SS | 3 | may be referred under EPBC Act for Federal government assessment
42 | Yes | Auto Scheduled | Data submission | 1 day | 19/10/15 8:00 AM | 19/10/15 5:00 PM |  | 3 | proponent must submit resource data to DMP throughout activity
43 | Yes | Auto Scheduled | Activity Approval (Completion) | 30 days | 03/10/14 5:00 PM | 14/11/14 5:00 PM |  | 2 | Required for each activity, batch approvals may be sought
44 | Yes | Auto Scheduled | Submit application | 0 days | 03/10/14 5:00 PM | 03/10/14 5:00 PM |  | 3
45 | Yes | Auto Scheduled | Assess Technical Report | 30 days | 06/10/14 8:00 AM | 14/11/14 5:00 PM | 44SS | 3
46 | Yes | Auto Scheduled | Assess Well Operation Management Plan (WOMP) and Drill Program | 30 days | 06/10/14 8:00 AM | 14/11/14 5:00 PM | 44SS | 3
47 | Yes | Auto Scheduled | Assess Safety Management System | 20 days | 06/10/14 8:00 AM | 31/10/14 5:00 PM | 44SS | 3
48 | Yes | Auto Scheduled | Environment Plans | 30 days | 06/10/14 8:00 AM | 14/11/14 5:00 PM | 44SS | 3 | may be referred under EPBC Act for Federal government assessment
49 | Yes | Auto Scheduled | Data submission | 1 day | 06/10/14 8:00 AM | 06/10/14 5:00 PM |  | 3 | proponent must submit resource data to DMP throughout activity
50 | Yes | Manually Scheduled | EXPLORATION ACTIVITY | 1000 days | 17/11/14 8:00 AM | 14/09/18 5:00 PM | 30,1 | 2
51 | Yes | Auto Scheduled | Notice of Discovery | 1 day | 17/11/14 8:00 AM | 17/11/14 5:00 PM |  | 3
52 | Yes | Auto Scheduled | Extended Production Test (EPT) | 212 days | 06/10/14 8:00 AM | 28/07/15 5:00 PM |  | 2
53 | Yes | Auto Scheduled | Submit application | 0 days | 17/11/14 5:00 PM | 17/11/14 5:00 PM | 51 | 3
54 | Yes | Auto Scheduled | Assess Technical Report | 30 days | 18/11/14 8:00 AM | 29/12/14 5:00 PM | 53SS | 3
55 | Yes | Auto Scheduled | Assess Well Operation Management Plan (WOMP) and Drill Program | 30 days | 18/11/14 8:00 AM | 29/12/14 5:00 PM | 53SS | 3
56 | Yes | Auto Scheduled | Assess Safety Management System | 20 days | 18/11/14 8:00 AM | 15/12/14 5:00 PM | 53SS | 3
57 | Yes | Auto Scheduled | Environment Plans | 30 days | 18/11/14 8:00 AM | 29/12/14 5:00 PM | 53SS | 3 | may be referred under EPBC Act for Federal government assessment
58 | Yes | Auto Scheduled | Data submission | 1 day | 06/10/14 8:00 AM | 06/10/14 5:00 PM |  | 3 | proponent must submit resource data to DMP throughout activity
59 | Yes | Auto Scheduled | Declaration of Location | 30 days | 18/11/14 8:00 AM | 29/12/14 5:00 PM |  | 3 | If not proceeding to production approvals, then retention approvals must be sought)
60 | Yes | Auto Scheduled | application and technical assessment | 30 days | 18/11/14 8:00 AM | 29/12/14 5:00 PM | 51 | 4 | valid for up to 4 years (2 years plus 2 year renewal)
61 | Yes | Auto Scheduled | Proof of Concept (Reservoir) | 212 days | 06/10/14 8:00 AM | 28/07/15 5:00 PM |  | 3 | eg for stimulation activities not previously applied for
62 | Yes | Auto Scheduled | Extended Production Testing | 6 mons | 30/12/14 8:00 AM | 15/06/15 5:00 PM | 60 | 4 | renewable, volume limits apply
63 | Yes | Auto Scheduled | Submit application | 1 day | 16/06/15 8:00 AM | 16/06/15 5:00 PM | 62 | 4
64 | Yes | Auto Scheduled | Preliminary Field Development Plan and Schedule | 30 days | 17/06/15 8:00 AM | 28/07/15 5:00 PM | 63 | 4
65 | Yes | Auto Scheduled | Technical Report | 30 days | 17/06/15 8:00 AM | 28/07/15 5:00 PM | 63 | 4
66 | Yes | Auto Scheduled | WOMP & Drill Program | 30 days | 17/06/15 8:00 AM | 28/07/15 5:00 PM | 63 | 4
67 | Yes | Auto Scheduled | Environment Plans | 30 days | 17/06/15 8:00 AM | 28/07/15 5:00 PM | 63 | 4 | may be referred under EPBC Act for Federal government assessment
68 | Yes | Auto Scheduled | Safety Management System(re-entry) | 20 days | 17/06/15 8:00 AM | 14/07/15 5:00 PM | 63 | 4
69 | Yes | Auto Scheduled | Data submission | 1 day | 06/10/14 8:00 AM | 06/10/14 5:00 PM |  | 4 | proponent must submit resource data to DMP throughout activity
70 | Yes | Auto Scheduled | PILOT APPROVALS | 261 days | 30/12/14 8:00 AM | 29/12/15 5:00 PM | 60 | 1 | *NB: projects may be referred at pilot through State or Federal environmental approval process. See line 84 and 107
71 | Yes | Auto Scheduled | Activity Approval (Drilling) | 90 days | 14/07/15 5:00 PM | 17/11/15 5:00 PM | 68 | 2 | Required for each activity, batch approvals may be sought
72 | Yes | Auto Scheduled | Submit application | 0 days | 14/07/15 5:00 PM | 14/07/15 5:00 PM | 68 | 3
73 | Yes | Auto Scheduled | Assess Technical Report | 30 days | 15/07/15 8:00 AM | 25/08/15 5:00 PM | 72SS | 3
74 | Yes | Auto Scheduled | Assess Well Operation Management Plan (WOMP) and Drill Program | 30 days | 15/07/15 8:00 AM | 25/08/15 5:00 PM | 72SS | 3
75 | Yes | Auto Scheduled | Assess Safety Management System | 20 days | 15/07/15 8:00 AM | 11/08/15 5:00 PM | 72SS | 3
76 | Yes | Auto Scheduled | Access and Compensation Agreements | 90 days | 15/07/15 8:00 AM | 17/11/15 5:00 PM |  | 3 | this is an estimate only - times will vary depending on nature of agreements
77 | Yes | Auto Scheduled | Environment Plans | 30 days | 15/07/15 8:00 AM | 25/08/15 5:00 PM | 72SS | 3 | may be referred under EPBC Act for Federal government assessment
78 | Yes | Auto Scheduled | Data submission | 1 day | 15/07/15 8:00 AM | 15/07/15 5:00 PM |  | 3 | proponent must submit resource data to DMP throughout activity
79 | Yes | Auto Scheduled | Activity Approval (Fraccing) | 90 days | 25/08/15 5:00 PM | 29/12/15 5:00 PM | 77 | 2 | Required for each activity, batch approvals may be sought
80 | Yes | Auto Scheduled | Submit application | 0 days | 25/08/15 5:00 PM | 25/08/15 5:00 PM | 77 | 3
81 | Yes | Auto Scheduled | Assess Technical Report | 30 days | 26/08/15 8:00 AM | 06/10/15 5:00 PM | 80SS | 3
82 | Yes | Auto Scheduled | Assess Well Operation Management Plan (WOMP) and Drill Program | 30 days | 26/08/15 8:00 AM | 06/10/15 5:00 PM | 80SS | 3
83 | Yes | Auto Scheduled | Assess Safety Management System | 20 days | 26/08/15 8:00 AM | 22/09/15 5:00 PM | 80SS | 3
84 | Yes | Auto Scheduled | Access and Compensation Agreements | 90 days | 26/08/15 8:00 AM | 29/12/15 5:00 PM |  | 3 | this is an estimate only - times will vary depending on nature of agreements
85 | Yes | Auto Scheduled | Environment Plans | 30 days | 26/08/15 8:00 AM | 06/10/15 5:00 PM | 80SS | 3 | may be referred under EPBC Act for Federal government assessment
86 | Yes | Auto Scheduled | Data submission | 1 day | 26/08/15 8:00 AM | 26/08/15 5:00 PM |  | 3 | proponent must submit resource data to DMP throughout activity
87 | Yes | Auto Scheduled | Pipeline Licence (Petroleum Pipelines Act 1969) (s6) | 91 days | 30/12/14 8:00 AM | 05/05/15 5:00 PM |  | 2 | (volume dependent)
88 | Yes | Auto Scheduled | Submit application | 1 day | 30/12/14 8:00 AM | 30/12/14 5:00 PM | 60 | 3
89 | Yes | Auto Scheduled | advertised (ss8(4)) | 30 days | 30/12/14 8:00 AM | 09/02/15 5:00 PM | 88SS | 3
90 | Yes | Auto Scheduled | notification (ss8(3)(b)) | 28 days | 30/12/14 8:00 AM | 05/02/15 5:00 PM | 88SS | 3 | notification to landholders
91 | Yes | Auto Scheduled | Acquire land tenure (Land Administration Act) | 30 days | 30/12/14 8:00 AM | 09/02/15 5:00 PM | 88SS | 3 | this is an estimate only - times will vary depending on nature of agreements, only need to be in place by construction
92 | Yes | Auto Scheduled | grant | 30 days | 31/12/14 8:00 AM | 10/02/15 5:00 PM | 88 | 3 | DMP policy position - condition that construction must begin within two years
93 | Yes | Auto Scheduled | approval to construct | 30 days | 11/02/15 8:00 AM | 24/03/15 5:00 PM |  | 3
94 | Yes | Auto Scheduled | Safety Management Case | 30 days | 11/02/15 8:00 AM | 24/03/15 5:00 PM | 92 | 4
95 | Yes | Auto Scheduled | Environment Plans | 30 days | 11/02/15 8:00 AM | 24/03/15 5:00 PM | 92 | 4 | may be referred under EPBC Act for Federal government assessment
96 | Yes | Auto Scheduled | Native Vegetation Clearing Approvals (schedule 6) (EP Act) | 30 days | 11/02/15 8:00 AM | 24/03/15 5:00 PM | 92 | 4
97 | Yes | Auto Scheduled | Heritage Clearance | 30 days | 11/02/15 8:00 AM | 24/03/15 5:00 PM | 92 | 4 | estimate only
98 | Yes | Auto Scheduled | Approval to operate (s36) | 30 days | 25/03/15 8:00 AM | 05/05/15 5:00 PM |  | 3
99 | Yes | Auto Scheduled | Safety Management Case | 30 days | 25/03/15 8:00 AM | 05/05/15 5:00 PM | 93 | 4
100 | Yes | Auto Scheduled | Environment Plans | 30 days | 25/03/15 8:00 AM | 05/05/15 5:00 PM | 93 | 4 | may be referred under EPBC Act for Federal government assessment
101 | Yes | Auto Scheduled | PILOT ACTIVITY | 730 days | 30/12/15 8:00 AM | 16/10/18 5:00 PM | 100,70 | 1
102 | Yes | Auto Scheduled | PRODUCTION APPROVALS | 832 days | 30/12/14 8:00 AM | 07/03/18 5:00 PM | 60 | 1
103 | Yes | Auto Scheduled | Production Licence (s62) | 743 days | 30/12/14 8:00 AM | 02/11/17 5:00 PM | 60 | 2
104 | Yes | Auto Scheduled | Application Submitted | 1 day | 30/12/14 8:00 AM | 30/12/14 5:00 PM | 60 | 3
105 | Yes | Auto Scheduled | Assessment of application | 30 days | 31/12/14 8:00 AM | 10/02/15 5:00 PM | 104 | 3 | http://www.dmp.wa.gov.au/documents/EXPLORATION_PERMIT_APPLICATION_PROCESS_FLOWCHART_(WEB).pdf
106 | Yes | Auto Scheduled | Final Field Development Plan and Schedule | 30 days | 11/02/15 8:00 AM | 24/03/15 5:00 PM | 105 | 3 | estimate only, timelines depend on quality of preliminary field development proposal
107 | Yes | Auto Scheduled | Determine and approve royalty regime | 30 days | 11/02/15 8:00 AM | 24/03/15 5:00 PM | 105 | 3
108 | Yes | Auto Scheduled | Native Title Agreements | 185 days | 31/12/14 8:00 AM | 15/09/15 5:00 PM |  | 3
109 | Yes | Auto Scheduled | Advertised (s29 NTA) | 120 days | 31/12/14 8:00 AM | 05/05/15 5:00 PM | 104 | 4
110 | Yes | Auto Scheduled | Administration | 60 days | 24/06/15 8:00 AM | 15/09/15 5:00 PM | 109,111 | 4
111 | Yes | Auto Scheduled | "Right to Negotiate" | 125 days | 31/12/14 8:00 AM | 23/06/15 5:00 PM | 109SS | 4
112 | Yes | Auto Scheduled | State Deed (s31) | 18 days | 24/06/15 8:00 AM | 17/07/15 5:00 PM | 109,111 | 4
113 | Yes | Auto Scheduled | Grant Production Licence | 91 days | 29/06/17 8:00 AM | 02/11/17 5:00 PM | 151 | 3
114 | Yes | Auto Scheduled | Offer of grant | 30 days | 29/06/17 8:00 AM | 09/08/17 5:00 PM | 151 | 4
115 | Yes | Auto Scheduled | Consideration of offer | 3 mons | 10/08/17 8:00 AM | 01/11/17 5:00 PM | 114 | 4
116 | Yes | Auto Scheduled | Award of Licence | 1 day | 02/11/17 8:00 AM | 02/11/17 5:00 PM | 115 | 4
117 | Yes | Auto Scheduled | Production Facility Approval | 60 days | 29/06/17 8:00 AM | 20/09/17 5:00 PM | 151 | 2
118 | Yes | Auto Scheduled | approval to construct | 30 days | 29/06/17 8:00 AM | 09/08/17 5:00 PM | 151 | 3
119 | Yes | Auto Scheduled | Safety Management Case | 30 days | 29/06/17 8:00 AM | 09/08/17 5:00 PM |  | 4
120 | Yes | Auto Scheduled | Environment Plans | 30 days | 29/06/17 8:00 AM | 09/08/17 5:00 PM |  | 4
121 | Yes | Auto Scheduled | Native Vegetation Clearing Approvals (schedule 6) (EP Act) | 30 days | 29/06/17 8:00 AM | 09/08/17 5:00 PM |  | 4
122 | Yes | Auto Scheduled | Heritage Clearance | 30 days | 29/06/17 8:00 AM | 09/08/17 5:00 PM |  | 4 | estimate only
123 | Yes | Auto Scheduled | Approval to operate (s36) | 30 days | 10/08/17 8:00 AM | 20/09/17 5:00 PM | 151 | 3
124 | Yes | Auto Scheduled | Safety Management Case | 30 days | 10/08/17 8:00 AM | 20/09/17 5:00 PM | 118 | 4
125 | Yes | Auto Scheduled | Environment Plans | 30 days | 10/08/17 8:00 AM | 20/09/17 5:00 PM | 118 | 4
126 | Yes | Auto Scheduled | State Environmental Assessment (Pt 4 EP Act) | 643 days | 30/12/14 8:00 AM | 15/06/17 5:00 PM |  | 2 | NB. Projects may be referred from exploration through to development
127 | Yes | Auto Scheduled | EP Act Referral (s38 EP Act)/Public comment period | 7 days | 30/12/14 8:00 AM | 07/01/15 5:00 PM |  | 3
128 | Yes | Auto Scheduled | EPA consideration/Advice to proponent on whether to Assess and level of assessment | 28 days | 08/01/15 8:00 AM | 16/02/15 5:00 PM | 127 | 3
129 | Yes | Auto Scheduled | Proponent prepares ESD/EPA receives 1st draft ESD | 14 days | 17/02/15 8:00 AM | 06/03/15 5:00 PM | 128 | 3 | if EPA prepares ESD, allow 6 weeks for consultation with other agencies
130 | Yes | Auto Scheduled | OEPA comments on 1st draft ESD | 35 days | 09/03/15 8:00 AM | 24/04/15 5:00 PM | 129 | 3 | if EPA prepares ESD, this step is removed
131 | Yes | Auto Scheduled | Proponents prepares revised ESD | 21 days | 27/04/15 8:00 AM | 25/05/15 5:00 PM | 130 | 3
132 | Yes | Auto Scheduled | EPA authorises release of ESD for Public Review | 14 days | 26/05/15 8:00 AM | 12/06/15 5:00 PM | 131 | 3
133 | Yes | Auto Scheduled | ESD Public Review | 14 days | 15/06/15 8:00 AM | 02/07/15 5:00 PM | 132 | 3
134 | Yes | Auto Scheduled | Summary of submissions provided to proponent | 14 days | 03/07/15 8:00 AM | 22/07/15 5:00 PM | 133 | 3
135 | Yes | Auto Scheduled | Proponent response to submissions and revision of ESD | 21 days | 23/07/15 8:00 AM | 20/08/15 5:00 PM | 134 | 3
136 | Yes | Auto Scheduled | ESD Approval | 35 days | 21/08/15 8:00 AM | 08/10/15 5:00 PM | 135 | 3
137 | Yes | Auto Scheduled | Proponent prepares draft ERMP/EPA receives 1st draft ERMP | 90 days | 09/10/15 8:00 AM | 11/02/16 5:00 PM | 136 | 3 | this is a very conservative estimate. More likely 12 months
138 | Yes | Auto Scheduled | OEPA provides comments on ERMP document | 42 days | 12/02/16 8:00 AM | 11/04/16 5:00 PM | 137 | 3
139 | Yes | Auto Scheduled | Proponent revised ERMP document | 42 days | 12/04/16 8:00 AM | 08/06/16 5:00 PM | 138 | 3 | very conservative
140 | Yes | Auto Scheduled | EPA authorises release of ERMP for public review | 14 days | 09/06/16 8:00 AM | 28/06/16 5:00 PM | 139 | 3
141 | Yes | Auto Scheduled | Public Review period for ERMP document | 70 days | 29/06/16 8:00 AM | 04/10/16 5:00 PM | 140 | 3 | can be up to 12 weeks
142 | Yes | Auto Scheduled | OEPA provides summary of submissions to proponent | 21 days | 05/10/16 8:00 AM | 02/11/16 5:00 PM | 141 | 3
143 | Yes | Auto Scheduled | Proponent prepares submission summary and response | 42 days | 03/11/16 8:00 AM | 30/12/16 5:00 PM | 142 | 3
144 | Yes | Auto Scheduled | OEPA reviews response to submissions | 49 days | 02/01/17 8:00 AM | 09/03/17 5:00 PM | 143 | 3
145 | Yes | Auto Scheduled | EPA consults with proponent and key agencies on condistions | 14 days | 10/03/17 8:00 AM | 29/03/17 5:00 PM | 144 | 3
146 | Yes | Auto Scheduled | EPA report and recommendations prepared/EPA report published | 35 days | 30/03/17 8:00 AM | 17/05/17 5:00 PM | 145 | 3
147 | Yes | Auto Scheduled | Appeal period to the Minister on EPA report | 21 days | 18/05/17 8:00 AM | 15/06/17 5:00 PM | 146 | 3
148 | Yes | Auto Scheduled | Minister considers EPA report/Minister makes decision | 14 days | 18/05/17 8:00 AM | 06/06/17 5:00 PM | 146 | 3
149 | Yes | Auto Scheduled | Comonwealth EPBC Act Referrals | 645 days | 08/01/15 8:00 AM | 28/06/17 5:00 PM |  | 2 | NB. Projects may be referred from exploration through to development
150 | Yes | Auto Scheduled | EPBC Act Referral | 20 days | 08/01/15 8:00 AM | 04/02/15 5:00 PM | 127 | 3
151 | Yes | Auto Scheduled | Minister considers EPA report, 'sign off' | 30 days | 18/05/17 8:00 AM | 28/06/17 5:00 PM | 150,146 | 3
152 | Yes | Auto Scheduled | State Works Approval & Licensing (Pt 5 EP Act) | 60 days | 02/11/17 8:00 AM | 24/01/18 5:00 PM |  | 2
153 | Yes | Auto Scheduled | Advertised | 21 days | 02/11/17 8:00 AM | 30/11/17 5:00 PM | 154SS | 3 | DEC reuires proponents to undertake scoping meeting
154 | Yes | Auto Scheduled | Works (s52/53 EP Act) - Application/Assessment/Approval | 60 days | 02/11/17 8:00 AM | 24/01/18 5:00 PM | 115 | 3
155 | Yes | Auto Scheduled | License to discharge etc (s56 EP Act) - Approval/Assessment/Licence Issued | 60 days | 02/11/17 8:00 AM | 24/01/18 5:00 PM | 154SS | 3
156 | Yes | Auto Scheduled | Registration of Prescribed Premises (r5A EPR) - Application/Assessment/Approval | 20 days | 02/11/17 8:00 AM | 29/11/17 5:00 PM | 153SS | 3
157 | Yes | Auto Scheduled | Application for Production Well(s) | 90 days | 01/11/17 5:00 PM | 07/03/18 5:00 PM | 115 | 2 | batch approvals may be sought. During life of field approvals are required for any new well & well intervention
158 | Yes | Auto Scheduled | Submit application | 0 days | 01/11/17 5:00 PM | 01/11/17 5:00 PM | 115 | 3
159 | Yes | Auto Scheduled | Assess Technical Report | 30 days | 02/11/17 8:00 AM | 13/12/17 5:00 PM | 158SS | 3
160 | Yes | Auto Scheduled | Assess Well Operation Management Plan (WOMP) Drill Program, Well Intervention and Well Abandonment plan | 30 days | 02/11/17 8:00 AM | 13/12/17 5:00 PM | 158SS | 3
161 | Yes | Auto Scheduled | Assess Safety Management System | 20 days | 02/11/17 8:00 AM | 29/11/17 5:00 PM | 158SS | 3
162 | Yes | Auto Scheduled | Heritage Clearance | 30 days | 02/11/17 8:00 AM | 13/12/17 5:00 PM | 158SS | 3
163 | Yes | Auto Scheduled | Access and Compensation Agreements | 90 days | 02/11/17 8:00 AM | 07/03/18 5:00 PM | 158SS | 3 | this is an estimate only - times will vary depending on nature of agreements
164 | Yes | Auto Scheduled | Environment Plans | 30 edays | 01/11/17 5:00 PM | 01/12/17 5:00 PM | 158SS | 3
165 | Yes | Auto Scheduled | Data submission | 1 day | 02/11/17 8:00 AM | 02/11/17 5:00 PM |  | 3 | proponent must submit resource data to DMP throughout activity
166 | Yes | Auto Scheduled | PRODUCTION ACTIVITY | 4967 days | 07/03/18 5:00 PM | 23/03/37 8:00 AM | 102 | 1 | this is just an estimate, some wells may go for as long as 40 years
167 | Yes | Auto Scheduled | Monthly Production Reports | 4952 days | 08/03/18 8:00 AM | 27/02/37 5:00 PM | 164 | 2
168 | Yes | Auto Scheduled | Monthly Production Reports 1 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
169 | Yes | Auto Scheduled | Monthly Production Reports 2 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
170 | Yes | Auto Scheduled | Monthly Production Reports 3 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
171 | Yes | Auto Scheduled | Monthly Production Reports 4 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
172 | Yes | Auto Scheduled | Monthly Production Reports 5 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
173 | Yes | Auto Scheduled | Monthly Production Reports 6 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
174 | Yes | Auto Scheduled | Monthly Production Reports 7 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
175 | Yes | Auto Scheduled | Monthly Production Reports 8 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
176 | Yes | Auto Scheduled | Monthly Production Reports 9 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
177 | Yes | Auto Scheduled | Monthly Production Reports 10 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
178 | Yes | Auto Scheduled | Monthly Production Reports 11 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
179 | Yes | Auto Scheduled | Monthly Production Reports 12 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
180 | Yes | Auto Scheduled | Monthly Production Reports 13 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
181 | Yes | Auto Scheduled | Monthly Production Reports 14 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
182 | Yes | Auto Scheduled | Monthly Production Reports 15 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
183 | Yes | Auto Scheduled | Monthly Production Reports 16 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
184 | Yes | Auto Scheduled | Monthly Production Reports 17 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
185 | Yes | Auto Scheduled | Monthly Production Reports 18 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
186 | Yes | Auto Scheduled | Monthly Production Reports 19 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
187 | Yes | Auto Scheduled | Monthly Production Reports 20 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
188 | Yes | Auto Scheduled | Monthly Production Reports 21 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
189 | Yes | Auto Scheduled | Monthly Production Reports 22 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
190 | Yes | Auto Scheduled | Monthly Production Reports 23 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
191 | Yes | Auto Scheduled | Monthly Production Reports 24 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
192 | Yes | Auto Scheduled | Monthly Production Reports 25 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
193 | Yes | Auto Scheduled | Monthly Production Reports 26 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
194 | Yes | Auto Scheduled | Monthly Production Reports 27 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
195 | Yes | Auto Scheduled | Monthly Production Reports 28 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
196 | Yes | Auto Scheduled | Monthly Production Reports 29 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
197 | Yes | Auto Scheduled | Monthly Production Reports 30 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
198 | Yes | Auto Scheduled | Monthly Production Reports 31 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
199 | Yes | Auto Scheduled | Monthly Production Reports 32 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
200 | Yes | Auto Scheduled | Monthly Production Reports 33 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
201 | Yes | Auto Scheduled | Monthly Production Reports 34 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
202 | Yes | Auto Scheduled | Monthly Production Reports 35 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
203 | Yes | Auto Scheduled | Monthly Production Reports 36 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
204 | Yes | Auto Scheduled | Monthly Production Reports 37 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
205 | Yes | Auto Scheduled | Monthly Production Reports 38 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
206 | Yes | Auto Scheduled | Monthly Production Reports 39 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
207 | Yes | Auto Scheduled | Monthly Production Reports 40 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
208 | Yes | Auto Scheduled | Monthly Production Reports 41 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
209 | Yes | Auto Scheduled | Monthly Production Reports 42 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
210 | Yes | Auto Scheduled | Monthly Production Reports 43 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
211 | Yes | Auto Scheduled | Monthly Production Reports 44 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
212 | Yes | Auto Scheduled | Monthly Production Reports 45 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
213 | Yes | Auto Scheduled | Monthly Production Reports 46 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
214 | Yes | Auto Scheduled | Monthly Production Reports 47 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
215 | Yes | Auto Scheduled | Monthly Production Reports 48 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
216 | Yes | Auto Scheduled | Monthly Production Reports 49 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
217 | Yes | Auto Scheduled | Monthly Production Reports 50 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
218 | Yes | Auto Scheduled | Monthly Production Reports 51 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
219 | Yes | Auto Scheduled | Monthly Production Reports 52 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
220 | Yes | Auto Scheduled | Monthly Production Reports 53 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
221 | Yes | Auto Scheduled | Monthly Production Reports 54 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
222 | Yes | Auto Scheduled | Monthly Production Reports 55 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
223 | Yes | Auto Scheduled | Monthly Production Reports 56 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
224 | Yes | Auto Scheduled | Monthly Production Reports 57 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
225 | Yes | Auto Scheduled | Monthly Production Reports 58 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
226 | Yes | Auto Scheduled | Monthly Production Reports 59 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
227 | Yes | Auto Scheduled | Monthly Production Reports 60 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
228 | Yes | Auto Scheduled | Monthly Production Reports 61 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
229 | Yes | Auto Scheduled | Monthly Production Reports 62 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
230 | Yes | Auto Scheduled | Monthly Production Reports 63 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
231 | Yes | Auto Scheduled | Monthly Production Reports 64 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
232 | Yes | Auto Scheduled | Monthly Production Reports 65 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
233 | Yes | Auto Scheduled | Monthly Production Reports 66 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
234 | Yes | Auto Scheduled | Monthly Production Reports 67 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
235 | Yes | Auto Scheduled | Monthly Production Reports 68 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
236 | Yes | Auto Scheduled | Monthly Production Reports 69 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
237 | Yes | Auto Scheduled | Monthly Production Reports 70 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
238 | Yes | Auto Scheduled | Monthly Production Reports 71 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
239 | Yes | Auto Scheduled | Monthly Production Reports 72 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
240 | Yes | Auto Scheduled | Monthly Production Reports 73 | 1 day | 08/03/18 8:00 AM | 08/03/18 5:00 PM |  | 3
241 | Yes | Auto Scheduled | Monthly Production Reports 74 | 1 day | 27/03/18 8:00 AM | 27/03/18 5:00 PM |  | 3
242 | Yes | Auto Scheduled | Monthly Production Reports 75 | 1 day | 27/04/18 8:00 AM | 27/04/18 5:00 PM |  | 3
243 | Yes | Auto Scheduled | Monthly Production Reports 76 | 1 day | 28/05/18 8:00 AM | 28/05/18 5:00 PM |  | 3
244 | Yes | Auto Scheduled | Monthly Production Reports 77 | 1 day | 27/06/18 8:00 AM | 27/06/18 5:00 PM |  | 3
245 | Yes | Auto Scheduled | Monthly Production Reports 78 | 1 day | 27/07/18 8:00 AM | 27/07/18 5:00 PM |  | 3
246 | Yes | Auto Scheduled | Monthly Production Reports 79 | 1 day | 27/08/18 8:00 AM | 27/08/18 5:00 PM |  | 3
247 | Yes | Auto Scheduled | Monthly Production Reports 80 | 1 day | 27/09/18 8:00 AM | 27/09/18 5:00 PM |  | 3
248 | Yes | Auto Scheduled | Monthly Production Reports 81 | 1 day | 29/10/18 8:00 AM | 29/10/18 5:00 PM |  | 3
249 | Yes | Auto Scheduled | Monthly Production Reports 82 | 1 day | 27/11/18 8:00 AM | 27/11/18 5:00 PM |  | 3
250 | Yes | Auto Scheduled | Monthly Production Reports 83 | 1 day | 27/12/18 8:00 AM | 27/12/18 5:00 PM |  | 3
251 | Yes | Auto Scheduled | Monthly Production Reports 84 | 1 day | 28/01/19 8:00 AM | 28/01/19 5:00 PM |  | 3
252 | Yes | Auto Scheduled | Monthly Production Reports 85 | 1 day | 27/02/19 8:00 AM | 27/02/19 5:00 PM |  | 3
253 | Yes | Auto Scheduled | Monthly Production Reports 86 | 1 day | 27/03/19 8:00 AM | 27/03/19 5:00 PM |  | 3
254 | Yes | Auto Scheduled | Monthly Production Reports 87 | 1 day | 29/04/19 8:00 AM | 29/04/19 5:00 PM |  | 3
255 | Yes | Auto Scheduled | Monthly Production Reports 88 | 1 day | 27/05/19 8:00 AM | 27/05/19 5:00 PM |  | 3
256 | Yes | Auto Scheduled | Monthly Production Reports 89 | 1 day | 27/06/19 8:00 AM | 27/06/19 5:00 PM |  | 3
257 | Yes | Auto Scheduled | Monthly Production Reports 90 | 1 day | 29/07/19 8:00 AM | 29/07/19 5:00 PM |  | 3
258 | Yes | Auto Scheduled | Monthly Production Reports 91 | 1 day | 27/08/19 8:00 AM | 27/08/19 5:00 PM |  | 3
259 | Yes | Auto Scheduled | Monthly Production Reports 92 | 1 day | 27/09/19 8:00 AM | 27/09/19 5:00 PM |  | 3
260 | Yes | Auto Scheduled | Monthly Production Reports 93 | 1 day | 28/10/19 8:00 AM | 28/10/19 5:00 PM |  | 3
261 | Yes | Auto Scheduled | Monthly Production Reports 94 | 1 day | 27/11/19 8:00 AM | 27/11/19 5:00 PM |  | 3
262 | Yes | Auto Scheduled | Monthly Production Reports 95 | 1 day | 27/12/19 8:00 AM | 27/12/19 5:00 PM |  | 3
263 | Yes | Auto Scheduled | Monthly Production Reports 96 | 1 day | 27/01/20 8:00 AM | 27/01/20 5:00 PM |  | 3
264 | Yes | Auto Scheduled | Monthly Production Reports 97 | 1 day | 27/02/20 8:00 AM | 27/02/20 5:00 PM |  | 3
265 | Yes | Auto Scheduled | Monthly Production Reports 98 | 1 day | 27/03/20 8:00 AM | 27/03/20 5:00 PM |  | 3
266 | Yes | Auto Scheduled | Monthly Production Reports 99 | 1 day | 27/04/20 8:00 AM | 27/04/20 5:00 PM |  | 3
267 | Yes | Auto Scheduled | Monthly Production Reports 100 | 1 day | 27/05/20 8:00 AM | 27/05/20 5:00 PM |  | 3
268 | Yes | Auto Scheduled | Monthly Production Reports 101 | 1 day | 29/06/20 8:00 AM | 29/06/20 5:00 PM |  | 3
269 | Yes | Auto Scheduled | Monthly Production Reports 102 | 1 day | 27/07/20 8:00 AM | 27/07/20 5:00 PM |  | 3
270 | Yes | Auto Scheduled | Monthly Production Reports 103 | 1 day | 27/08/20 8:00 AM | 27/08/20 5:00 PM |  | 3
271 | Yes | Auto Scheduled | Monthly Production Reports 104 | 1 day | 28/09/20 8:00 AM | 28/09/20 5:00 PM |  | 3
272 | Yes | Auto Scheduled | Monthly Production Reports 105 | 1 day | 27/10/20 8:00 AM | 27/10/20 5:00 PM |  | 3
273 | Yes | Auto Scheduled | Monthly Production Reports 106 | 1 day | 27/11/20 8:00 AM | 27/11/20 5:00 PM |  | 3
274 | Yes | Auto Scheduled | Monthly Production Reports 107 | 1 day | 28/12/20 8:00 AM | 28/12/20 5:00 PM |  | 3
275 | Yes | Auto Scheduled | Monthly Production Reports 108 | 1 day | 27/01/21 8:00 AM | 27/01/21 5:00 PM |  | 3
276 | Yes | Auto Scheduled | Monthly Production Reports 109 | 1 day | 01/03/21 8:00 AM | 01/03/21 5:00 PM |  | 3
277 | Yes | Auto Scheduled | Monthly Production Reports 110 | 1 day | 29/03/21 8:00 AM | 29/03/21 5:00 PM |  | 3
278 | Yes | Auto Scheduled | Monthly Production Reports 111 | 1 day | 27/04/21 8:00 AM | 27/04/21 5:00 PM |  | 3
279 | Yes | Auto Scheduled | Monthly Production Reports 112 | 1 day | 27/05/21 8:00 AM | 27/05/21 5:00 PM |  | 3
280 | Yes | Auto Scheduled | Monthly Production Reports 113 | 1 day | 28/06/21 8:00 AM | 28/06/21 5:00 PM |  | 3
281 | Yes | Auto Scheduled | Monthly Production Reports 114 | 1 day | 27/07/21 8:00 AM | 27/07/21 5:00 PM |  | 3
282 | Yes | Auto Scheduled | Monthly Production Reports 115 | 1 day | 27/08/21 8:00 AM | 27/08/21 5:00 PM |  | 3
283 | Yes | Auto Scheduled | Monthly Production Reports 116 | 1 day | 27/09/21 8:00 AM | 27/09/21 5:00 PM |  | 3
284 | Yes | Auto Scheduled | Monthly Production Reports 117 | 1 day | 27/10/21 8:00 AM | 27/10/21 5:00 PM |  | 3
285 | Yes | Auto Scheduled | Monthly Production Reports 118 | 1 day | 29/11/21 8:00 AM | 29/11/21 5:00 PM |  | 3
286 | Yes | Auto Scheduled | Monthly Production Reports 119 | 1 day | 27/12/21 8:00 AM | 27/12/21 5:00 PM |  | 3
287 | Yes | Auto Scheduled | Monthly Production Reports 120 | 1 day | 27/01/22 8:00 AM | 27/01/22 5:00 PM |  | 3
288 | Yes | Auto Scheduled | Monthly Production Reports 121 | 1 day | 28/02/22 8:00 AM | 28/02/22 5:00 PM |  | 3
289 | Yes | Auto Scheduled | Monthly Production Reports 122 | 1 day | 28/03/22 8:00 AM | 28/03/22 5:00 PM |  | 3
290 | Yes | Auto Scheduled | Monthly Production Reports 123 | 1 day | 27/04/22 8:00 AM | 27/04/22 5:00 PM |  | 3
291 | Yes | Auto Scheduled | Monthly Production Reports 124 | 1 day | 27/05/22 8:00 AM | 27/05/22 5:00 PM |  | 3
292 | Yes | Auto Scheduled | Monthly Production Reports 125 | 1 day | 27/06/22 8:00 AM | 27/06/22 5:00 PM |  | 3
293 | Yes | Auto Scheduled | Monthly Production Reports 126 | 1 day | 27/07/22 8:00 AM | 27/07/22 5:00 PM |  | 3
294 | Yes | Auto Scheduled | Monthly Production Reports 127 | 1 day | 29/08/22 8:00 AM | 29/08/22 5:00 PM |  | 3
295 | Yes | Auto Scheduled | Monthly Production Reports 128 | 1 day | 27/09/22 8:00 AM | 27/09/22 5:00 PM |  | 3
296 | Yes | Auto Scheduled | Monthly Production Reports 129 | 1 day | 27/10/22 8:00 AM | 27/10/22 5:00 PM |  | 3
297 | Yes | Auto Scheduled | Monthly Production Reports 130 | 1 day | 28/11/22 8:00 AM | 28/11/22 5:00 PM |  | 3
298 | Yes | Auto Scheduled | Monthly Production Reports 131 | 1 day | 27/12/22 8:00 AM | 27/12/22 5:00 PM |  | 3
299 | Yes | Auto Scheduled | Monthly Production Reports 132 | 1 day | 27/01/23 8:00 AM | 27/01/23 5:00 PM |  | 3
300 | Yes | Auto Scheduled | Monthly Production Reports 133 | 1 day | 27/02/23 8:00 AM | 27/02/23 5:00 PM |  | 3
301 | Yes | Auto Scheduled | Monthly Production Reports 134 | 1 day | 27/03/23 8:00 AM | 27/03/23 5:00 PM |  | 3
302 | Yes | Auto Scheduled | Monthly Production Reports 135 | 1 day | 27/04/23 8:00 AM | 27/04/23 5:00 PM |  | 3
303 | Yes | Auto Scheduled | Monthly Production Reports 136 | 1 day | 29/05/23 8:00 AM | 29/05/23 5:00 PM |  | 3
304 | Yes | Auto Scheduled | Monthly Production Reports 137 | 1 day | 27/06/23 8:00 AM | 27/06/23 5:00 PM |  | 3
305 | Yes | Auto Scheduled | Monthly Production Reports 138 | 1 day | 27/07/23 8:00 AM | 27/07/23 5:00 PM |  | 3
306 | Yes | Auto Scheduled | Monthly Production Reports 139 | 1 day | 28/08/23 8:00 AM | 28/08/23 5:00 PM |  | 3
307 | Yes | Auto Scheduled | Monthly Production Reports 140 | 1 day | 27/09/23 8:00 AM | 27/09/23 5:00 PM |  | 3
308 | Yes | Auto Scheduled | Monthly Production Reports 141 | 1 day | 27/10/23 8:00 AM | 27/10/23 5:00 PM |  | 3
309 | Yes | Auto Scheduled | Monthly Production Reports 142 | 1 day | 27/11/23 8:00 AM | 27/11/23 5:00 PM |  | 3
310 | Yes | Auto Scheduled | Monthly Production Reports 143 | 1 day | 27/12/23 8:00 AM | 27/12/23 5:00 PM |  | 3
311 | Yes | Auto Scheduled | Monthly Production Reports 144 | 1 day | 29/01/24 8:00 AM | 29/01/24 5:00 PM |  | 3
312 | Yes | Auto Scheduled | Monthly Production Reports 145 | 1 day | 27/02/24 8:00 AM | 27/02/24 5:00 PM |  | 3
313 | Yes | Auto Scheduled | Monthly Production Reports 146 | 1 day | 27/03/24 8:00 AM | 27/03/24 5:00 PM |  | 3
314 | Yes | Auto Scheduled | Monthly Production Reports 147 | 1 day | 29/04/24 8:00 AM | 29/04/24 5:00 PM |  | 3
315 | Yes | Auto Scheduled | Monthly Production Reports 148 | 1 day | 27/05/24 8:00 AM | 27/05/24 5:00 PM |  | 3
316 | Yes | Auto Scheduled | Monthly Production Reports 149 | 1 day | 27/06/24 8:00 AM | 27/06/24 5:00 PM |  | 3
317 | Yes | Auto Scheduled | Monthly Production Reports 150 | 1 day | 29/07/24 8:00 AM | 29/07/24 5:00 PM |  | 3
318 | Yes | Auto Scheduled | Monthly Production Reports 151 | 1 day | 27/08/24 8:00 AM | 27/08/24 5:00 PM |  | 3
319 | Yes | Auto Scheduled | Monthly Production Reports 152 | 1 day | 27/09/24 8:00 AM | 27/09/24 5:00 PM |  | 3
320 | Yes | Auto Scheduled | Monthly Production Reports 153 | 1 day | 28/10/24 8:00 AM | 28/10/24 5:00 PM |  | 3
321 | Yes | Auto Scheduled | Monthly Production Reports 154 | 1 day | 27/11/24 8:00 AM | 27/11/24 5:00 PM |  | 3
322 | Yes | Auto Scheduled | Monthly Production Reports 155 | 1 day | 27/12/24 8:00 AM | 27/12/24 5:00 PM |  | 3
323 | Yes | Auto Scheduled | Monthly Production Reports 156 | 1 day | 27/01/25 8:00 AM | 27/01/25 5:00 PM |  | 3
324 | Yes | Auto Scheduled | Monthly Production Reports 157 | 1 day | 27/02/25 8:00 AM | 27/02/25 5:00 PM |  | 3
325 | Yes | Auto Scheduled | Monthly Production Reports 158 | 1 day | 27/03/25 8:00 AM | 27/03/25 5:00 PM |  | 3
326 | Yes | Auto Scheduled | Monthly Production Reports 159 | 1 day | 28/04/25 8:00 AM | 28/04/25 5:00 PM |  | 3
327 | Yes | Auto Scheduled | Monthly Production Reports 160 | 1 day | 27/05/25 8:00 AM | 27/05/25 5:00 PM |  | 3
328 | Yes | Auto Scheduled | Monthly Production Reports 161 | 1 day | 27/06/25 8:00 AM | 27/06/25 5:00 PM |  | 3
329 | Yes | Auto Scheduled | Monthly Production Reports 162 | 1 day | 28/07/25 8:00 AM | 28/07/25 5:00 PM |  | 3
330 | Yes | Auto Scheduled | Monthly Production Reports 163 | 1 day | 27/08/25 8:00 AM | 27/08/25 5:00 PM |  | 3
331 | Yes | Auto Scheduled | Monthly Production Reports 164 | 1 day | 29/09/25 8:00 AM | 29/09/25 5:00 PM |  | 3
332 | Yes | Auto Scheduled | Monthly Production Reports 165 | 1 day | 27/10/25 8:00 AM | 27/10/25 5:00 PM |  | 3
333 | Yes | Auto Scheduled | Monthly Production Reports 166 | 1 day | 27/11/25 8:00 AM | 27/11/25 5:00 PM |  | 3
334 | Yes | Auto Scheduled | Monthly Production Reports 167 | 1 day | 29/12/25 8:00 AM | 29/12/25 5:00 PM |  | 3
335 | Yes | Auto Scheduled | Monthly Production Reports 168 | 1 day | 27/01/26 8:00 AM | 27/01/26 5:00 PM |  | 3
336 | Yes | Auto Scheduled | Monthly Production Reports 169 | 1 day | 27/02/26 8:00 AM | 27/02/26 5:00 PM |  | 3
337 | Yes | Auto Scheduled | Monthly Production Reports 170 | 1 day | 27/03/26 8:00 AM | 27/03/26 5:00 PM |  | 3
338 | Yes | Auto Scheduled | Monthly Production Reports 171 | 1 day | 27/04/26 8:00 AM | 27/04/26 5:00 PM |  | 3
339 | Yes | Auto Scheduled | Monthly Production Reports 172 | 1 day | 27/05/26 8:00 AM | 27/05/26 5:00 PM |  | 3
340 | Yes | Auto Scheduled | Monthly Production Reports 173 | 1 day | 29/06/26 8:00 AM | 29/06/26 5:00 PM |  | 3
341 | Yes | Auto Scheduled | Monthly Production Reports 174 | 1 day | 27/07/26 8:00 AM | 27/07/26 5:00 PM |  | 3
342 | Yes | Auto Scheduled | Monthly Production Reports 175 | 1 day | 27/08/26 8:00 AM | 27/08/26 5:00 PM |  | 3
343 | Yes | Auto Scheduled | Monthly Production Reports 176 | 1 day | 28/09/26 8:00 AM | 28/09/26 5:00 PM |  | 3
344 | Yes | Auto Scheduled | Monthly Production Reports 177 | 1 day | 27/10/26 8:00 AM | 27/10/26 5:00 PM |  | 3
345 | Yes | Auto Scheduled | Monthly Production Reports 178 | 1 day | 27/11/26 8:00 AM | 27/11/26 5:00 PM |  | 3
346 | Yes | Auto Scheduled | Monthly Production Reports 179 | 1 day | 28/12/26 8:00 AM | 28/12/26 5:00 PM |  | 3
347 | Yes | Auto Scheduled | Monthly Production Reports 180 | 1 day | 27/01/27 8:00 AM | 27/01/27 5:00 PM |  | 3
348 | Yes | Auto Scheduled | Monthly Production Reports 181 | 1 day | 01/03/27 8:00 AM | 01/03/27 5:00 PM |  | 3
349 | Yes | Auto Scheduled | Monthly Production Reports 182 | 1 day | 29/03/27 8:00 AM | 29/03/27 5:00 PM |  | 3
350 | Yes | Auto Scheduled | Monthly Production Reports 183 | 1 day | 27/04/27 8:00 AM | 27/04/27 5:00 PM |  | 3
351 | Yes | Auto Scheduled | Monthly Production Reports 184 | 1 day | 27/05/27 8:00 AM | 27/05/27 5:00 PM |  | 3
352 | Yes | Auto Scheduled | Monthly Production Reports 185 | 1 day | 28/06/27 8:00 AM | 28/06/27 5:00 PM |  | 3
353 | Yes | Auto Scheduled | Monthly Production Reports 186 | 1 day | 27/07/27 8:00 AM | 27/07/27 5:00 PM |  | 3
354 | Yes | Auto Scheduled | Monthly Production Reports 187 | 1 day | 27/08/27 8:00 AM | 27/08/27 5:00 PM |  | 3
355 | Yes | Auto Scheduled | Monthly Production Reports 188 | 1 day | 27/09/27 8:00 AM | 27/09/27 5:00 PM |  | 3
356 | Yes | Auto Scheduled | Monthly Production Reports 189 | 1 day | 27/10/27 8:00 AM | 27/10/27 5:00 PM |  | 3
357 | Yes | Auto Scheduled | Monthly Production Reports 190 | 1 day | 29/11/27 8:00 AM | 29/11/27 5:00 PM |  | 3
358 | Yes | Auto Scheduled | Monthly Production Reports 191 | 1 day | 27/12/27 8:00 AM | 27/12/27 5:00 PM |  | 3
359 | Yes | Auto Scheduled | Monthly Production Reports 192 | 1 day | 27/01/28 8:00 AM | 27/01/28 5:00 PM |  | 3
360 | Yes | Auto Scheduled | Monthly Production Reports 193 | 1 day | 28/02/28 8:00 AM | 28/02/28 5:00 PM |  | 3
361 | Yes | Auto Scheduled | Monthly Production Reports 194 | 1 day | 27/03/28 8:00 AM | 27/03/28 5:00 PM |  | 3
362 | Yes | Auto Scheduled | Monthly Production Reports 195 | 1 day | 27/04/28 8:00 AM | 27/04/28 5:00 PM |  | 3
363 | Yes | Auto Scheduled | Monthly Production Reports 196 | 1 day | 29/05/28 8:00 AM | 29/05/28 5:00 PM |  | 3
364 | Yes | Auto Scheduled | Monthly Production Reports 197 | 1 day | 27/06/28 8:00 AM | 27/06/28 5:00 PM |  | 3
365 | Yes | Auto Scheduled | Monthly Production Reports 198 | 1 day | 27/07/28 8:00 AM | 27/07/28 5:00 PM |  | 3
366 | Yes | Auto Scheduled | Monthly Production Reports 199 | 1 day | 28/08/28 8:00 AM | 28/08/28 5:00 PM |  | 3
367 | Yes | Auto Scheduled | Monthly Production Reports 200 | 1 day | 27/09/28 8:00 AM | 27/09/28 5:00 PM |  | 3
368 | Yes | Auto Scheduled | Monthly Production Reports 201 | 1 day | 27/10/28 8:00 AM | 27/10/28 5:00 PM |  | 3
369 | Yes | Auto Scheduled | Monthly Production Reports 202 | 1 day | 27/11/28 8:00 AM | 27/11/28 5:00 PM |  | 3
370 | Yes | Auto Scheduled | Monthly Production Reports 203 | 1 day | 27/12/28 8:00 AM | 27/12/28 5:00 PM |  | 3
371 | Yes | Auto Scheduled | Monthly Production Reports 204 | 1 day | 29/01/29 8:00 AM | 29/01/29 5:00 PM |  | 3
372 | Yes | Auto Scheduled | Monthly Production Reports 205 | 1 day | 27/02/29 8:00 AM | 27/02/29 5:00 PM |  | 3
373 | Yes | Auto Scheduled | Monthly Production Reports 206 | 1 day | 27/03/29 8:00 AM | 27/03/29 5:00 PM |  | 3
374 | Yes | Auto Scheduled | Monthly Production Reports 207 | 1 day | 27/04/29 8:00 AM | 27/04/29 5:00 PM |  | 3
375 | Yes | Auto Scheduled | Monthly Production Reports 208 | 1 day | 28/05/29 8:00 AM | 28/05/29 5:00 PM |  | 3
376 | Yes | Auto Scheduled | Monthly Production Reports 209 | 1 day | 27/06/29 8:00 AM | 27/06/29 5:00 PM |  | 3
377 | Yes | Auto Scheduled | Monthly Production Reports 210 | 1 day | 27/07/29 8:00 AM | 27/07/29 5:00 PM |  | 3
378 | Yes | Auto Scheduled | Monthly Production Reports 211 | 1 day | 27/08/29 8:00 AM | 27/08/29 5:00 PM |  | 3
379 | Yes | Auto Scheduled | Monthly Production Reports 212 | 1 day | 27/09/29 8:00 AM | 27/09/29 5:00 PM |  | 3
380 | Yes | Auto Scheduled | Monthly Production Reports 213 | 1 day | 29/10/29 8:00 AM | 29/10/29 5:00 PM |  | 3
381 | Yes | Auto Scheduled | Monthly Production Reports 214 | 1 day | 27/11/29 8:00 AM | 27/11/29 5:00 PM |  | 3
382 | Yes | Auto Scheduled | Monthly Production Reports 215 | 1 day | 27/12/29 8:00 AM | 27/12/29 5:00 PM |  | 3
383 | Yes | Auto Scheduled | Monthly Production Reports 216 | 1 day | 28/01/30 8:00 AM | 28/01/30 5:00 PM |  | 3
384 | Yes | Auto Scheduled | Monthly Production Reports 217 | 1 day | 27/02/30 8:00 AM | 27/02/30 5:00 PM |  | 3
385 | Yes | Auto Scheduled | Monthly Production Reports 218 | 1 day | 27/03/30 8:00 AM | 27/03/30 5:00 PM |  | 3
386 | Yes | Auto Scheduled | Monthly Production Reports 219 | 1 day | 29/04/30 8:00 AM | 29/04/30 5:00 PM |  | 3
387 | Yes | Auto Scheduled | Monthly Production Reports 220 | 1 day | 27/05/30 8:00 AM | 27/05/30 5:00 PM |  | 3
388 | Yes | Auto Scheduled | Monthly Production Reports 221 | 1 day | 27/06/30 8:00 AM | 27/06/30 5:00 PM |  | 3
389 | Yes | Auto Scheduled | Monthly Production Reports 222 | 1 day | 29/07/30 8:00 AM | 29/07/30 5:00 PM |  | 3
390 | Yes | Auto Scheduled | Monthly Production Reports 223 | 1 day | 27/08/30 8:00 AM | 27/08/30 5:00 PM |  | 3
391 | Yes | Auto Scheduled | Monthly Production Reports 224 | 1 day | 27/09/30 8:00 AM | 27/09/30 5:00 PM |  | 3
392 | Yes | Auto Scheduled | Monthly Production Reports 225 | 1 day | 28/10/30 8:00 AM | 28/10/30 5:00 PM |  | 3
393 | Yes | Auto Scheduled | Monthly Production Reports 226 | 1 day | 27/11/30 8:00 AM | 27/11/30 5:00 PM |  | 3
394 | Yes | Auto Scheduled | Monthly Production Reports 227 | 1 day | 27/12/30 8:00 AM | 27/12/30 5:00 PM |  | 3
395 | Yes | Auto Scheduled | Monthly Production Reports 228 | 1 day | 27/01/31 8:00 AM | 27/01/31 5:00 PM |  | 3
396 | Yes | Auto Scheduled | Monthly Production Reports 229 | 1 day | 27/02/31 8:00 AM | 27/02/31 5:00 PM |  | 3
397 | Yes | Auto Scheduled | Monthly Production Reports 230 | 1 day | 27/03/31 8:00 AM | 27/03/31 5:00 PM |  | 3
398 | Yes | Auto Scheduled | Monthly Production Reports 231 | 1 day | 28/04/31 8:00 AM | 28/04/31 5:00 PM |  | 3
399 | Yes | Auto Scheduled | Monthly Production Reports 232 | 1 day | 27/05/31 8:00 AM | 27/05/31 5:00 PM |  | 3
400 | Yes | Auto Scheduled | Monthly Production Reports 233 | 1 day | 27/06/31 8:00 AM | 27/06/31 5:00 PM |  | 3
401 | Yes | Auto Scheduled | Monthly Production Reports 234 | 1 day | 28/07/31 8:00 AM | 28/07/31 5:00 PM |  | 3
402 | Yes | Auto Scheduled | Monthly Production Reports 235 | 1 day | 27/08/31 8:00 AM | 27/08/31 5:00 PM |  | 3
403 | Yes | Auto Scheduled | Monthly Production Reports 236 | 1 day | 29/09/31 8:00 AM | 29/09/31 5:00 PM |  | 3
404 | Yes | Auto Scheduled | Monthly Production Reports 237 | 1 day | 27/10/31 8:00 AM | 27/10/31 5:00 PM |  | 3
405 | Yes | Auto Scheduled | Monthly Production Reports 238 | 1 day | 27/11/31 8:00 AM | 27/11/31 5:00 PM |  | 3
406 | Yes | Auto Scheduled | Monthly Production Reports 239 | 1 day | 29/12/31 8:00 AM | 29/12/31 5:00 PM |  | 3
407 | Yes | Auto Scheduled | Monthly Production Reports 240 | 1 day | 27/01/32 8:00 AM | 27/01/32 5:00 PM |  | 3
408 | Yes | Auto Scheduled | Monthly Production Reports 241 | 1 day | 27/02/32 8:00 AM | 27/02/32 5:00 PM |  | 3
409 | Yes | Auto Scheduled | Monthly Production Reports 242 | 1 day | 29/03/32 8:00 AM | 29/03/32 5:00 PM |  | 3
410 | Yes | Auto Scheduled | Monthly Production Reports 243 | 1 day | 27/04/32 8:00 AM | 27/04/32 5:00 PM |  | 3
411 | Yes | Auto Scheduled | Monthly Production Reports 244 | 1 day | 27/05/32 8:00 AM | 27/05/32 5:00 PM |  | 3
412 | Yes | Auto Scheduled | Monthly Production Reports 245 | 1 day | 28/06/32 8:00 AM | 28/06/32 5:00 PM |  | 3
413 | Yes | Auto Scheduled | Monthly Production Reports 246 | 1 day | 27/07/32 8:00 AM | 27/07/32 5:00 PM |  | 3
414 | Yes | Auto Scheduled | Monthly Production Reports 247 | 1 day | 27/08/32 8:00 AM | 27/08/32 5:00 PM |  | 3
415 | Yes | Auto Scheduled | Monthly Production Reports 248 | 1 day | 27/09/32 8:00 AM | 27/09/32 5:00 PM |  | 3
416 | Yes | Auto Scheduled | Monthly Production Reports 249 | 1 day | 27/10/32 8:00 AM | 27/10/32 5:00 PM |  | 3
417 | Yes | Auto Scheduled | Monthly Production Reports 250 | 1 day | 29/11/32 8:00 AM | 29/11/32 5:00 PM |  | 3
418 | Yes | Auto Scheduled | Monthly Production Reports 251 | 1 day | 27/12/32 8:00 AM | 27/12/32 5:00 PM |  | 3
419 | Yes | Auto Scheduled | Monthly Production Reports 252 | 1 day | 27/01/33 8:00 AM | 27/01/33 5:00 PM |  | 3
420 | Yes | Auto Scheduled | Monthly Production Reports 253 | 1 day | 28/02/33 8:00 AM | 28/02/33 5:00 PM |  | 3
421 | Yes | Auto Scheduled | Monthly Production Reports 254 | 1 day | 28/03/33 8:00 AM | 28/03/33 5:00 PM |  | 3
422 | Yes | Auto Scheduled | Monthly Production Reports 255 | 1 day | 27/04/33 8:00 AM | 27/04/33 5:00 PM |  | 3
423 | Yes | Auto Scheduled | Monthly Production Reports 256 | 1 day | 27/05/33 8:00 AM | 27/05/33 5:00 PM |  | 3
424 | Yes | Auto Scheduled | Monthly Production Reports 257 | 1 day | 27/06/33 8:00 AM | 27/06/33 5:00 PM |  | 3
425 | Yes | Auto Scheduled | Monthly Production Reports 258 | 1 day | 27/07/33 8:00 AM | 27/07/33 5:00 PM |  | 3
426 | Yes | Auto Scheduled | Monthly Production Reports 259 | 1 day | 29/08/33 8:00 AM | 29/08/33 5:00 PM |  | 3
427 | Yes | Auto Scheduled | Monthly Production Reports 260 | 1 day | 27/09/33 8:00 AM | 27/09/33 5:00 PM |  | 3
428 | Yes | Auto Scheduled | Monthly Production Reports 261 | 1 day | 27/10/33 8:00 AM | 27/10/33 5:00 PM |  | 3
429 | Yes | Auto Scheduled | Monthly Production Reports 262 | 1 day | 28/11/33 8:00 AM | 28/11/33 5:00 PM |  | 3
430 | Yes | Auto Scheduled | Monthly Production Reports 263 | 1 day | 27/12/33 8:00 AM | 27/12/33 5:00 PM |  | 3
431 | Yes | Auto Scheduled | Monthly Production Reports 264 | 1 day | 27/01/34 8:00 AM | 27/01/34 5:00 PM |  | 3
432 | Yes | Auto Scheduled | Monthly Production Reports 265 | 1 day | 27/02/34 8:00 AM | 27/02/34 5:00 PM |  | 3
433 | Yes | Auto Scheduled | Monthly Production Reports 266 | 1 day | 27/03/34 8:00 AM | 27/03/34 5:00 PM |  | 3
434 | Yes | Auto Scheduled | Monthly Production Reports 267 | 1 day | 27/04/34 8:00 AM | 27/04/34 5:00 PM |  | 3
435 | Yes | Auto Scheduled | Monthly Production Reports 268 | 1 day | 29/05/34 8:00 AM | 29/05/34 5:00 PM |  | 3
436 | Yes | Auto Scheduled | Monthly Production Reports 269 | 1 day | 27/06/34 8:00 AM | 27/06/34 5:00 PM |  | 3
437 | Yes | Auto Scheduled | Monthly Production Reports 270 | 1 day | 27/07/34 8:00 AM | 27/07/34 5:00 PM |  | 3
438 | Yes | Auto Scheduled | Monthly Production Reports 271 | 1 day | 28/08/34 8:00 AM | 28/08/34 5:00 PM |  | 3
439 | Yes | Auto Scheduled | Monthly Production Reports 272 | 1 day | 27/09/34 8:00 AM | 27/09/34 5:00 PM |  | 3
440 | Yes | Auto Scheduled | Monthly Production Reports 273 | 1 day | 27/10/34 8:00 AM | 27/10/34 5:00 PM |  | 3
441 | Yes | Auto Scheduled | Monthly Production Reports 274 | 1 day | 27/11/34 8:00 AM | 27/11/34 5:00 PM |  | 3
442 | Yes | Auto Scheduled | Monthly Production Reports 275 | 1 day | 27/12/34 8:00 AM | 27/12/34 5:00 PM |  | 3
443 | Yes | Auto Scheduled | Monthly Production Reports 276 | 1 day | 29/01/35 8:00 AM | 29/01/35 5:00 PM |  | 3
444 | Yes | Auto Scheduled | Monthly Production Reports 277 | 1 day | 27/02/35 8:00 AM | 27/02/35 5:00 PM |  | 3
445 | Yes | Auto Scheduled | Monthly Production Reports 278 | 1 day | 27/03/35 8:00 AM | 27/03/35 5:00 PM |  | 3
446 | Yes | Auto Scheduled | Monthly Production Reports 279 | 1 day | 27/04/35 8:00 AM | 27/04/35 5:00 PM |  | 3
447 | Yes | Auto Scheduled | Monthly Production Reports 280 | 1 day | 28/05/35 8:00 AM | 28/05/35 5:00 PM |  | 3
448 | Yes | Auto Scheduled | Monthly Production Reports 281 | 1 day | 27/06/35 8:00 AM | 27/06/35 5:00 PM |  | 3
449 | Yes | Auto Scheduled | Monthly Production Reports 282 | 1 day | 27/07/35 8:00 AM | 27/07/35 5:00 PM |  | 3
450 | Yes | Auto Scheduled | Monthly Production Reports 283 | 1 day | 27/08/35 8:00 AM | 27/08/35 5:00 PM |  | 3
451 | Yes | Auto Scheduled | Monthly Production Reports 284 | 1 day | 27/09/35 8:00 AM | 27/09/35 5:00 PM |  | 3
452 | Yes | Auto Scheduled | Monthly Production Reports 285 | 1 day | 29/10/35 8:00 AM | 29/10/35 5:00 PM |  | 3
453 | Yes | Auto Scheduled | Monthly Production Reports 286 | 1 day | 27/11/35 8:00 AM | 27/11/35 5:00 PM |  | 3
454 | Yes | Auto Scheduled | Monthly Production Reports 287 | 1 day | 27/12/35 8:00 AM | 27/12/35 5:00 PM |  | 3
455 | Yes | Auto Scheduled | Monthly Production Reports 288 | 1 day | 28/01/36 8:00 AM | 28/01/36 5:00 PM |  | 3
456 | Yes | Auto Scheduled | Monthly Production Reports 289 | 1 day | 27/02/36 8:00 AM | 27/02/36 5:00 PM |  | 3
457 | Yes | Auto Scheduled | Monthly Production Reports 290 | 1 day | 27/03/36 8:00 AM | 27/03/36 5:00 PM |  | 3
458 | Yes | Auto Scheduled | Monthly Production Reports 291 | 1 day | 28/04/36 8:00 AM | 28/04/36 5:00 PM |  | 3
459 | Yes | Auto Scheduled | Monthly Production Reports 292 | 1 day | 27/05/36 8:00 AM | 27/05/36 5:00 PM |  | 3
460 | Yes | Auto Scheduled | Monthly Production Reports 293 | 1 day | 27/06/36 8:00 AM | 27/06/36 5:00 PM |  | 3
461 | Yes | Auto Scheduled | Monthly Production Reports 294 | 1 day | 28/07/36 8:00 AM | 28/07/36 5:00 PM |  | 3
462 | Yes | Auto Scheduled | Monthly Production Reports 295 | 1 day | 27/08/36 8:00 AM | 27/08/36 5:00 PM |  | 3
463 | Yes | Auto Scheduled | Monthly Production Reports 296 | 1 day | 29/09/36 8:00 AM | 29/09/36 5:00 PM |  | 3
464 | Yes | Auto Scheduled | Monthly Production Reports 297 | 1 day | 27/10/36 8:00 AM | 27/10/36 5:00 PM |  | 3
465 | Yes | Auto Scheduled | Monthly Production Reports 298 | 1 day | 27/11/36 8:00 AM | 27/11/36 5:00 PM |  | 3
466 | Yes | Auto Scheduled | Monthly Production Reports 299 | 1 day | 29/12/36 8:00 AM | 29/12/36 5:00 PM |  | 3
467 | Yes | Auto Scheduled | Monthly Production Reports 300 | 1 day | 27/01/37 8:00 AM | 27/01/37 5:00 PM |  | 3
468 | Yes | Auto Scheduled | Monthly Production Reports 301 | 1 day | 27/02/37 8:00 AM | 27/02/37 5:00 PM |  | 3
469 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) | 4967 days | 07/03/18 5:00 PM | 23/03/37 8:00 AM | 164 | 2 | submitted quarterly to DMP
470 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 1 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
471 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 2 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
472 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 3 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
473 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 4 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
474 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 5 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
475 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 6 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
476 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 7 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
477 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 8 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
478 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 9 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
479 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 10 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
480 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 11 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
481 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 12 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
482 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 13 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
483 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 14 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
484 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 15 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
485 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 16 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
486 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 17 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
487 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 18 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
488 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 19 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
489 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 20 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
490 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 21 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
491 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 22 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
492 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 23 | 0 days | 07/03/18 5:00 PM | 07/03/18 5:00 PM |  | 3
493 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 24 | 0 days | 26/03/18 8:00 AM | 26/03/18 8:00 AM |  | 3
494 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 25 | 0 days | 25/06/18 8:00 AM | 25/06/18 8:00 AM |  | 3
495 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 26 | 0 days | 24/09/18 8:00 AM | 24/09/18 8:00 AM |  | 3
496 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 27 | 0 days | 24/12/18 8:00 AM | 24/12/18 8:00 AM |  | 3
497 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 28 | 0 days | 25/03/19 8:00 AM | 25/03/19 8:00 AM |  | 3
498 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 29 | 0 days | 24/06/19 8:00 AM | 24/06/19 8:00 AM |  | 3
499 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 30 | 0 days | 23/09/19 8:00 AM | 23/09/19 8:00 AM |  | 3
500 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 31 | 0 days | 23/12/19 8:00 AM | 23/12/19 8:00 AM |  | 3
501 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 32 | 0 days | 23/03/20 8:00 AM | 23/03/20 8:00 AM |  | 3
502 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 33 | 0 days | 22/06/20 8:00 AM | 22/06/20 8:00 AM |  | 3
503 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 34 | 0 days | 28/09/20 8:00 AM | 28/09/20 8:00 AM |  | 3
504 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 35 | 0 days | 28/12/20 8:00 AM | 28/12/20 8:00 AM |  | 3
505 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 36 | 0 days | 22/03/21 8:00 AM | 22/03/21 8:00 AM |  | 3
506 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 37 | 0 days | 28/06/21 8:00 AM | 28/06/21 8:00 AM |  | 3
507 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 38 | 0 days | 27/09/21 8:00 AM | 27/09/21 8:00 AM |  | 3
508 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 39 | 0 days | 27/12/21 8:00 AM | 27/12/21 8:00 AM |  | 3
509 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 40 | 0 days | 28/03/22 8:00 AM | 28/03/22 8:00 AM |  | 3
510 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 41 | 0 days | 27/06/22 8:00 AM | 27/06/22 8:00 AM |  | 3
511 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 42 | 0 days | 26/09/22 8:00 AM | 26/09/22 8:00 AM |  | 3
512 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 43 | 0 days | 26/12/22 8:00 AM | 26/12/22 8:00 AM |  | 3
513 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 44 | 0 days | 27/03/23 8:00 AM | 27/03/23 8:00 AM |  | 3
514 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 45 | 0 days | 26/06/23 8:00 AM | 26/06/23 8:00 AM |  | 3
515 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 46 | 0 days | 25/09/23 8:00 AM | 25/09/23 8:00 AM |  | 3
516 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 47 | 0 days | 25/12/23 8:00 AM | 25/12/23 8:00 AM |  | 3
517 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 48 | 0 days | 25/03/24 8:00 AM | 25/03/24 8:00 AM |  | 3
518 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 49 | 0 days | 24/06/24 8:00 AM | 24/06/24 8:00 AM |  | 3
519 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 50 | 0 days | 23/09/24 8:00 AM | 23/09/24 8:00 AM |  | 3
520 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 51 | 0 days | 23/12/24 8:00 AM | 23/12/24 8:00 AM |  | 3
521 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 52 | 0 days | 24/03/25 8:00 AM | 24/03/25 8:00 AM |  | 3
522 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 53 | 0 days | 23/06/25 8:00 AM | 23/06/25 8:00 AM |  | 3
523 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 54 | 0 days | 22/09/25 8:00 AM | 22/09/25 8:00 AM |  | 3
524 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 55 | 0 days | 22/12/25 8:00 AM | 22/12/25 8:00 AM |  | 3
525 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 56 | 0 days | 23/03/26 8:00 AM | 23/03/26 8:00 AM |  | 3
526 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 57 | 0 days | 22/06/26 8:00 AM | 22/06/26 8:00 AM |  | 3
527 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 58 | 0 days | 28/09/26 8:00 AM | 28/09/26 8:00 AM |  | 3
528 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 59 | 0 days | 28/12/26 8:00 AM | 28/12/26 8:00 AM |  | 3
529 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 60 | 0 days | 22/03/27 8:00 AM | 22/03/27 8:00 AM |  | 3
530 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 61 | 0 days | 28/06/27 8:00 AM | 28/06/27 8:00 AM |  | 3
531 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 62 | 0 days | 27/09/27 8:00 AM | 27/09/27 8:00 AM |  | 3
532 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 63 | 0 days | 27/12/27 8:00 AM | 27/12/27 8:00 AM |  | 3
533 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 64 | 0 days | 27/03/28 8:00 AM | 27/03/28 8:00 AM |  | 3
534 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 65 | 0 days | 26/06/28 8:00 AM | 26/06/28 8:00 AM |  | 3
535 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 66 | 0 days | 25/09/28 8:00 AM | 25/09/28 8:00 AM |  | 3
536 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 67 | 0 days | 25/12/28 8:00 AM | 25/12/28 8:00 AM |  | 3
537 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 68 | 0 days | 26/03/29 8:00 AM | 26/03/29 8:00 AM |  | 3
538 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 69 | 0 days | 25/06/29 8:00 AM | 25/06/29 8:00 AM |  | 3
539 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 70 | 0 days | 24/09/29 8:00 AM | 24/09/29 8:00 AM |  | 3
540 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 71 | 0 days | 24/12/29 8:00 AM | 24/12/29 8:00 AM |  | 3
541 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 72 | 0 days | 25/03/30 8:00 AM | 25/03/30 8:00 AM |  | 3
542 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 73 | 0 days | 24/06/30 8:00 AM | 24/06/30 8:00 AM |  | 3
543 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 74 | 0 days | 23/09/30 8:00 AM | 23/09/30 8:00 AM |  | 3
544 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 75 | 0 days | 23/12/30 8:00 AM | 23/12/30 8:00 AM |  | 3
545 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 76 | 0 days | 24/03/31 8:00 AM | 24/03/31 8:00 AM |  | 3
546 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 77 | 0 days | 23/06/31 8:00 AM | 23/06/31 8:00 AM |  | 3
547 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 78 | 0 days | 22/09/31 8:00 AM | 22/09/31 8:00 AM |  | 3
548 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 79 | 0 days | 22/12/31 8:00 AM | 22/12/31 8:00 AM |  | 3
549 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 80 | 0 days | 22/03/32 8:00 AM | 22/03/32 8:00 AM |  | 3
550 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 81 | 0 days | 28/06/32 8:00 AM | 28/06/32 8:00 AM |  | 3
551 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 82 | 0 days | 27/09/32 8:00 AM | 27/09/32 8:00 AM |  | 3
552 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 83 | 0 days | 27/12/32 8:00 AM | 27/12/32 8:00 AM |  | 3
553 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 84 | 0 days | 28/03/33 8:00 AM | 28/03/33 8:00 AM |  | 3
554 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 85 | 0 days | 27/06/33 8:00 AM | 27/06/33 8:00 AM |  | 3
555 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 86 | 0 days | 26/09/33 8:00 AM | 26/09/33 8:00 AM |  | 3
556 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 87 | 0 days | 26/12/33 8:00 AM | 26/12/33 8:00 AM |  | 3
557 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 88 | 0 days | 27/03/34 8:00 AM | 27/03/34 8:00 AM |  | 3
558 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 89 | 0 days | 26/06/34 8:00 AM | 26/06/34 8:00 AM |  | 3
559 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 90 | 0 days | 25/09/34 8:00 AM | 25/09/34 8:00 AM |  | 3
560 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 91 | 0 days | 25/12/34 8:00 AM | 25/12/34 8:00 AM |  | 3
561 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 92 | 0 days | 26/03/35 8:00 AM | 26/03/35 8:00 AM |  | 3
562 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 93 | 0 days | 25/06/35 8:00 AM | 25/06/35 8:00 AM |  | 3
563 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 94 | 0 days | 24/09/35 8:00 AM | 24/09/35 8:00 AM |  | 3
564 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 95 | 0 days | 24/12/35 8:00 AM | 24/12/35 8:00 AM |  | 3
565 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 96 | 0 days | 24/03/36 8:00 AM | 24/03/36 8:00 AM |  | 3
566 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 97 | 0 days | 23/06/36 8:00 AM | 23/06/36 8:00 AM |  | 3
567 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 98 | 0 days | 22/09/36 8:00 AM | 22/09/36 8:00 AM |  | 3
568 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 99 | 0 days | 22/12/36 8:00 AM | 22/12/36 8:00 AM |  | 3
569 | Yes | Auto Scheduled | Quarterly Reports (Safety, Environment, Resource) 100 | 0 days | 23/03/37 8:00 AM | 23/03/37 8:00 AM |  | 3
570 | Yes | Auto Scheduled | Field Development Plan | 3915 days | 22/02/21 8:00 AM | 25/02/36 8:00 AM |  | 2 | updated every 5 years
571 | Yes | Auto Scheduled | Field Development Plan 5 year | 0 days | 22/02/21 8:00 AM | 22/02/21 8:00 AM |  | 3
572 | Yes | Auto Scheduled | Field Development Plan 10 year | 0 days | 23/02/26 8:00 AM | 23/02/26 8:00 AM |  | 3
573 | Yes | Auto Scheduled | Field Development Plan 15 year | 0 days | 24/02/31 8:00 AM | 24/02/31 8:00 AM |  | 3
574 | Yes | Auto Scheduled | Field Development Plan 20 year | 0 days | 25/02/36 8:00 AM | 25/02/36 8:00 AM |  | 3
575 | Yes | Auto Scheduled | Safety Case | 3915 days | 22/02/21 8:00 AM | 25/02/36 8:00 AM |  | 2 | updated every 5 years
576 | Yes | Auto Scheduled | Safety Case 5 year | 0 days | 22/02/21 8:00 AM | 22/02/21 8:00 AM |  | 3
577 | Yes | Auto Scheduled | Safety Case 10 year | 0 days | 23/02/26 8:00 AM | 23/02/26 8:00 AM |  | 3
578 | Yes | Auto Scheduled | Safety Case 15 year | 0 days | 24/02/31 8:00 AM | 24/02/31 8:00 AM |  | 3
579 | Yes | Auto Scheduled | Safety Case 20 year | 0 days | 25/02/36 8:00 AM | 25/02/36 8:00 AM |  | 3
580 | Yes | Auto Scheduled | Environment Plans | 3915 days | 22/02/21 8:00 AM | 25/02/36 8:00 AM |  | 2 | updated every 5 years
581 | Yes | Auto Scheduled | Environment Plans 5 year | 0 days | 22/02/21 8:00 AM | 22/02/21 8:00 AM |  | 3
582 | Yes | Auto Scheduled | Environment Plans 10 year | 0 days | 23/02/26 8:00 AM | 23/02/26 8:00 AM |  | 3
583 | Yes | Auto Scheduled | Environment Plans 15 year | 0 days | 24/02/31 8:00 AM | 24/02/31 8:00 AM |  | 3
584 | Yes | Auto Scheduled | Environment Plans 20 year | 0 days | 25/02/36 8:00 AM | 25/02/36 8:00 AM |  | 3
585 | Yes | Manually Scheduled | CLOSURE APPROVALS |  |  | 07/04/36 5:00 PM |  | 1
586 | Yes | Auto Scheduled | Field Abandonment Plan | 30 days | 25/02/36 8:00 AM | 04/04/36 5:00 PM | 584,579,574 | 2
587 | Yes | Auto Scheduled | Safety Case | 30 days | 25/02/36 8:00 AM | 04/04/36 5:00 PM | 584,579,574 | 3
588 | Yes | Auto Scheduled | Environment Plans | 30 days | 25/02/36 8:00 AM | 04/04/36 5:00 PM | 584,579,574 | 3
589 | Yes | Auto Scheduled | WOMP & Plug and Abandonment Plan | 30 days | 25/02/36 8:00 AM | 04/04/36 5:00 PM | 584,579,574 | 3
590 | Yes | Auto Scheduled | Decommissioning Plan | 30 days | 25/02/36 8:00 AM | 04/04/36 5:00 PM | 584,579,574 | 3
591 | Yes | Auto Scheduled | Removal of Surface Facilities & Pipeline Rehabilitation | 30 days | 25/02/36 8:00 AM | 04/04/36 5:00 PM | 584,579,574 | 3
592 | Yes | Auto Scheduled | Land Rehabilitation | 30 days | 25/02/36 8:00 AM | 04/04/36 5:00 PM | 584,579,574 | 3
593 | Yes | Auto Scheduled | Contaminated Sites Clearance | 30 days | 07/04/36 8:00 AM | 16/05/36 5:00 PM | 592 | 2
594 | Yes | Auto Scheduled | Surrender | 1 day | 07/04/36 8:00 AM | 07/04/36 5:00 PM | 586 | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | Windows User Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | DMP PEG | D | Work |  |  |  |  | 100% | $0.00/h | 0
2 | DEC | D | Work |  |  |  |  | 100% | $0.00/h | 0
3 | EPA | E | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Fisheries | F | Work |  |  |  |  | 100% | $0.00/h | 0
5 | NT | N | Work |  |  |  |  | 100% | $0.00/h | 0
6 | DMP/NNTT | D | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Proponent | P | Work |  |  |  |  | 100% | $0.00/h | 0
8 | DMP PD | D | Work |  |  |  |  | 100% | $0.00/h | 0
9 | DMP PTLAB | D | Work |  |  |  |  | 100% | $0.00/h | 0
10 | Resources Branch | R | Work |  |  |  |  | 100% | $0.00/h | 0
11 | Environment Division | E | Work |  |  |  |  | 100% | $0.00/h | 0
12 | Petroleum Tenure and Land Access Branch | P | Work |  |  |  |  | 100% | $0.00/h | 0
13 | http://www.dmp.wa.gov.au/1695.aspx | h | Work |  |  |  |  | 100% | $0.00/h | 0
14 | ED P | E | Work |  |  |  |  | 100% | $0.00/h | 0
15 | DOW | D | Work |  |  |  |  | 100% | $0.00/h | 0
16 | OEPA | O | Work |  |  |  |  | 100% | $0.00/h | 0
17 | DMP ED | D | Work |  |  |  |  | 100% | $0.00/h | 0
18 | DMP MTD | D | Work |  |  |  |  | 100% | $0.00/h | 0
19 | PD | P | Work |  |  |  |  | 100% | $0.00/h | 0
20 | DMP RSD | D | Work |  |  |  |  | 100% | $0.00/h | 0
21 | DIA | D | Work |  |  |  |  | 100% | $0.00/h | 0
22 | Proponent/Landgate | P | Work |  |  |  |  | 100% | $0.00/h | 0
23 | DMP | D | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
EXPLORATION TENURE APPROVALS | http://www.dmp.wa.gov.au/1695.aspx | 0 | 3,344h | 100%
Pre-gazette development | DMP PD | 0 | 480h | 100%
Determine area, prepare maps of lease showing conservation estates, reserves, NT | DMP PD | 0 | 160h | 100%
Consultation with stakeholders | DMP PD | 0 | 160h | 100%
Preparation of Gazette notice | DMP PD | 0 | 160h | 100%
Publish Gazette Notice (s30) | DMP PD | 0 | 8h | 100%
Prepare bid | Proponent | 0 | 960h | 100%
Lodge bid with DMP (s31) | Proponent | 0 | 8h | 100%
Award of Exploration Permit (s38) | DMP PD | 0 | 1,784h | 100%
assessment of bids/applications | DMP PD | 0 | 480h | 100%
bid assessment report | DMP PD | 0 | 160h | 100%
response to preferred applicant letter | Proponent | 0 | 112h | 100%
Native Title Agreements | DMP/NNTT | 0 | 1,144h | 100%
Advertised (s29 NTA) | DMP PD | 0 | 960h | 100%
Administration | DMP/NNTT | 0 | 480h | 100%
"Right to Negotiate" | DMP/NNTT | 0 | 1,000h | 100%
State Deed (s31) | DMP PD | 0 | 144h | 100%
offer of grant | DMP PD | 0 | 240h | 100%
award permit | DMP PD | 0 | 8h | 100%
Submit application | Proponent | 0 | 0h | 100%
Assess Technical Report | DMP PD | 0 | 240h | 100%
Assess Well Operation Management Plan (WOMP) and Drill Program | DMP PD | 0 | 240h | 100%
Assess Safety Management System | DMP RSD | 0 | 160h | 100%
Heritage Clearance | DIA | 0 | 240h | 100%
Access and Compensation Agreements | Proponent | 0 | 720h | 100%
Environment Plans | DMP ED | 0 | 240h | 100%
Data submission | Proponent | 0 | 8h | 100%
EXPLORATION ACTIVITY (seismic, drilling, interpreting data) | Proponent | 0 | 1,920h | 100%
Licence to Take water (s5c RIWA) | DOW | 0 | 480h | 100%
Native Vegetation Clearing Approvals (schedule 6) (EP Act) | DMP ED | 0 | 480h | 100%
Submit application | Proponent | 0 | 0h | 100%
Assess Technical Report | DMP PD | 0 | 240h | 100%
Assess Well Operation Management Plan (WOMP) and Drill Program | DMP PD | 0 | 240h | 100%
Assess Safety Management System | DMP RSD | 0 | 160h | 100%
Environment Plans | DMP ED | 0 | 240h | 100%
Data submission | Proponent | 0 | 8h | 100%
Submit application | Proponent | 0 | 0h | 100%
Assess Technical Report | DMP PD | 0 | 240h | 100%
Assess Well Operation Management Plan (WOMP) and Drill Program | DMP PD | 0 | 240h | 100%
Assess Safety Management System | DMP RSD | 0 | 160h | 100%
Environment Plans | DMP ED | 0 | 240h | 100%
Data submission | Proponent | 0 | 8h | 100%
EXPLORATION ACTIVITY | Proponent | 0 | 8,000h | 100%
Notice of Discovery | Proponent | 0 | 8h | 100%
Submit application | Proponent | 0 | 0h | 100%
Assess Technical Report | DMP PD | 0 | 240h | 100%
Assess Well Operation Management Plan (WOMP) and Drill Program | DMP PD | 0 | 240h | 100%
Assess Safety Management System | DMP RSD | 0 | 160h | 100%
Environment Plans | DMP ED | 0 | 240h | 100%
Data submission | Proponent | 0 | 8h | 100%
application and technical assessment | DMP PD | 0 | 240h | 100%
Extended Production Testing | Proponent | 0 | 960h | 100%
Submit application | Proponent | 0 | 8h | 100%
Preliminary Field Development Plan and Schedule | DMP PD | 0 | 240h | 100%
Technical Report | DMP PD | 0 | 240h | 100%
WOMP & Drill Program | DMP PD | 0 | 240h | 100%
Environment Plans | DMP ED | 0 | 240h | 100%
Safety Management System(re-entry) | DMP RSD | 0 | 160h | 100%
Data submission | Proponent | 0 | 8h | 100%
Submit application | Proponent | 0 | 0h | 100%
Assess Technical Report | DMP PD | 0 | 240h | 100%
Assess Well Operation Management Plan (WOMP) and Drill Program | DMP PD | 0 | 240h | 100%
Assess Safety Management System | DMP RSD | 0 | 160h | 100%
Access and Compensation Agreements | Proponent | 0 | 720h | 100%
Environment Plans | DMP ED | 0 | 240h | 100%
Data submission | Proponent | 0 | 8h | 100%
Submit application | Proponent | 0 | 0h | 100%
Assess Technical Report | DMP PD | 0 | 240h | 100%
Assess Well Operation Management Plan (WOMP) and Drill Program | DMP PD | 0 | 240h | 100%
Assess Safety Management System | DMP RSD | 0 | 160h | 100%
Access and Compensation Agreements | Proponent | 0 | 720h | 100%
Environment Plans | DMP ED | 0 | 240h | 100%
Data submission | Proponent | 0 | 8h | 100%
Submit application | Proponent | 0 | 8h | 100%
advertised (ss8(4)) | DMP PD | 0 | 240h | 100%
notification (ss8(3)(b)) | Proponent | 0 | 224h | 100%
Acquire land tenure (Land Administration Act) | Proponent/Landgate | 0 | 240h | 100%
grant | DMP PD | 0 | 240h | 100%
Safety Management Case | DMP RSD | 0 | 240h | 100%
Environment Plans | DMP ED | 0 | 240h | 100%
Native Vegetation Clearing Approvals (schedule 6) (EP Act) | DMP ED | 0 | 240h | 100%
Heritage Clearance | DIA | 0 | 240h | 100%
Safety Management Case | DMP RSD | 0 | 240h | 100%
Environment Plans | DMP PD | 0 | 240h | 100%
PILOT ACTIVITY | Proponent | 0 | 5,840h | 100%
Application Submitted | Proponent | 0 | 8h | 100%
Assessment of application | DMP PD | 0 | 240h | 100%
Final Field Development Plan and Schedule | DMP PD | 0 | 240h | 100%
Determine and approve royalty regime | DMP | 0 | 240h | 100%
Native Title Agreements | DMP/NNTT | 0 | 1,480h | 100%
Advertised (s29 NTA) | DMP MTD | 0 | 720h | 100%
Administration | DMP/NNTT | 0 | 480h | 100%
"Right to Negotiate" | DMP/NNTT | 0 | 1,000h | 100%
State Deed (s31) | DMP PD | 0 | 144h | 100%
Offer of grant | DMP PD | 0 | 240h | 100%
Consideration of offer | Proponent | 0 | 480h | 100%
Award of Licence | DMP PD | 0 | 8h | 100%
Production Facility Approval | DMP PD | 0 | 480h | 100%
Safety Management Case | DMP RSD | 0 | 240h | 100%
Environment Plans | DMP ED | 0 | 240h | 100%
Native Vegetation Clearing Approvals (schedule 6) (EP Act) | DMP ED | 0 | 240h | 100%
Heritage Clearance | DIA | 0 | 240h | 100%
Safety Management Case | DMP RSD | 0 | 240h | 100%
Environment Plans | DMP PD | 0 | 240h | 100%
State Environmental Assessment (Pt 4 EP Act) | OEPA | 0 | 5,144h | 100%
EP Act Referral (s38 EP Act)/Public comment period | Proponent | 0 | 56h | 100%
EPA consideration/Advice to proponent on whether to Assess and level of assessment | OEPA | 0 | 224h | 100%
Proponent prepares ESD/EPA receives 1st draft ESD | Proponent | 0 | 112h | 100%
OEPA comments on 1st draft ESD | OEPA | 0 | 280h | 100%
Proponents prepares revised ESD | Proponent | 0 | 168h | 100%
EPA authorises release of ESD for Public Review | OEPA | 0 | 112h | 100%
Summary of submissions provided to proponent | OEPA | 0 | 112h | 100%
Proponent response to submissions and revision of ESD | Proponent | 0 | 168h | 100%
ESD Approval | OEPA | 0 | 280h | 100%
Proponent prepares draft ERMP/EPA receives 1st draft ERMP | Proponent | 0 | 720h | 100%
OEPA provides comments on ERMP document | OEPA | 0 | 336h | 100%
Proponent revised ERMP document | Proponent | 0 | 336h | 100%
EPA authorises release of ERMP for public review | OEPA | 0 | 112h | 100%
OEPA provides summary of submissions to proponent | OEPA | 0 | 168h | 100%
Proponent prepares submission summary and response | Proponent | 0 | 336h | 100%
OEPA reviews response to submissions | OEPA | 0 | 392h | 100%
EPA consults with proponent and key agencies on condistions | OEPA | 0 | 112h | 100%
EPA report and recommendations prepared/EPA report published | OEPA | 0 | 280h | 100%
Minister considers EPA report/Minister makes decision | OEPA | 0 | 112h | 100%
State Works Approval & Licensing (Pt 5 EP Act) | DEC | 0 | 480h | 100%
Advertised | DEC | 0 | 168h | 100%
Works (s52/53 EP Act) - Application/Assessment/Approval | DEC | 0 | 480h | 100%
License to discharge etc (s56 EP Act) - Approval/Assessment/Licence Issued | DEC | 0 | 480h | 100%
Registration of Prescribed Premises (r5A EPR) - Application/Assessment/Approval | DEC | 0 | 160h | 100%
Submit application | Proponent | 0 | 0h | 100%
Assess Technical Report | DMP PD | 0 | 240h | 100%
Assess Well Operation Management Plan (WOMP) Drill Program, Well Intervention and Well Abandonment plan | DMP PD | 0 | 240h | 100%
Assess Safety Management System | DMP RSD | 0 | 160h | 100%
Heritage Clearance | DIA | 0 | 240h | 100%
Access and Compensation Agreements | Proponent | 0 | 720h | 100%
Environment Plans | DMP ED | 0 | 720h | 100%
Data submission | Proponent | 0 | 8h | 100%
Quarterly Reports (Safety, Environment, Resource) | Proponent | 0 | 39,736h | 100%
Field Development Plan | DMP PD | 0 | 31,320h | 100%
Field Development Plan 5 year | DMP PD | 0 | 0h | 100%
Field Development Plan 10 year | DMP PD | 0 | 0h | 100%
Field Development Plan 15 year | DMP PD | 0 | 0h | 100%
Field Development Plan 20 year | DMP PD | 0 | 0h | 100%
Safety Case | DMP RSD | 0 | 31,320h | 100%
Safety Case 5 year | DMP RSD | 0 | 0h | 100%
Safety Case 10 year | DMP RSD | 0 | 0h | 100%
Safety Case 15 year | DMP RSD | 0 | 0h | 100%
Safety Case 20 year | DMP RSD | 0 | 0h | 100%
Environment Plans | DMP ED | 0 | 31,320h | 100%
Environment Plans 5 year | DMP ED | 0 | 0h | 100%
Environment Plans 10 year | DMP ED | 0 | 0h | 100%
Environment Plans 15 year | DMP ED | 0 | 0h | 100%
Environment Plans 20 year | DMP ED | 0 | 0h | 100%
Safety Case | DMP RSD | 0 | 240h | 100%
Environment Plans | DMP ED | 0 | 240h | 100%
WOMP & Plug and Abandonment Plan | DMP PD | 0 | 240h | 100%
Decommissioning Plan | DMP PD | 0 | 240h | 100%
Removal of Surface Facilities & Pipeline Rehabilitation | DMP PD | 0 | 240h | 100%
Land Rehabilitation | DMP ED | 0 | 240h | 100%
Contaminated Sites Clearance | DEC | 0 | 240h | 100%
Surrender | DMP PD | 0 | 8h | 100%